## Sheet2
[5 empty] | Years (Date) | 2026 | Years (Date) | 2026 | Years (Date) | 2026 | Years (Date) | 2026 | Years (Date) | 2026
[5 empty] | Months (Date) | Feb | Months (Date) | Feb | Months (Date) | Feb | Months (Date) | Feb | Months (Date) | Feb
Years (Date) | 2026 |  |  |  | Days (Date) | (All) | Days (Date) | (All) | Days (Date) | 12-Feb | Days (Date) | 12-Feb | Days (Date) | (All)
Count of Current Status |  | Current Status |  |  | Count of Current Status | Current Status | Count of Current Status | Current Status | Count of Current Status | Current Status | Count of Current Status |  | Count of Current Status
Months (Date) | Days (Date) | Completed | Ongoing | Hold | Panel | Completed | Panel | Completed | Panel | Ongoing | Current Status | Total | Current Status | Total
Feb | 02-Feb | 14 | 4 | 1 | Contractor dewatering Pump | 59 | Contractor dewatering Pump | 59 | Borehole pump | 1 | Ongoing | 18 | Ongoing | 82
| 03-Feb | 21 |  | 1 | Diesel Driven CP Pump | 32 | Diesel Driven CP Pump | 32 | Generator | 2 | Completed | 7 | Hold | 5
| 04-Feb | 21 | 4 |  | Generator | 31 | Generator | 31 | Other | 2 | Grand Total | 25 | Completed | 173
| 05-Feb | 24 | 4 |  | Panel | 20 | Panel | 20 | Panel | 2 |  |  | Grand Total | 260
| 06-Feb | 13 | 15 | 2 | Submersible pump | 9 | Submersible pump | 9 | Contractor dewatering Pump | 3
| 07-Feb | 22 | 9 |  | Borehole pump | 8 | Borehole pump | 8 | Submersible pump | 3
| 09-Feb | 14 | 14 |  | Submersible pumps | 7 | Submersible pumps | 7 | Diesel Driven CP Pump | 5
| 10-Feb | 18 | 7 | 1 | Other | 7 | Other | 7 | Grand Total | 18
| 11-Feb | 19 | 7 |  | Grand Total | 173 | Grand Total | 173
| 12-Feb | 7 | 18
Grand Total |  | 173 | 82 | 5

## Dash Board Final
260
Total Task FEB
173
Total Task Completed
Delay Completion
Task Today
Task Completed Today
7
Work Shop Daily Activity FEB 2026

## Man Hours
Years (Date) | 2026
Months (Date) | Feb
Sum of Total Hours | Employee Name
Days (Date) | Suresh | Suraj | Harish | Aman | Cherith | Ismail | Shaji | Saqib | Bharathesha | Bilal | Zaheer | Fahad | James | Faisal | Suhaib | Vinod | Anwar | Mintu | Ghiyan | Martino | Afsar | Donald | Venu | Jagdev | Mamun | Lijo | Suleman | Grand Total
02-Feb | 9 | 22 | 9 | 11 | 11 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 9 | 9 | 9 | 9 | 3.5 | 3.5 | 7 | 9 | 9 |  | 229
03-Feb | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 |  | 9 | 9 | 3.5 | 3.5 | 9 |  | 9 |  | 205
04-Feb | 18 | 11 | 9 | 9 | 9 | 12.5 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9.5 | 9 |  | 9 | 9 | 9 | 9 |  |  | 9 | 231
05-Feb | 18 | 5 | 12 | 9 | 9 | 6 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 16 | 3 | 9 | 9 |  | 9 | 9 |  | 9 |  | 9 | 222
Grand Total | 54 | 47 | 39 | 38 | 38 | 36.5 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 34 | 30.5 | 27 | 27 | 27 | 25 | 25 | 25 | 18 | 18 | 18 | 887

## Daily_Activity_Tracker
Area | Date | Employee Name | Panel | Fleet Number | Task Description | Task Start Date | Planned Completion Date | Actual Completion Date | Repair Status | Task Start Time(Today) | Task End Time(Today) | Total Hours | Current Status | Remarks
Bay 4&5 - Pumps | 2025-12-03 | Suresh S | Contractor dewatering Pump | 2X CP150 | vaccum Pump repair | 2025-12-03 | 2025-12-03 | 0 |  | 8:00 | 15:30 | 7.5 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Ismail | Contractor dewatering Pump | PT175-522 | Pump assembling | 2025-11-28 | 2025-12-02 | 4 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Shaji | [7 empty] | 7:30 | 9:30 | 2
Bay 4&5 - Pumps | 2025-12-03 | Bharathesha | Contractor dewatering Pump | CP150-218 | Pump repair & water test | 2025-11-27 | 2025-12-01 | 2025-12-03 |  | 7:30 | 12:30 | 5 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Shaji | [7 empty] | 9:30 | 11:30 | 2
Bay 4&5 - Pumps | 2025-12-03 | Bharathesha | Contractor dewatering Pump | CP150-676 | Contractor dewatering Pump | 2025-12-03 | 2025-12-03 | 2025-12-04 |  | 12:30 | 16:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Mintu | Contractor dewatering Pump | PT175-515 | Engine prepapre for assembling, gear dismantled & repairing. | 2025-11-28 | 2025-12-01 | 2025-12-03 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Shaji | [7 empty] | 15:00 | 17:00 | 2
Bay 4&5 - Pumps | 2025-12-03 | James | Contractor dewatering Pump | CP150-002 | Engine repair & water testing | 2025-11-28 | 2025-12-03 | 2025-12-02 |  | 8:00 | 11:00 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Shaji | [7 empty] | 11:30 | 15:00 | 3.5
Bay 4&5 - Pumps | 2025-12-03 | James | Contractor dewatering Pump | CP150V-001 | Pump dismantle | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 15:00 | 17:00 | 2 | Ongoing
Bay 6 - Generator | 2025-12-03 | Shakeel | Generator | GEN200-014 | Oil service | 2025-11-28 | 2025-12-03 | 2025-12-03 |  | 7:30 | 10:30 | 3 | Completed
Bay 6 - Generator | 2025-12-03 | Shakeel | Generator | GEN250-051 | Oil service, Silencer fabrication work. | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 10:30 | 15:30 | 5 | Completed
Bay 6 - Generator | 2025-12-03 | Jagdev | Generator | GEN20-002 | FIP & injector filing, fuel tank cleaning, valave guard & gegenral repair | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 7:30 | 12:30 | 5 | Completed
Bay 6 - Generator | 2025-12-03 | Jagdev | Generator | GENJ80-027 | fuel tank cleaning, valave guaging & genenral repair | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 7:30 | 9:30 | 2 | Completed
Bay 6 - Generator | 2025-12-03 | Jagdev | Generator | GEN7-008 | General repair, ac alternator service, dc charging, oil service | 2025-11-28 | 2025-12-03 | 2025-12-03 |  | 13:00 | 16:30 | 3.5 | Completed
Electrical | 2025-12-03 | Fahad | Panel | SPB95-001 | Power & control wiring | 2025-11-28 | 2025-12-03 | 2025-12-03 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-03 | Lijo | Panel | SPB22.037 | Repairing & testing | 2025-11-28 | 2025-12-03 | 2025-12-03 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-03 | Shahanawaz | Panel | General work | Lock holder & alarm system, cutting & drilling | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-03 | Charith | Generator | GEN250-043 | Ac alternator inspection & servicing assembling | 2025-12-03 |  | 2025-12-04 |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-03 | Aman |  |  |  | 2025-12-03 |  |  |  | 7:30 | 17:00 | 9.5
Electrical | 2025-12-03 | Ghiyan | Submersible pump | SM1002-140 | Stator rewinding | 2025-11-29 | 2025-12-03 |  |  | 7:30 | 16:30 | 9 | Hold
Electrical | 2025-12-03 | Venu | Borehole pump | 2.2kw | 25nos pump inspection checking & socket fixing & number tagging | 2025-12-03 | 2025-12-03 | 2025-12-04 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-03 | Afsar | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-03 | Donal | Submersible pump | SM1002/SM530 | 3nos pumps water test | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-03 | Saqib | [7 empty] | 7:30 | 17:00 | 9.5
Bay 4&5 - Pumps | 2025-12-03 | Asif | Diesel Driven CP Pump | CP1212S15-015 | Float & vaccum pump repairing, vaccum testing, NRV repairing | 2025-12-03 | 2025-12-06 | 2025-12-06 |  | 7:30 | 13:00 | 5.5 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Martino | [7 empty] | 7:30 | 13:00 | 5.5
Bay 4&5 - Pumps | 2025-12-03 | Vinod | Diesel Driven CP Pump | CD300M-03 | Injector and turbo installation and top cover gasket replacement | 2025-11-12 | 2025-12-09 | 2025-12-09 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-03 | Jahir | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-03 | Asif | General work | General work | System work for work orders & IDT | 2025-12-03 | 2025-12-03 | 2025-12-03 |  | 15:30 | 16:30 | 1 | Completed
Bay 4&5 - Pumps | 2025-12-04 | Suresh S | Contractor dewatering Pump | CP150-033 | vaccum Pump repair & test | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-04 | Ismail | Contractor dewatering Pump | PT175-515 | Pump assembling | 2025-11-28 | 2025-12-04 | 2025-12-04 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps |  | Shaji | [5 empty] | 2025-12-04 |  | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-04 | Bharathesha | Contractor dewatering Pump | CP150-676 | Cylinder head repairing | 2025-12-03 | 2025-12-04 | 2025-12-04 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-04 | Mintu | Contractor dewatering Pump | PT175-515 | Engine assembling | 2025-11-28 | 2025-12-04 | 2025-12-04 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps |  | Shaji | [5 empty] | 2025-12-04 |  | 9:30 | 11:30 | 2
Bay 4&5 - Pumps | 2025-12-04 | James | Contractor dewatering Pump | CP150V-001 | Pump dismantling & prepare for assembling | 2025-12-03 | 2025-12-04 | 2025-12-04 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps |  | Shaji | [5 empty] | 2025-12-04 |  | 11:30 | 15:00 | 3.5
Bay 4&5 - Pumps | 2025-12-04 | Shaji | Other | System work | System work for work orders & IDT | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 15:00 | 17:00 | 2 | Completed
Bay 6 - Generator | 2025-12-04 | Shakeel | Generator | GEN20-002 | Load testing & cable connection | 2025-12-03 | 2025-12-04 | 2025-12-04 |  | 7:30 | 9:30 | 2 | Completed
Bay 6 - Generator |  | Saqib khan | [5 empty] | 2025-12-04 |  | 8:30 | 9:30 | 1
Bay 6 - Generator | 2025-12-04 | Shakeel | Generator | GENJ80-027 | Load testing & cable connection | 2025-12-03 | 2025-12-04 | 2025-12-04 |  | 9:30 | 11:00 | 1.5 | Completed
Bay 6 - Generator |  | Saqib khan | [7 empty] | 9:30 | 11:00 | 1.5
Bay 6 - Generator | 2025-12-04 | Shakeel | Generator | GEN150-053 | Load testing & cable connection | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 14:30 | 16:30 | 2 | Completed
Bay 6 - Generator |  | Saqib khan | [7 empty] | 15:30 | 16:30 | 1
Bay 6 - Generator | 2025-12-04 | Jagdev | Generator | GEN250-044 | FIP & injector filing, fuel tank cleaning, valave guard & gegenral repair | 2025-11-18 | 2025-12-04 |  |  | 13:00 | 16:30 | 3.5 | Completed
Bay 6 - Generator | 2025-12-04 | Suraj | [7 empty] | 13:00 | 16:30 | 3.5
Bay 6 - Generator | 2025-12-04 | Jagdev | Generator | GEN150-053 | General repair, fuel tank cleaning, coolant change, valve gauging | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 7:30 | 12:30 | 5 | Completed
Bay 6 - Generator |  | Suraj | [5 empty] | 2025-12-04 |  |  |  | 0
Electrical | 2025-12-04 | Fahad | Panel | SPB95-001 | Enclosure cutting & door wiring | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-04 | Lijo | Other | Electrical section | Panel section wiring & light fixing. | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-04 | Shahanawaz | Other | Electrical section | Panel section wiring & light fixing. | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-04 | Charith | Generator | GEN250-043 | Ac alternator inspection & servicing assembling | 2025-12-03 | 2025-12-04 | 2025-12-04 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical |  | Aman | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-04 | Ghiyan | Submersible pump | SM1002-140 | Stator rewinding | 2025-11-29 | 2025-12-04 | 2025-12-04 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-04 | Venu | Borehole pump | 2.2kw | 13nos pump inspection checking & socket fixing & number tagging | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical |  | Suhaib | [5 empty] | 2025-12-04 |  | 7:30 | 17:00 | 9.5
Electrical | 2025-12-04 | Suhaib |  |  |  | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 12:00 | 16:30 | 4.5
Electrical | 2025-12-04 | Suhaib | Submersible pump | SM1002-140 | Water testing | 2025-12-04 | 2025-12-03 | 2025-12-04 |  | 12:00 | 16:00 | 4 | Completed
Electrical | 2025-12-04 | Saqib | Submersible pump | SM1002 | pumps water test | 2025-12-04 | 2025-12-04 |  |  | 7:30 | 12:00 | 4.5 | Ongoing
Bay 4&5 - Pumps | 2025-12-04 | Asif | Diesel Driven CP Pump | ACT12-27/28 | Coolant & oil filling, gauges & connections installation. | 2025-12-04 | 2025-12-08 |  |  | 7:30 | 13:00 | 5.5 | Completed
Bay 4&5 - Pumps |  | Martino | [7 empty] | 7:30 | 13:00 | 5.5
Bay 4&5 - Pumps | 2025-12-04 | Vinod | Diesel Driven CP Pump | CD300M-033 | Water testing & removing from bay | 2025-12-04 | 2025-12-08 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps |  | Jahir | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2025-12-04 | Jahir | [7 empty] | 6:30 | 13:00 | 6.5
Bay 4&5 - Pumps | 2025-12-04 | Asif | Other | General work | System work for work orders & IDT | 2025-12-04 | 2025-12-04 | 2025-12-04 |  | 15:30 | 16:30 | 1 | Completed
Bay 4&5 - Pumps | 2025-12-04 | Asif | Diesel Driven CP Pump | ACT12-29/30 | Coolant & oil filling, gauges & connections installation. | 2025-12-04 | 2025-12-06 | 2025-12-04 |  | 14:00 | 15:30 | 1.5 | Completed
Bay 4&5 - Pumps | 2025-12-04 | Allah Ditta | Diesel Driven CP Pump | CP220S12SP-029/031/032 | Inspection, fuel filling connections, Starting PDI | 2025-12-04 | 2025-12-05 | 2025-12-04 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-04 | Vinod | Diesel Driven CP Pump | CP1212-006 | Inspection, vaccum testing | 2025-12-04 | 2025-12-06 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2025-12-04 | Jahir | [7 empty] | 13:00 | 16:30 | 3.5
Bay 4&5 - Pumps | 2025-12-05 | Suresh S | Contractor dewatering Pump | CP150-033 | Vaccum Pump repair & test | 2025-12-04 | 2025-12-05 | 2025-12-05 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-05 | Suresh S | Contractor dewatering Pump | PT175-515 | Engine assembling | 2025-12-04 | 2025-12-05 |  |  |  |  | 0 | Ongoing
Bay 4&5 - Pumps | 2025-12-05 | Shaji | [9 empty] | 0
Bay 4&5 - Pumps | 2025-12-05 | Ismail | Contractor dewatering Pump | PT175-515 | Pump assembling | 2025-11-28 | 2025-12-05 | 2025-12-05 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2025-12-05 | Bharathesha | Contractor dewatering Pump | CP150-676 | Engine repair & test | 2025-12-03 | 2025-12-05 | 2025-12-05 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Mintu | Contractor dewatering Pump | PT175-515 | Engine assembling | 2025-11-28 | 2025-12-04 |  |  | 8:00 | 17:00 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-05 | James | Contractor dewatering Pump | CP150V-001 | Pump assembling | 2025-12-03 | 2025-12-05 | 2025-12-05 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2025-12-05 | Shaji | Other | System work | System work for work orders & IDT | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 15:00 | 17:00 | 2 | Completed
Bay 6 - Generator | 2025-12-05 | Shakeel | Generator | GEN250-012 | DSE configuration & load test | 2025-12-05 | 2025-12-05 |  |  | 7:30 | 10:30 | 3 | Ongoing
Bay 6 - Generator | 2025-12-05 | Shakeel | Generator | GEN250-044 | Load testing & cable connection | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 10:30 | 3:30 | 17 | Completed
Bay 6 - Generator | 2025-12-05 | Shakeel | Generator | GEN150-053 | Load testing & cable connection | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 14:30 | 16:30 | 2 | Completed
Bay 6 - Generator | 2025-12-05 | Jagdev | Generator | GEN150-053 | FIP, injector & radiator remove | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 7:30 | 13:00 | 5.5 | Completed
Bay 6 - Generator | 2025-12-05 | Suraj | [7 empty] | 7:30 | 13:00 | 5.5
Bay 6 - Generator | 2025-12-05 | Jagdev | Generator | GENJ135-002 | Ac alternator remove & service | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 6 - Generator | 2025-12-05 | Suraj | [7 empty] | 14:00 | 16:30 | 2.5
Electrical | 2025-12-05 | Fahad | Panel | SPB95-001 | Ventilation fan fixing | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 8:00 | 12:00 | 4 | Completed
Electrical | 2025-12-05 | Fahad | Panel | DB-289 | Reparing & safety cover making | 2025-12-05 | 2025-12-05 |  |  | 12:00 | 18:00 | 6 | Ongoing
Electrical | 2025-12-05 | Lijo | Other | Electrical section | Panel section wiring & light fixing. | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-05 | Shahanawaz | Other | Electrical section | Panel section wiring & light fixing. | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-05 | Aman | Generator | GEN40-003 | Ac alternator inspection & servicing assembling | 2025-12-04 | 2025-12-05 |  |  | 7:30 | 12:00 | 4.5 | Ongoing
Electrical | 2025-12-05 | Charith | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-05 | Ghiyan | Submersible pump | FM150 | 8nos new flowmeter fixing, cable & socket | 2025-12-05 | 2025-12-05 |  |  | 7:30 | 16:00 | 8.5 | Completed
Electrical | 2025-12-05 | Ghiyan | Generator | GEN250-021 | Load testing | 2025-12-05 | 2025-12-05 |  |  | 16:00 | 17:00 | 1 | Completed
Electrical | 2025-12-05 | Venu | Borehole pump | New 2.2kw | 25nos pump inspection checking & socket fixing & number tagging | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-05 | Suhaib |  |  |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 7:30 | 17:00 | 9.5
Electrical | 2025-12-05 | Saqib | Submersible pump | SM1002-125 | Rotor repair & assembling | 2025-12-05 | 2025-12-06 |  |  | 7:30 | 17:30 | 10 | Ongoing
Bay 4&5 - Pumps | 2025-12-05 | Allah ditta | Diesel Driven CP Pump | CD300M-03 | Installation on test bay & testing | 2025-12-05 | 2025-12-10 | 2025-12-05 |  | 7:30 | 17:30 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Martino | [7 empty] | 7:30 | 13:00 | 5.5
Bay 4&5 - Pumps | 2025-12-05 | Allah ditta | Diesel Driven CP Pump | HL130M-07 |  | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 14:00 | 17:00 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Vinod | Diesel Driven CP Pump | CP1212-006 | Vaccum testing & fuel line replacement | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 8:00 | 11:00 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Jahir | Other | BA180-002 | General work with quality controller | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Asif | Diesel Driven CP Pump | CP220S12SP-029/031/032 | General work & PDI flowfinity | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 7:00 | 12:00 | 5 | Completed
Bay 4&5 - Pumps | 2025-12-05 | Asif | Other | System work | IDT & system work | 2025-12-05 | 2025-12-05 | 2025-12-05 |  | 13:00 | 15:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Suresh S | Contractor dewatering Pump | CP150 | Vaccum Pump repair for site | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 8:00 | 11:00 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-08 | Suresh S | Contractor dewatering Pump | CP150-033 | Pump dismantle & prepare for assemble | 2025-12-04 | 2025-12-08 | 2025-12-08 |  | 11:00 | 19:30 | 8.5 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2025-12-08 | Ismail | Contractor dewatering Pump | PT175-554 | Pump assembling ongoing | 2025-12-06 | 2025-12-08 | 2025-12-08 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Shaji | [7 empty] | 10:30 | 11:30 | 1
Bay 4&5 - Pumps | 2025-12-08 | Bharathesha | Contractor dewatering Pump | CP150V-009 | Pump repair & water test | 2025-12-05 | 2025-12-08 | 2025-12-08 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-08 |  |  |  |  | 2025-12-05 | 2025-12-08 | 2025-12-08 |  | 7:30 | 11:30 | 4
Bay 4&5 - Pumps | 2025-12-08 | Bharathesha | Contractor dewatering Pump | CP150-574 | Pump & engine repair, test failed, mechanical seal leakage | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 11:30 | 18:30 | 7 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Mintu | Contractor dewatering Pump | PT175-515 | Engine assembling ongoing | 2025-11-28 | 2025-12-08 | 2025-12-08 |  | 8:00 | 11:30 | 3.5 | Completed
Bay 4&5 - Pumps | 2025-12-08 | James | Contractor dewatering Pump | CP150V-001 | Pump assembling ongoing | 2025-12-03 | 2025-12-08 | 2025-12-08 |  | 10:00 | 19:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Shaji | [7 empty] | 11:30 | 13:00 | 1.5
Bay 4&5 - Pumps | 2025-12-08 | James | Contractor dewatering Pump | CP150-694 | Pump & engine minor repair | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 8:00 | 10:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Imran |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 8:00 | 10:00 | 2
Bay 4&5 - Pumps | 2025-12-08 | Shaji | Other | System work | System work for work orders & IDT | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 14:00 | 17:00 | 3 | Completed
Bay 6 - Generator | 2025-12-08 | Jagdev | Generator | GEN200-009 | General repair, fuel tank cleaning, Ac alternator fixing | 2025-12-06 | 2025-12-08 | 2025-12-08 |  | 7:30 | 13:00 | 5.5 | Completed
Bay 6 - Generator | 2025-12-08 | Harish | [7 empty] | 7:30 | 13:00 | 5.5
Bay 6 - Generator | 2025-12-08 | 142744 | Generator | GENJ150-021 | General repair safety guard fixing, load test/ac alternator fail need to service | 2025-12-08 | 2025-12-08 |  |  | 7:30 | 12:00 | 4.5 | Hold
Bay 6 - Generator | 2025-12-08 | 143344 | [7 empty] | 7:30 | 12:00 | 4.5
Bay 6 - Generator | 2025-12-08 | 142744 | Generator | GEN20-002 | Silencer cleaning & fixing, load test | 2025-12-05 | 2025-12-08 | 2025-12-08 |  | 13:00 | 16:30 | 3.5 | Completed
Bay 6 - Generator | 2025-12-08 | Jagdev |  |  |  | 2025-12-05 | 2025-12-08 | 2025-12-08 |  | 13:00 | 16:30 | 3.5
Bay 6 - Generator | 2025-12-08 | Ghiyan | Generator | GEN20-002 | Cable connection & load test | 2025-12-05 | 2025-12-08 | 2025-12-08 |  | 15:00 | 15:30 | 0.5 | Completed
Bay 6 - Generator | 2025-12-08 | Ghiyan | Generator | GEN200-009 | Cable connection | 2025-12-06 | 2025-12-08 | 2025-12-08 |  | 15:30 | 16:30 | 1 | Completed
Electrical | 2025-12-08 | Fahad | Other | General work | New employee training & general work | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-08 | Lijo | Panel | DB-289 | Enclosure replacement repairing & stand fixing | 2025-12-06 | 2025-12-08 | 2025-12-08 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-08 | Shahanawaz | Panel | SPB15-010 | Testing & PDI, general work in mechanical section. | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 7:30 | 11:30 | 4 | Completed
Electrical | 2025-12-08 | 142862 |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 11:00 | 16:30 | 5.5
Electrical | 2025-12-08 | Aman | Generator | GEN250-051 | RC stator winding | 2025-12-06 | 2025-12-11 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-08 | Charith | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-08 | Ghiyan | Submersible pump | FM150 | 2nos new flowmeter fixing, cable & socket | 2025-12-08 | 2025-12-08 |  |  | 7:30 | 9:30 | 2 | Ongoing
Electrical | 2025-12-08 | Ghiyan | Generator | GEN250-021 | Load testing | 2025-12-05 | 2025-12-05 |  |  | 16:00 | 17:00 | 1 | Ongoing
Electrical | 2025-12-08 | Venu | Borehole pump | New 3kw | 25nos pump inspection checking & socket fixing & number tagging | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 7:30 | 13:00 | 5.5 | Completed
Electrical | 2025-12-08 | Suhaib |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 7:30 | 13:00 | 5.5
Electrical | 2025-12-08 | Venu | Borehole pump | New 2.2kw | 10nos pump inspection checking & socket fixing & number tagging | 2025-12-08 | 2025-12-08 | 2025-12-08 |  |  |  | 0 | Completed
Electrical | 2025-12-08 | Suhaib |  |  |  | 2025-12-08 | 2025-12-08 | 2025-12-08 |  |  |  | 0
Electrical | 2025-12-08 | Saqib | Submersible pump | SM1002-126 | Rotor repair & assembling | 2025-12-08 | 2025-12-09 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-08 | Allah ditta | Diesel Driven CP Pump | AC825-05 | Radiator installation & engine service | 2025-12-08 | 2025-12-20 | 2025-12-08 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-08 | Martino | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-08 | Vinod | Diesel Driven CP Pump | BA180-002 | Pump assembling | 2025-12-08 | 2025-12-15 |  |  | 8:00 | 17:00 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-08 | Jahir |  |  |  | 2025-12-08 | 2025-12-15 |  |  | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-08 | Asif | Other | General work | General work & system work | 2025-12-08 | 2025-12-08 | 2025-12-08 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Ismail | Contractor dewatering Pump | PT175-554 | Pump assembling | 2025-12-06 | 2025-12-06 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-06 | Bharathesha | Contractor dewatering Pump | CP150V-009 | Pump repair and water test | 2025-12-05 | 2025-12-06 |  |  | 7:30 | 8:30 | 1 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Mintu | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-06 | Suresh S | Contractor dewatering Pump | CP150-033 | Pump dismantling and prepare for assembling | 2025-12-04 | 2025-12-06 |  |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2025-12-06 | James | Contractor dewatering Pump | CP150V-001 | Pump assembling | 2025-12-03 | 2025-12-06 |  |  | 8:00 | 17:00 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-06 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 6 - Generator | 2025-12-06 | Suraj | Generator | GEN40-003 | Alternator fixing, Fuel tank cleaning | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 7:30 | 13:00 | 5.5 | Completed
Bay 6 - Generator | 2025-12-06 | Jagdev | Generator | GEN200-009 | Alternator fixing, Fuel tank cleaning | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 6 - Generator | 2025-12-06 | Suraj | [7 empty] | 14:00 | 16:30 | 2.5
Bay 6 - Generator | 2025-12-06 | Jagdev | Drill rig | DR-024 | Repair on site | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 7:30 | 14:00 | 6.5 | Completed
Electrical | 2025-12-06 | Fahad | Panel | SPB3.7-029 | Repair on site | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 8:00 | 12:00 | 4 | Completed
Electrical | 2025-12-06 | Fahad | Panel | SPB3.7-100 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-06 | Lijo | Panel | DB-289 | Enclosure replacement | 2025-12-06 | 2025-12-08 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2025-12-06 | Shahanawaz | Panel | SPB15-010 | Canopy and alarm system fixing | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-06 | Aman | Generator | GEN250-051 | Alternator rewinding | 2025-12-06 | 2025-12-11 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2025-12-06 | Charith | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-06 | Ghiyan | Contractor dewatering Pump | FM150 | 8nos new flowmeter fixing, cable & socket | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-06 | Venu | Borehole pump | New 2.2kw | 12nos pump inspection checking & socket fixing & number tagging | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-06 | Suhaib |  |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 8:00 | 12:00 | 4
Electrical | 2025-12-06 | Venu | Borehole pump | New 3kw | 10nos pump inspection checking & socket fixing & number tagging | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 13:00 | 16:30 | 3.5 | Completed
Electrical | 2025-12-06 | Suhaib |  |  |  | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-06 | Saqib | Submersible pump | SM1002-074 | Pump dismantling | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-06 | Saqib | Submersible pump | SM1002-074 | Rotor repair & assembling | 2025-12-06 | 2025-12-08 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2025-12-06 | Allah ditta | Diesel Driven CP Pump | CD300M-03 | Air compressor and priming unit repair, Air line and fuel line replacemnet | 2025-12-06 | 2025-12-10 | 2025-12-06 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Martino |  |  |  | 2025-12-06 | 2025-12-10 | 2025-12-06 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Vinod | Diesel Driven CP Pump | BA180-002 | Parts cleaning, Shaft, bearing seal replacement | 2025-12-06 | 2025-12-12 | 2025-12-06 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Jahir |  |  |  | 2025-12-06 | 2025-12-12 | 2025-12-06 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-06 | Asif | Other | System work | IDT & system work | 2025-12-06 | 2025-12-06 | 2025-12-06 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Suresh S | Contractor dewatering Pump | CP150-033 | Pump assembling & water test | 2025-12-04 | 2025-12-09 | 2025-12-09 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-09 | Ismail | Contractor dewatering Pump | PT175-511 | Pump assembling ongoing | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Shaji | [7 empty] | 8:30 | 9:30 | 1
Bay 4&5 - Pumps | 2025-12-09 | Bharathesha | Contractor dewatering Pump | CP150-574 | Pump dismantling | 2025-12-08 | 2025-12-09 | 2025-12-09 |  | 9:30 | 10:30 | 1 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Shaji | [7 empty] | 7:30 | 11:30 | 4
Bay 4&5 - Pumps | 2025-12-09 | Mintu | Contractor dewatering Pump | PT175-522 | Engine assembling ongoing | 2025-12-08 | 2025-12-09 | 2025-12-09 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Shaji | [7 empty] | 10:30 | 11:30 | 1
Bay 4&5 - Pumps | 2025-12-09 | James | Contractor dewatering Pump | CP150V-001 | Pump assembling ongoing | 2025-12-03 | 2025-12-09 | 2025-12-09 |  | 8:00 | 12:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Shaji | [7 empty] | 11:30 | 13:00 | 1.5
Bay 4&5 - Pumps | 2025-12-09 | Shaji | Other | System work | System work for work orders & IDT | 2025-12-09 | 2025-12-09 |  |  | 14:00 | 17:00 | 3 | Ongoing
Bay 4&5 - Pumps | 2025-12-09 | James | Contractor dewatering Pump | CP150-396 | Engine dismantling | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | 13:00 | 19:00 | 6 | Completed
Bay 6 - Generator | 2025-12-09 | Jagdev | Generator | GENJ250-043 | Ac alternator fixing, fuel pump & injector fixing, valve clearance setting | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2025-12-09 | Harish | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-09 | Suraj | Tank | BFT3-121 | Tank removing & cleaning, new fitting fixing, | 2025-12-08 | 2025-12-09 | 2025-12-09 |  | 7:30 | 14:30 | 7 | Completed
Bay 6 - Generator | 2025-12-09 | Anwar | [7 empty] | 7:30 | 14:30 | 7
Bay 6 - Generator | 2025-12-09 | Suraj | Generator | GEN200-009 | Load test, final fitting | 2025-12-08 | 2025-12-09 |  |  | 14:30 | 14:30 | 0 | Hold
Bay 6 - Generator | 2025-12-09 | Anwar |  |  |  | 2025-12-08 | 2025-12-09 |  |  | 14:30 | 14:30 | 0
Electrical | 2025-12-09 | Fahad | Other | General work | Site task | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-09 | Lijo | Panel | DB-289 | Safety Cover & PDI | 2025-12-09 | 2025-12-09 |  |  | 8:00 | 13:00 | 5 | Ongoing
Electrical | 2025-12-09 | Aman | Generator | GEN250-051 | RC stator winding | 2025-12-06 | 2025-12-11 |  |  | 7:30 | 17:30 | 10 | Ongoing
Electrical | 2025-12-09 | Charith | [7 empty] | 7:30 | 17:30 | 10
Electrical | 2025-12-09 | Ghiyan | Generator | GEN200-009 | Power cable connection | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-09 | Ghiyan | Other | BFM355-008 | welding machine 3units (A,B,C) inspection repair | 2025-12-09 | 2025-12-10 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Electrical | 2025-12-09 | Venu | Borehole pump | New 5.5kw pump | 9nos pump inspection checking & socket fixing & number tagging | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-09 | Suhaib | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-09 | Venu | Borehole pump | Old BH pump 2.2kw | 4nos cable joints & water testing | 2025-12-09 | 2025-12-10 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Electrical | 2025-12-09 | Suhaib | [7 empty] | 13:00 | 16:30 | 3.5
Electrical | 2025-12-09 | Saqib | Submersible pump | SM1002-126 | Rotor repair & assembling | 2025-12-09 | 2025-12-09 | 2025-12-09 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Asif | Diesel Driven CP Pump | ACT900-002 | Air compressor and air drier connection, pressure testing, removing | 2025-12-09 | 2025-12-15 | 2025-12-09 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Allah ditta | Diesel Driven CP Pump | ACT900-001 | Air compressor and air drier connection, pressure testing, removing | 2025-12-09 | 2025-12-15 | 2025-12-09 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Vinod | Diesel Driven CP Pump | CD300M-033 | Radiator installation & testing bay | 2025-12-09 | 2025-12-15 | 2025-12-09 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Jahir |  |  |  |  | 2025-12-15 |  |  | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-09 | Asif | Contractor dewatering Pump | ISO250E-001 | pump coupling dismantling | 2025-12-09 | 2025-12-30 | 2025-12-09 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2025-12-09 | Allah ditta | [7 empty] | 14:00 | 16:30 | 2.5
Bay 4&5 - Pumps | 2025-12-09 | Martino | Diesel Driven CP Pump | AC825-05 | Each muffler piping installation | 2025-12-09 | 2025-12-20 | 2025-12-09 |  | 7:00 | 16:30 | 9.5 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Suresh S | Contractor dewatering Pump | 3XCP150 | Vaccum pump repair | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 8:00 | 18:00 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-10 | James | Contractor dewatering Pump | CP150-396 | Pump dismantle & prepare for assemble | 2025-12-09 | 2025-12-10 | 2025-12-10 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Shaji | [7 empty] | 8:30 | 9:30 | 1
Bay 4&5 - Pumps | 2025-12-10 | Bharathesha | Contractor dewatering Pump | CP150-574 | Pump assembling & engine repair | 2025-12-08 | 2025-12-09 | 2025-12-10 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Shaji | [7 empty] | 9:30 | 11:30 | 2
Bay 4&5 - Pumps | 2025-12-10 | Mintu | Contractor dewatering Pump | PT175-522 | Engine assembling ongoing | 2025-12-08 | 2025-12-10 | 2025-12-10 |  | 8:00 | 11:00 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Shaji | [7 empty] | 11:30 | 12:00 | 0.5
Bay 4&5 - Pumps | 2025-12-10 | Harish | Contractor dewatering Pump | CP150-514 | Pump repair & water test | 2025-12-10 | 2025-12-09 | 2025-12-10 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2025-12-10 | Ismail | Contractor dewatering Pump | PT175-554 | Pump repair & warer test | 2025-11-26 | 2025-12-10 | 2025-12-10 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Shaji | Other | System work | System work for work orders & IDT | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 14:00 | 17:00 | 3 | Completed
Bay 6 - Generator | 2025-12-10 | Jagdev | Generator | GEN150-021 | Canopy & alternator removing | 2025-12-08 | 2025-12-10 | 2025-12-10 |  | 7:30 | 12:00 | 4.5 | Completed
Bay 6 - Generator | 2025-12-10 | Suraj | [7 empty] | 10:30 | 12:00 | 1.5
Bay 6 - Generator | 2025-12-10 | Suraj | Generator | GEN150-047 | PDI & flowfinity | 2025-12-10 | 2025-12-08 | 2025-12-10 |  | 7:30 | 8:30 | 1 | Completed
Bay 6 - Generator | 2025-12-10 | Anwar | [7 empty] | 7:30 | 8:30 | 1
Bay 6 - Generator | 2025-12-10 | Suraj | Generator | GEN40-003 | Load test | 2025-12-08 | 2025-12-10 | 2025-12-10 |  | 8:30 | 10:30 | 2 | Completed
Bay 6 - Generator | 2025-12-10 | Anwar | [7 empty] | 8:30 | 10:30 | 2
Bay 6 - Generator | 2025-12-10 | Suraj | Generator | GEN150-053 | Fuel pump injector fitting, valve clearance setting | 2025-12-10 | 2025-12-09 | 2025-12-10 |  | 12:00 | 16:30 | 4.5 | Completed
Bay 6 - Generator | 2025-12-10 | Jagdev | [7 empty] | 12:00 | 16:30 | 4.5
Electrical | 2025-12-10 | Fahad | Other | General work | General work & system work | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-10 | Lijo | Panel | SPB15-019 | Socket fixing & testing | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-10 | Aman | Generator | GEN250-051 | RC stator winding | 2025-12-06 | 2025-12-11 | 2025-12-10 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-10 | Charith | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-10 | Aman | Generator | GEN45-005 | Exciter rotor & field winding removing | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-10 | Charith | [7 empty] | 13:00 | 17:00 | 4
Electrical | 2025-12-10 | Ghiyan | Other | BFM355-008 | HDP welding nocting, 3units inspection & repair | 2025-12-09 | 2025-12-10 | 2025-12-10 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-10 | Venu | Borehole pump | Old BH pump 2.2kw | 4nos cable joints & water testing | 2025-12-09 | 2025-12-10 | 2025-12-10 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-10 | Suhaib | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-10 | Saqib | Submersible pump | SM530-563 | Rotor repair & assembling | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-10 | Saqib | Submersible pump | SM530-617 | Rotor repair & assembling | 2025-12-10 | 2025-12-11 |  |  | 11:00 | 16:00 | 5 | Ongoing
Bay 4&5 - Pumps | 2025-12-10 | Asif | Other | General work | General work & system work | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Vinod | Diesel Driven CP Pump | CD300M-033 | Water testing & removing from bay,washing & vernior control installation | 2025-12-10 | 2025-12-15 | 2025-12-10 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Jahir | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-10 | Martino | Diesel Driven CP Pump | AC825-05 | Each muffler piping installation | 2025-12-10 | 2025-12-20 | 2025-12-10 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-10 | Allah ditta | [7 empty] | 7:30 | 14:00 | 6.5
Bay 4&5 - Pumps | 2025-12-10 | Allah ditta | Diesel Driven CP Pump | CD300M-03 | Final fitting | 2025-12-10 | 2025-12-10 | 2025-12-10 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Suresh S | Contractor dewatering Pump | CP150-569/814/783 | Vaccum pump repair | 2025-12-10 | 2025-12-11 | 2025-12-11 |  | 8:00 | 18:00 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-11 | James | Contractor dewatering Pump | CP150-396 | New engine fitting on pump alignment, external parts fittings. | 2025-12-09 | 2025-12-11 | 2025-12-11 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Shaji | [7 empty] | 8:30 | 9:30 | 1
Bay 4&5 - Pumps | 2025-12-11 | Bharathesha | Contractor dewatering Pump | CP150-574 | Engine reapir & water test failed,engine flywheel seal leakage, | 2025-12-08 | 2025-12-11 | 2025-12-11 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Shaji | [7 empty] | 9:30 | 11:30 | 2
Bay 4&5 - Pumps | 2025-12-11 | Mintu | Contractor dewatering Pump | PT175-521 | Engine repair & assembling | 2025-12-10 | 2025-12-11 | 2025-12-11 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Shaji | [7 empty] | 11:30 | 12:00 | 0.5
Bay 4&5 - Pumps | 2025-12-11 | Harish | Contractor dewatering Pump | CP150-514 | Pump assembling, float repair, vaccum oil tank clean, oil change | 2025-12-10 | 2025-12-11 | 2025-12-11 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2025-12-11 | Ismail | Contractor dewatering Pump | PT175-521 | Pump dismantle & prepare for assemble | 2025-12-08 | 2025-12-11 | 2025-12-11 |  | 8:30 | 18:30 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Shaji | Other | System work | System work for work orders & IDT | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 14:00 | 17:00 | 3 | Completed
Bay 6 - Generator | 2025-12-11 | Suraj | Tank | BFT3-305 | Hose fitting | 2025-11-27 | 2025-12-11 | 2025-12-11 |  | 7:30 | 8:30 | 1 | Completed
Bay 6 - Generator | 2025-12-11 | Suraj | Tank | BFT3-309/330/325 | Main cover removing, NRV checking, Hose & fittings fixing | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 8:30 | 16:30 | 8 | Completed
Bay 6 - Generator | 2025-12-11 | Anwar | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-11 | Jagdev | Drill rig | ABI-001 | Reapir on site | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 8:00 | 12:30 | 4.5 | Completed
Bay 6 - Generator | 2025-12-11 | Jagdev | Generator | GEN30-020 | Repair on site | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 14:00 | 16:30 | 2.5 | Completed
Electrical | 2025-12-11 | Fahad | Tank | WOT-012 | Waste tank sensor installation | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 8:00 | 12:00 | 4 | Completed
Electrical | 2025-12-11 | Fahad | Other | BT20-113 | General work for SS | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-11 | Lijo | Other | General work | Panel section wiring & ss work | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-11 | Aman | Generator | GEN45-005 | Exciter rotor & field winding removing | 2025-12-11 | 2025-12-12 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-11 | Charith | [7 empty] | 7:30 | 13:00 | 5.5
Electrical | 2025-12-11 | Ghiyan | Other | BFM355-008 | HDP welding nocting, 2units inspection & repair | 2025-12-09 | 2025-12-11 | 2025-12-11 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-11 | Suhaib | Borehole pump | New BH pump 7.5kw | 13nos new B:h pumps inspection & fleet socket 32A | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 8:00 | 13:00 | 5 | Completed
Electrical | 2025-12-11 | Saqib | Submersible pump | SM530-617 | Rotor repair & assembling | 2025-12-10 | 2025-12-10 | 2025-12-11 |  | 7:30 | 16:00 | 8.5 | Completed
Electrical | 2025-12-11 | Venu | Submersible pump | SM1002-276 | Inspection & dismantling | 2025-12-11 | 2025-12-11 | 2025-12-11 |  | 7:30 | 16:00 | 8.5 | Completed
Electrical | 2025-12-11 | Charith | Generator | GENJ135-003 | Inspection, servicing & assemble | 2025-12-11 | 2025-12-12 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Electrical | 2025-12-11 | Suhaib | Submersible pump | New BH pump 7.5kw | 13nos new B:h pumps inspection & fleet socket 32A | 2025-12-11 | 2025-12-12 |  |  | 13:00 | 17:00 | 4 | Ongoing
Bay 4&5 - Pumps | 2025-12-11 | Asif | Other | General work | General work & system work | 2025-12-11 | 2025-12-11 |  |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Vinod | Diesel Driven CP Pump | CD300M-033 | Water testing & removing from bay,washing & vernior control installation | 2025-12-11 | 2025-12-12 |  |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Jahir | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-11 | Martino | Diesel Driven CP Pump | CP1212-001 | vaccum pump overhauling | 2025-12-11 | 2025-12-12 |  |  | 7:30 | 12:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2025-12-11 | Martino | Diesel Driven CP Pump | CP1212517-26 | vaccum pump overhauling | 2025-12-11 | 2025-12-12 |  |  | 13:00 | 16:30 | 3.5 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Suresh S | Contractor dewatering Pump | CP150X3 | Vaccum pump repair | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 8:00 | 18:00 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-12 | James | Contractor dewatering Pump | CP150-832 | Pump water test & repair | 2025-12-09 | 2025-12-12 | 2025-12-12 |  | 13:00 | 19:00 | 6 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Shaji | [7 empty] | 8:30 | 9:30 | 1
Bay 4&5 - Pumps | 2025-12-12 | Bharathesha | Contractor dewatering Pump | CP150-574 | Oil sump repair, bearing check & seal change, engine fitting with frame & test. | 2025-12-08 | 2025-12-12 | 2025-12-12 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-12 | Mintu | Contractor dewatering Pump | PT175-521 | Engine repair & assembling ongoing | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 8:00 | 10:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-12 | Harish | Contractor dewatering Pump | CP150-813 | Pump assembling, float repair, vaccum oil tank clean, oil change, manifold change, | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-12 | Ismail | Contractor dewatering Pump | PT175-521 | Pump dismantle & prepare for assemble ongoing | 2025-12-11 | 2025-12-14 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Shaji | Contractor dewatering Pump | CP150V-001 | Final fitting, PDI, flowfinity, hose repair. | 2025-12-12 | 2025-12-12 |  |  | 13:00 | 15:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Shaji | Other | System work | System work for work orders & IDT | 2025-12-12 | 2025-12-12 |  |  | 15:00 | 18:00 | 3 | Completed
Bay 6 - Generator | 2025-12-12 | Suraj | Tank | BFT3-121 | Hose & fittings Final fitting | 2025-12-09 | 2025-12-12 | 2025-12-12 |  | 7:30 | 10:30 | 3 | Completed
Bay 6 - Generator | 2025-12-12 | Anwar | [7 empty] | 7:30 | 10:30 | 3
Bay 6 - Generator | 2025-12-12 | Suraj | Generator | GEN150-021 | Fuel pump & injector removing, | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 10:30 | 14:30 | 4 | Completed
Bay 6 - Generator | 2025-12-12 | Anwar | [7 empty] | 10:30 | 14:30 | 4
Bay 6 - Generator | 2025-12-12 | Suraj | Generator | GEN20-002 | Load test, CT coil failure | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 14:30 | 16:30 | 2 | Completed
Bay 6 - Generator | 2025-12-12 | Anwar | [7 empty] | 14:30 | 16:30 | 2
Bay 6 - Generator | 2025-12-12 | Jagdev | Generator | GEN135-013 | Ac alternator removing, crank shaft oil seal work, fuel tank cleaning, | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-12 | Fahad | Other | General work | General work stock labeling & paint for SS | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-12 | Lijo | Other | General work | General work stock labeling & paint for SS | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-12 | Aman | Generator | GEN45-005 | Exciter rotor & field rewinding | 2025-12-11 | 2025-12-12 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-12 | Ghiyan | [7 empty] | 10:30 | 17:00 | 6.5
Electrical | 2025-12-12 | Cherith | Generator | GENJ135-003 | Inspection, servicing & assemble | 2025-12-11 | 2025-12-13 |  |  | 7:30 | 12:00 | 4.5 | Ongoing
Electrical | 2025-12-12 | Faisal | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-12 | Cherith | Generator | GEN150-021 | Inspection, servicing & assemble | 2025-12-12 | 2025-12-13 |  |  | 12:00 | 16:30 | 4.5 | Ongoing
Electrical | 2025-12-12 | Faisal | [7 empty] | 12:00 | 16:30 | 4.5
Electrical | 2025-12-12 | Ghiyan | Generator | GENJ250-043 | Power cable connection | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 7:30 | 10:30 | 3 | Completed
Electrical | 2025-12-12 | Ghiyan | Generator | GEN20-002 | Coil repairing | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 3:30 | 4:30 | 1 | Completed
Electrical | 2025-12-12 | Suhaib | Borehole pump | New BH pump 7.5kw | 12nos new B:H pumps inspection & fleet socket 32A | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 8:00 | 13:00 | 5 | Completed
Electrical | 2025-12-12 | Saqib | Submersible pump | SM530X2 | Water testing | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-12 | Venu |  | SM1002X1 | [5 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-12 | Saqib | Submersible pump | SM1002-276 | Rotor repair & assembling | 2025-12-12 | 2025-12-12 |  |  | 15:00 | 16:30 | 1.5 | Ongoing
Electrical | 2025-12-12 | Venu | [7 empty] | 15:00 | 16:30 | 1.5
Bay 4&5 - Pumps | 2025-12-12 | Asif | Other | General work | General work & system work | 2025-12-12 | 2025-12-12 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Vinod | Diesel Driven CP Pump | HL130M-10 | Exh modification,priming & NRV repairing, fan guard repairing | 2025-12-12 | 2025-12-20 |  |  | 8:00 | 18:00 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Jahir | [7 empty] | 8:00 | 18:00 | 10
Bay 4&5 - Pumps | 2025-12-12 | Allah ditta | Diesel Driven CP Pump | CD150M-004 | Pump end dismantling, compressor repairing, engine service | 2025-12-12 | 2025-12-25 | 2025-12-12 |  | 7:30 | 17:30 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Martino | [7 empty] | 7:30 | 17:30 | 10
Bay 4&5 - Pumps | 2025-12-12 | Asif | Diesel Driven CP Pump | BA700-001 BA700-002 | Inspection battery installation, washing & testing, PDI | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 16:00 | 19:00 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-12 | Allah ditta | [7 empty] | 16:00 | 19:00 | 3
Bay 4&5 - Pumps | 2025-12-12 | Asif | [7 empty] | 16:00 | 19:00 | 3
Bay 4&5 - Pumps | 2025-12-13 | Suresh S | Contractor dewatering Pump | CP150X3 | Vaccum pump repair | 2025-12-12 | 2025-12-13 |  |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Shaji | [7 empty] | 7:30 | 8:30 | 1
Bay 4&5 - Pumps | 2025-12-13 | James | Contractor dewatering Pump | CP150-832 | Pump prepapre for assembling | 2025-12-09 | 2025-12-13 |  |  | 13:00 | 19:00 | 6 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Shaji | [7 empty] | 8:30 | 9:30 | 1
Bay 4&5 - Pumps | 2025-12-13 | Bharathesha | Contractor dewatering Pump | CP150-574 | Engine minor repair & test | 2025-12-08 | 2025-12-13 | 2025-12-13 |  | 7:30 | 10:30 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-13 | Mintu | Contractor dewatering Pump | PT175-536 | Engine dismantling & prepare for assembling | 2025-12-12 | 2025-12-13 |  |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-13 | Harish | Contractor dewatering Pump | CP150-836 | Pump & float repair, vaccum oil tank clean, oil change, water test | 2025-12-13 | 2025-12-13 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Shaji | [7 empty] | 11:00 | 12:00 | 1 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Ismail | Contractor dewatering Pump | PT175-521 | Pump assembling, engine fixing on frame, alignment & water test | 2025-12-11 | 2025-12-13 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Shaji | [7 empty] | 13:00 | 15:00 | 2
Bay 6 - Generator | 2025-12-13 | Jagdev | Generator | GENJ30-069/070 | General inspection & general repair | 2025-12-13 | 2025-12-13 |  |  | 7:30 | 12:30 | 5 | Completed
Bay 6 - Generator | 2025-12-13 | Jagdev | Generator | GEN250-057 | Ac alternator | 2025-11-14 | 2025-12-13 |  |  | 12:30 | 16:30 | 4 | Hold
Bay 6 - Generator | 2025-12-13 | Jagdev | Other | 3rd party pump | Silincer fixing, fuel connection & PDI | 2025-12-13 | 2025-12-13 |  |  | 14:00 | 16:30 | 2.5 | Completed
Bay 6 - Generator | 2025-12-13 | Suraj | Generator | GEN5-013/014 | General repair, oil service, load test | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 7:30 | 11:30 | 4 | Completed
Bay 6 - Generator | 2025-12-13 | Anwar | [7 empty] | 7:30 | 11:30 | 4
Bay 6 - Generator | 2025-12-13 | Suraj | Generator | GEN10-001 | Load test | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 11:30 | 12:30 | 1 | Completed
Bay 6 - Generator | 2025-12-13 | Anwar | [7 empty] | 11:30 | 12:30 | 1
Bay 6 - Generator | 2025-12-13 | Suraj | Generator | GENJ30-069/070 | Load test | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 12:30 | 16:30 | 4 | Completed
Bay 6 - Generator | 2025-12-13 | Anwar | [7 empty] | 12:30 | 16:30 | 4
Electrical | 2025-12-13 | Fahad | Other | General work | General work stock labeling & paint for SS | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-13 | Lijo | Other | General work | General work stock labeling & paint for SS | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-13 | Aman | Submersible pump | SMSP3-021 | 95kw pump water testing | 2025-12-13 | 2025-12-13 |  |  | 7:30 | 13:00 | 5.5 | Completed
Electrical | 2025-12-13 | Saqib | [7 empty] | 7:30 | 13:00 | 5.5
Electrical | 2025-12-13 | Venu | [7 empty] | 7:30 | 13:00 | 5.5
Electrical | 2025-12-13 | Saqib | Submersible pump | SM1002-276 | Rotor repair & assembling | 2025-12-12 | 2025-12-15 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-13 | Cherith | Generator | GENJ135-003 | Inspection, servicing & assemble | 2025-12-11 | 2025-12-13 |  |  | 7:30 | 16:00 | 8.5 | Completed
Electrical | 2025-12-13 | Faisal | [7 empty] | 7:30 | 16:00 | 8.5
Electrical | 2025-12-13 | Suhaib | Borehole pump | New BH pump 2.2kw | 10nos new B:H pumps inspection & fleet socketing | 2025-12-13 | 2025-12-13 |  |  | 8:00 | 13:00 | 5 | Completed
Electrical | 2025-12-13 | Aman | Submersible pump | SMSP3-017 | 7.5kw pump water testing | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-13 | Gulam | [7 empty] | 13:00 | 17:00 | 4
Electrical | 2025-12-13 | Venu | [7 empty] | 13:00 | 17:00 | 4
Bay 4&5 - Pumps | 2025-12-13 | Asif | Other | General work | General work & system work | 2025-12-12 | 2025-12-12 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Vinod | Diesel Driven CP Pump | HL130M-10 | Exh modification,priming & NRV repairing, fan guard repairing | 2025-12-12 | 2025-12-20 |  |  | 8:00 | 18:00 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Jahir | [7 empty] | 8:00 | 18:00 | 10
Bay 4&5 - Pumps | 2025-12-13 | Allah ditta | Diesel Driven CP Pump | CD150M-004 | Pump end dismantling, compressor repairing, engine service | 2025-12-12 | 2025-12-25 | 2025-12-12 |  | 7:30 | 17:30 | 10 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Martino | [7 empty] | 7:30 | 17:30 | 10
Bay 4&5 - Pumps | 2025-12-13 | Asif | Diesel Driven CP Pump | BA700-001 BA700-002 | Inspection battery installation, washing & testing, PDI | 2025-12-12 | 2025-12-12 | 2025-12-12 |  | 16:00 | 19:00 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-13 | Allah ditta | [7 empty] | 16:00 | 19:00 | 3
Bay 4&5 - Pumps | 2025-12-13 | Asif | [7 empty] | 16:00 | 19:00 | 3
Electrical | 2025-12-15 | Fahad | Other | General work | General work stock labeling & paint for SS | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-15 | Lijo | Other | General work | General work stock labeling & paint for SS | 2025-12-13 | 2025-12-13 | 2025-12-13 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-15 | Aman | Generator | GEN250-051 | Alternator service and assembling | 2025-12-15 | 2025-12-16 |  |  | 8:00 | 17:00 | 9 | Hold
Electrical | 2025-12-15 | Gulam | [7 empty] | 8:00 | 17:00 | 9
Electrical | 2025-12-15 | Faisal | Generator | GEN150-021 | Alternator service and assembling | 2025-12-15 | 2025-12-15 |  |  | 7:30 | 16:30 | 9 | Hold
Electrical | 2025-12-15 | Cherith | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-15 | Suhaib | Borehole pump | New BH pump 2.2kw | 19nos new BH pumps inspection & fleet socketing | 2025-12-15 | 2025-12-15 |  |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-15 | Gihan | Generator | GEN45-005 | Exciter field rewinding and assembling | 2025-12-15 | 2025-12-15 |  |  | 7:30 | 16:30 | 9 | Hold
Electrical | 2025-12-15 | Saqib | Submersible pump | SM1002-276 | Rotor repair & assembling | 2025-12-12 | 2025-12-15 |  |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-15 | Venu |  |  |  | 2025-12-12 | 2025-12-15 |  |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-15 | Lijo | Panel | General work | Scrap panels stand removing and arrangements | 2025-12-15 | 2025-12-15 |  |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-15 | Fahad |  |  |  | 2025-12-15 | 2025-12-15 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2025-12-15 | Jagdev | Generator | GEN30-020 | Repair on site - Fuel pump replacement | 2025-12-15 | 2025-12-15 |  |  | 7:30 | 13:00 | 5.5 | Completed
Bay 6 - Generator | 2025-12-15 | Suraj | Tank | BFT1-006 | Fuel tank cleaning | 2025-12-15 | 2025-12-15 |  |  | 7:30 | 14:00 | 6.5 | Hold
Bay 6 - Generator | 2025-12-15 | Suraj |  | BFT1-015 | [5 empty] | 7:30 | 14:00 | 6.5
Bay 6 - Generator | 2025-12-15 | Suraj | Generator | GEN250-057 | Ac alternator fixing | 2025-12-13 | 2025-12-15 |  |  | 14:00 | 16:30 | 2.5 | Completed
Bay 6 - Generator | 2025-12-15 | Jagdev | [7 empty] | 14:00 | 16:30 | 2.5
Bay 6 - Generator | 2025-12-15 | Jagdev | Generator | GENJ150-058 | Alternator removing and dismantling | 2025-12-15 | 2025-12-15 |  |  | 9:00 | 14:00 | 5 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Asif | Other | AC350-08 | Inspection funtional test | 2025-12-15 | 2025-12-15 |  |  | 7:30 | 13:00 | 5.5 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Asif | Other | AC350-08 | Inspection funtional test | 2025-12-15 | 2025-12-15 |  |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Asif | Diesel Driven CP Pump | BA100-001 | Inspection funtional test | 2025-12-15 | 2025-12-15 |  |  | 13:00 | 16:30 | 3.5 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Allah ditta | Diesel Driven CP Pump | CD150M-004 | Pump assembling and installation on test bay | 2025-12-15 | 2025-12-25 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-15 | Martino | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-15 | Jahir | Diesel Driven CP Pump | CP1212-009 | Pump end removing out from canopy | 2025-12-15 | 2025-12-30 |  |  | 8:00 | 17:00 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-15 | Vinod | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-15 | Suresh S | Contractor dewatering Pump | CP150X3 | Vaccum pump repair | 2025-12-15 | 2025-12-15 |  |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-15 | James | Contractor dewatering Pump | CP150-832 | Pummp assembling | 2025-12-12 | 2025-12-15 |  |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Shaji | [7 empty] | 8:30 | 9:30 | 1
Bay 4&5 - Pumps | 2025-12-15 | Bharathesha | Contractor dewatering Pump | CP150-276 | Engine preparing for assembling and assembling | 2025-12-13 | 2025-12-15 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-15 | Mintu | Contractor dewatering Pump | PT175-536 | Engine assembling | 2025-12-12 | 2025-12-15 |  |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-15 | Harish | Contractor dewatering Pump | CP150-836 | Pummp assembling | 2025-12-13 | 2025-12-15 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Shaji | [7 empty] | 11:00 | 12:00 | 1 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Ismail | Contractor dewatering Pump | PT175-515 | Pump assembling, engine fixing on frame and alignment | 2025-12-13 | 2025-12-15 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-15 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Electrical | 2025-12-16 | Fahad | Panel | SPB2.2-076 | Inspection & repair | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 8:00 | 12:00 | 4 | Completed
Electrical | 2025-12-16 | Fahad | Panel | DB-287 | Inspection & repair | 2025-12-16 | 2025-12-16 |  |  | 13:00 | 17:00 | 4 | Hold
Electrical | 2025-12-16 | Shahanawaz | Panel | SPB3.7-180 | New build stand & canopy | 2025-12-16 | 2025-12-16 |  |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-16 | Fahad | Panel | SPB75-001 | Testing & PDI | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 12:00 | 15:00 | 3 | Completed
Electrical | 2025-12-16 | Fahad | Panel | SPB75-004 | Testing & PDI | 2025-12-16 | 2025-12-16 |  |  | 15:00 | 17:00 | 2 | Completed
Electrical | 2025-12-16 | Aman | Generator | GEN250-051 | Inspection & assemble | 2025-12-15 | 2025-12-16 | 2025-12-16 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-16 | Venu | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-16 | Cherith | Generator | GEN150-021 | Inspection & assemble | 2025-12-15 | 2025-12-16 | 2025-12-16 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-16 | Suhaib | Borehole pump | New BH pump 2.2kw | 15nos new BH pumps inspection & fleet socketing | 2025-12-15 | 2025-12-16 | 2025-12-16 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-16 | Gihan | Generator | GEN250-057 | Power cable connection | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 7:30 | 11:00 | 3.5 | Completed
Electrical | 2025-12-16 | Gihan | Generator | GENJ150-058 | Exciter field copper cable removing | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 13:00 | 16:30 | 3.5 | Completed
Electrical | 2025-12-16 | Saqib | Submersible pump | SM1002-276 | Assemble | 2025-12-15 | 2025-12-16 | 2025-12-16 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-16 | Gulam | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-16 | Cherith | Other | FM-034/036 | Flowmeter inspection & PDI | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 10:00 | 11:00 | 1 | Completed
Bay 6 - Generator | 2025-12-16 | Jagdev | Generator | HVMRZV925-003 | All seal reapir, hydraulic pipe | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 7:30 | 12:00 | 4.5 | Completed
Bay 6 - Generator | 2025-12-16 | Jagdev | Generator | GEN150-021 | Fuel pump & injector fitting. | 2025-12-08 | 2025-12-16 | 2025-12-16 |  | 12:00 | 16:30 | 4.5 | Completed
Bay 6 - Generator | 2025-12-16 | Suraj | Tank | BFT1-006 | Fuel tank cleaning & fitting fixing | 2025-12-15 | 2025-12-16 | 2025-12-16 |  | 7:30 | 14:30 | 7 | Completed
Bay 6 - Generator | 2025-12-16 | Anwar |  | BFT1-015 | [5 empty] | 7:30 | 14:30 | 7
Bay 6 - Generator | 2025-12-16 | Suraj | Generator | GENJ30-079 | General inspection & load test | 2025-12-13 | 2025-12-16 | 2025-12-16 |  | 14:30 | 16:30 | 2 | Completed
Bay 6 - Generator | 2025-12-16 | Anwar | [7 empty] | 14:30 | 16:30 | 2
Bay 4&5 - Pumps | 2025-12-16 | Asif | Other | General work | General work | 2025-12-16 | 2025-12-16 | 2025-12-16 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-16 | Allah ditta | Diesel Driven CP Pump | CD150M-004 | installation on test bay, water test & removing from test bay | 2025-12-15 | 2025-12-25 | 2025-12-16 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-16 | Martino | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-16 | Jahir | Diesel Driven CP Pump | CP1212-009 | Pump end removing out from canopy | 2025-12-15 | 2025-12-30 | 2025-12-16 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-16 | Vinod | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-16 | Suresh S | Contractor dewatering Pump | CP150X3 | Final fitting, flowfinity, vaccum pump repair, | 2025-12-15 | 2025-12-16 | 2025-12-16 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-16 | James | Contractor dewatering Pump | CP150-832 | Water test & float repair | 2025-12-12 | 2025-12-16 |  |  | 8:00 | 19:00 | 11 | Ongoing
Bay 4&5 - Pumps | 2025-12-16 | Shaji | [7 empty] | 8:30 | 9:30 | 1
Bay 4&5 - Pumps | 2025-12-16 | Bharathesha | Contractor dewatering Pump | CP150-276 | Engine preparing for assembling and assembling | 2025-12-13 | 2025-12-16 | 2025-12-16 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-16 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-16 | Mintu | Contractor dewatering Pump | PT175-536 | Engine assembling | 2025-12-12 | 2025-12-16 | 2025-12-16 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-16 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-16 | Harish | Contractor dewatering Pump | CP150-403 | Pummp dismantlling | 2025-12-13 | 2025-12-16 | 2025-12-16 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-16 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-16 | Ismail | Contractor dewatering Pump | PT175-536 | Pump dismantling | 2025-12-13 | 2025-12-16 | 2025-12-16 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-16 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-16 | Shaji | Contractor dewatering Pump | CP150-396 | Electrical repair | 2025-12-16 | 2025-12-16 |  |  | 10:00 | 12:00 | 2 | Completed
Electrical | 2025-12-17 | Fahad | Panel | SPB75-004 | PLC replacement, test & PDI | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 8:00 | 12:00 | 4 | Completed
Electrical | 2025-12-17 | Fahad | Panel | DB-287 | Inspection & repair | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-17 | Lijo | Panel | SPB3.7-181/182 | Stand fixing | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-17 | Shahanawaz | Panel | SPB3.7-181/182 | Stand fixing | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-17 | Aman | Panel | SMSP3-022 | Inspection & reapir | 2025-12-16 | 2025-12-18 | 2025-12-17 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-17 | Venu | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-17 | Cherith | Generator | GEN135-013 | Inspection & assemble | 2025-12-17 | 2025-12-17 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-17 | Faisal | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-17 | Gihan | Generator | GENJ150-058 | Exciter field rewinding | 2025-12-17 | 2025-12-19 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-17 | Saqib | Submersible pump | SM1002-179 | Pump dismantle | 2025-12-17 | 2025-12-18 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-17 | Gulam | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-17 | Suhaib | Panel | New 5.5kw pump | 5nos BH pumps inspection, fleet number socket | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 8:00 | 12:00 | 4 | Completed
Electrical | 2025-12-17 | Suhaib | Panel | New 2.2kw pump | 12nos BH pumps inspection, fleet number socket | 2025-12-17 | 2025-12-17 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Bay 6 - Generator | 2025-12-17 | Suraj | Generator | GEN20-002 | Load test & final fitting | 2025-11-26 | 2025-12-17 | 2025-12-17 |  | 7:30 | 9:30 | 2 | Completed
Bay 6 - Generator | 2025-12-17 | Jagdev | Tank | BFT334/339/343/344 | Tank cap removing, suction return fitting & hose fixing | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 12:00 | 16:30 | 4.5 | Completed
Bay 6 - Generator | 2025-12-17 | Suraj | [7 empty] | 9:30 | 14:30 | 5
Bay 6 - Generator | 2025-12-17 | Anwar | [7 empty] | 7:30 | 14:30 | 7
Bay 4&5 - Pumps | 2025-12-17 | Asif | Other | General work | General work | 2025-12-17 | 2025-12-17 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-17 | Allah ditta | Diesel Driven CP Pump | HL130M-10 | NRV installation, fan guard installation on test bay | 2025-12-17 | 2025-12-25 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-17 | Martino | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-17 | Jahir | Diesel Driven CP Pump | CP1212-009 | engine removing out from canopy | 2025-12-15 | 2025-12-30 | 2025-12-30 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-17 | Vinod | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-17 | Suresh S | Contractor dewatering Pump | DIP pump | Engine & pump repair | 2025-12-17 | 2025-12-17 |  |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-17 | Bharathesha | Contractor dewatering Pump | CP150-276 | Engine assembling pump prepare for assembling | 2025-12-13 | 2025-12-17 |  |  | 7:30 | 18:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2025-12-17 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-17 | Mintu | Contractor dewatering Pump | PT175-536 | Engine assembling ongoing | 2025-12-12 | 2025-12-17 | 2025-12-17 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-17 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-17 | Harish | Contractor dewatering Pump | CP150-403 | Pummp pump assembling | 2025-12-15 | 2025-12-17 | 2025-12-17 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-17 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-17 | Harish | Contractor dewatering Pump | CP150-836 | Pump assembling waiting for machine job | 2025-12-13 | 2025-12-17 |  |  | 7:30 | 12:30 | 5 | Hold
Bay 4&5 - Pumps | 2025-12-17 | Ismail | Contractor dewatering Pump | PT175-536 | Pump prepare for assembling | 2025-12-13 | 2025-12-17 |  |  | 7:30 | 18:30 | 11 | Hold
Bay 4&5 - Pumps | 2025-12-17 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-17 | Shaji | Contractor dewatering Pump | CP150X3 | Tested | 2025-12-17 | 2025-12-17 | 2025-12-17 |  | 10:00 | 12:00 | 2 | Completed
Electrical | 2025-12-18 | Fahad | Panel | SPB3.7-180/181/182 | Test & PDI, dispatching | 2025-12-18 | 2025-12-18 |  |  | 8:00 | 12:00 | 4 | Hold
Electrical | 2025-12-18 | Fahad | Panel | SPB95-001 | Test & PDI with load | 2025-12-18 | 2025-12-18 | 2025-12-18 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-18 | Lijo | Panel | SPB3.7-183/184 | Stand fixing | 2025-12-18 | 2025-12-18 | 2025-12-18 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-18 | Shahanawaz | Panel | SPB3.7-183/184 | Stand fixing | 2025-12-18 | 2025-12-18 | 2025-12-18 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-18 | Aman | Panel | SMSP3-022 | 95kw pump water testing | 2025-12-18 | 2025-12-18 | 2025-12-18 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-18 | Venu | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-18 | Gulam | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-18 | Cherith | Generator | GEN135-013 | Inspection & assemble | 2025-12-17 | 2025-12-18 | 2025-12-18 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-18 | Faisal | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-18 | Gihan | Generator | GENJ150-058 | Exciter field rewinding | 2025-12-17 | 2025-12-18 | 2025-12-18 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-18 | Saqib | Panel | SM1002-058 | Rotor repair & assembling | 2025-12-17 | 2025-12-18 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-18 | Suhaib | Panel | New 2.2kw pump | 12nos BH pumps inspection, fleet number socket | 2025-12-17 | 2025-12-18 |  |  | 8:00 | 12:00 | 4 | Ongoing
Electrical | 2025-12-18 | Venu | Panel | SM1002-276 | 37kw pump water testing | 2025-12-18 | 2025-12-18 |  |  | 13:00 | 15:00 | 2 | Ongoing
Electrical | 2025-12-18 | Gulam | [7 empty] | 13:00 | 15:00 | 2
Electrical | 2025-12-18 | Gihan | Generator | GEN60-041 | Ac alternator, copper winding removing | 2025-12-18 | 2025-12-18 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Electrical | 2025-12-18 | Aman | [7 empty] | 13:00 | 16:30 | 3.5
Electrical | 2025-12-18 | Cherith | Generator | GEN45-005 | Inspection & assemble | 2025-12-18 | 2025-12-18 |  |  | 13:00 | 16:30 | 3.5 | Ongoing
Electrical | 2025-12-18 | Faisal | [7 empty] | 13:00 | 16:30 | 3.5
Bay 6 - Generator | 2025-12-18 | Suraj | Generator | GEN20-002 | Load test & final fitting | 2025-11-26 | 2025-12-17 |  |  | 7:30 | 9:30 | 2 | Ongoing
Bay 6 - Generator | 2025-12-18 | Jagdev | Tank | BFT334/321/326/327/335 | Main cover removing, suction return fitting & hose fixing | 2025-12-18 | 2025-12-18 | 2025-12-18 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2025-12-18 | Suraj | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-18 | Anwar | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-18 | Jahir | Diesel Driven CP Pump | HL130M-10 | Water & Vaccum test | 2025-12-18 | 2025-12-25 |  |  | 8:00 | 15:00 | 7 | Ongoing
Bay 4&5 - Pumps | 2025-12-18 | Vinod | [7 empty] | 8:00 | 15:00 | 7
Bay 4&5 - Pumps | 2025-12-18 | Jahir | Diesel Driven CP Pump | CD150M-004 | Final fitting, PDI, flowfinity | 2025-12-18 | 2025-12-18 |  |  | 15:00 | 17:00 | 2 | Ongoing
Bay 4&5 - Pumps | 2025-12-18 | Vinod | [7 empty] | 15:00 | 17:00 | 2
Bay 4&5 - Pumps | 2025-12-18 | Suresh S | Contractor dewatering Pump | DIP pump 3rd party | Engine prepapre for assembling, | 2025-12-17 | 2025-12-18 |  |  | 8:00 | 12:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-18 | Suresh S | Contractor dewatering Pump | CP150X2 | vaccum pump | 2025-12-18 | 2025-12-18 |  |  | 13:00 | 19:00 | 6 | Completed
Bay 4&5 - Pumps | 2025-12-18 | Bharathesha | Contractor dewatering Pump | CP150-090 | Pump repair | 2025-12-18 | 2025-12-18 |  |  | 12:30 | 18:30 | 6 | Completed
Bay 4&5 - Pumps | 2025-12-18 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-18 | Bharathesha | Contractor dewatering Pump | CP150-276 | Engine assmebling | 2025-12-16 | 2025-12-18 |  |  | 7:30 | 12:30 | 5 | Completed
Bay 4&5 - Pumps | 2025-12-18 | Mintu | Contractor dewatering Pump | PT175-520 | Engine repair | 2025-12-12 | 2025-12-18 |  |  | 8:00 | 19:00 | 11 | Ongoing
Bay 4&5 - Pumps | 2025-12-18 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-18 | Harish | Contractor dewatering Pump | CP150-403 | Pump & engine repair, water test | 2025-12-15 | 2025-12-18 |  |  | 7:30 | 11:30 | 4 | Ongoing
Bay 4&5 - Pumps | 2025-12-18 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-18 | Harish | Contractor dewatering Pump | CP150-836 | Pump assembling waiting for machine job | 2025-12-13 | 2025-12-18 |  |  | 7:30 | 12:30 | 5 | Hold
Bay 4&5 - Pumps | 2025-12-18 | Ismail | Contractor dewatering Pump | PT175-536 | Pump prepare for assembling | 2025-12-13 | 2025-12-17 |  |  | 7:30 | 18:30 | 11 | Hold
Bay 4&5 - Pumps | 2025-12-18 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-18 | Shaji | Other | General work | MCS work & general work | 2025-12-18 | 2025-12-18 |  |  | 10:00 | 11:00 | 1 | Ongoing
Electrical | 2025-12-19 | Lijo | Panel | SPB37-082 | Repair work | 2025-12-19 | 2025-12-19 |  |  | 7:00 | 17:00 | 10 | Ongoing
Electrical | 2025-12-19 | Shahanawaz | [7 empty] | 7:00 | 17:00 | 10
Electrical | 2025-12-19 | Cherith | Panel | SMSP3-023 | 75kw pump inspection & dismantle | 2025-12-19 | 2025-12-19 | 2025-12-19 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-19 | Venu | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-19 | Gihan | Generator | GEN60-041 | Ac alternator copper winding, rewinding | 2025-12-18 | 2025-12-19 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-19 | Suhaib | Panel | New 5.5kw pump | 10nos BH pumps inspection, fleet number socket32a, tagging. | 2025-12-19 | 2025-12-19 | 2025-12-19 |  | 8:00 | 17:00 | 9 | Completed
Bay 6 - Generator | 2025-12-19 | Suraj | Generator | GEN20-002 | Load test & final fitting | 2025-11-26 | 2025-12-17 |  |  | 7:30 | 9:30 | 2 | Ongoing
Bay 6 - Generator | 2025-12-19 | Jagdev | Generator | GEN250-057 | Radiator & ac alternator fixing | 2025-11-21 | 2025-12-19 | 2025-12-19 |  | 9:45 | 16:30 | 6.75 | Completed
Bay 6 - Generator | 2025-12-19 | Suraj | [7 empty] | 14:00 | 14:30 | 0.5
Bay 6 - Generator | 2025-12-19 | Suraj | Generator | GEN100-013 | Canopy & ac alternator removing | 2025-12-19 | 2025-12-19 | 2025-12-19 |  | 9:00 | 14:00 | 5 | Completed
Bay 6 - Generator | 2025-12-19 | Anwar | [7 empty] | 9:00 | 14:00 | 5
Bay 4&5 - Pumps | 2025-12-19 | Asif | Diesel Driven CP Pump | KV550-001 | pump dismentaling | 2025-12-19 | 2025-12-30 | 2025-12-19 |  | 8:00 | 12:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-19 | Vinod | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-19 | Asif | Diesel Driven CP Pump | CD300M-08 | Pump end dismantling. | 2025-12-19 | 2025-12-19 | 2025-12-19 |  | 13:00 | 17:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-19 | Bilal | [7 empty] | 15:00 | 17:00 | 2
Bay 4&5 - Pumps | 2025-12-19 | Suresh S | Contractor dewatering Pump | CP150X3 | vaccum pump repair | 2025-12-19 | 2025-12-19 |  |  | 8:00 | 19:00 | 11 | Ongoing
Bay 4&5 - Pumps | 2025-12-19 | Bharathesha | Contractor dewatering Pump | CP150-090 | Pump repair | 2025-12-18 | 2025-12-18 | 2025-12-19 |  | 12:30 | 18:30 | 6 | Completed
Bay 4&5 - Pumps | 2025-12-19 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-19 | Mintu | Contractor dewatering Pump | PT175-520 | Pump assembling | 2025-12-18 | 2025-12-19 | 2025-12-19 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-19 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-19 | Harish | Contractor dewatering Pump | CP150-836 | Pump assembling ongoing | 2025-12-13 | 2025-12-19 |  |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-19 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-19 | Ismail | Contractor dewatering Pump | PT175-536 | Pump prepare for assembling | 2025-12-16 | 2025-12-19 | 2025-12-19 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-19 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-19 | Shaji | Other | General work | MCS work & general work | 2025-12-18 | 2025-12-19 |  |  | 10:00 | 11:00 | 1 | Ongoing
Bay 4&5 - Pumps | 2025-12-19 | James | Contractor dewatering Pump | CP150-276 | Pump assembling | 2025-12-16 | 2025-12-19 | 2025-12-19 |  | 7:30 | 19:00 | 11.5 | Completed
Bay 4&5 - Pumps | 2025-12-19 | Bharathesha | Contractor dewatering Pump | CP150-632 | Pump repair | 2025-12-18 | 2025-12-19 | 2025-12-19 |  | 7:30 | 12:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2025-12-18 | James | Contractor dewatering Pump | CP150-632 | Pump repair | 2025-12-17 | 2025-12-19 |  |  | 14:00 | 19:00 | 5 | Ongoing
Electrical | 2025-12-20 | Fahad | Panel | SPB3.7 | 4nos panels testing, PDI & dispatching | 2025-12-20 | 2025-12-20 |  |  | 8:00 | 17:00 | 9 | Hold
Electrical | 2025-12-20 | Lijo | Panel | SPB3.7-185/186 | Stand & canopy fixing | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-20 | Shahanawaz | [7 empty] | 7:00 | 17:00 | 10
Electrical | 2025-12-20 | Cherith | Panel | SMSP3-023 | 75kw pumpservicing & cleaning | 2025-12-19 | 2025-12-20 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-20 | Venu | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-20 | Gihan | Generator | GEN60-041 | Ac alternator copper winding, removing | 2025-12-18 | 2025-12-20 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-20 | Suhaib | Panel | New 2.2kw pump | 12nos BH pumps inspection, fleet number socket 32a, number tagging. | 2025-12-20 | 2025-12-20 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2025-12-20 | Saqib | Submersible pump | SM1002-058 | Cable glinding | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 7:30 | 9:30 | 2 | Completed
Electrical | 2025-12-20 | Saqib | Generator | GEN135-013 | Power cable connection | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 10:00 | 13:00 | 3 | Completed
Electrical | 2025-12-20 | Aman | Submersible pump | SMSP3-021 | 95kw pump inspection | 2025-12-20 | 2025-12-20 |  |  | 7:30 | 12:00 | 4.5 | Ongoing
Electrical | 2025-12-20 | Faisal | [7 empty] | 7:30 | 12:00 | 4.5
Bay 6 - Generator | 2025-12-20 | Jagdev | Generator | GEN135-013 | Rear seal change, ac alternator fixing, valve & fuel tank cleaning | 2025-12-12 | 2025-12-20 | 2025-12-20 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2025-12-20 | Anwar | Generator | GEN200-007 | Radiator fixing & final fitting | 2025-11-08 | 2025-12-20 | 2025-12-20 |  | 7:30 | 10:30 | 3 | Completed
Bay 6 - Generator | 2025-12-20 | Suraj | [7 empty] | 7:30 | 10:30 | 3
Bay 6 - Generator | 2025-12-20 | Suraj | Generator | GEN150-053 | Radiator fixing & final fitting | 2025-12-05 | 2025-12-20 | 2025-12-20 |  | 10:30 | 15:30 | 5 | Completed
Bay 6 - Generator | 2025-12-20 | Anwar | [7 empty] | 10:30 | 15:30 | 5
Bay 6 - Generator | 2025-12-20 | Suraj | Generator | GEN250-057 | Load test | 2025-11-21 | 2025-12-20 |  |  | 15:30 | 16:30 | 1 | Hold
Bay 6 - Generator | 2025-12-20 | Anwar | [7 empty] | 15:30 | 16:30 | 1
Bay 4&5 - Pumps | 2025-12-20 | Asif | Diesel Driven CP Pump | KV550-001 | Suction casing repairing, sleeve removing from the shaft | 2025-12-20 | 2025-12-30 | 2025-12-30 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Vinod | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-20 | Jaheer | Diesel Driven CP Pump | HL130M-10 | Water testing, removing from the test bay | 2025-12-20 | 2025-12-30 | 2025-12-30 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-20 | Suresh S | Contractor dewatering Pump | CP150X3 | vaccum pump repair for maf | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Bharathesha | Contractor dewatering Pump | CP150-090 | Pump repair | 2025-12-18 | 2025-12-20 | 2025-12-20 |  | 7:30 | 9:30 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Shaji | [7 empty] | 9:30 | 10:30 | 1
Bay 4&5 - Pumps | 2025-12-20 | Mintu | Contractor dewatering Pump | PT175-531 | Engine dismantling | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-20 | Harish | Contractor dewatering Pump | CP150-022 | Pump repair | 2025-12-13 | 2025-12-20 | 2025-12-20 |  | 11:30 | 18:30 | 7 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-20 | Ismail | Contractor dewatering Pump | PT175-521 | Final fitting | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-20 | Ismail | Contractor dewatering Pump | PT175-536 | Pump & engine repair, water test | 2025-12-16 | 2025-12-20 |  |  | 11:30 | 18:30 | 7 | Ongoing
Bay 4&5 - Pumps | 2025-12-20 | Shaji | Other | General work | MCS work & general work | 2025-12-18 | 2025-12-19 |  |  | 10:00 | 11:00 | 1 | Ongoing
Bay 4&5 - Pumps | 2025-12-20 | James | Contractor dewatering Pump | CP150-001 | Pump repair | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-20 | Bharathesha | Contractor dewatering Pump | CP150-923 | Engine repair | 2025-12-20 | 2025-12-20 | 2025-12-20 |  | 9:30 | 18:30 | 9 | Completed
Electrical | 2025-12-22 | Fahad | Panel | ATS400 | Motorized change over inspection& repairing | 2025-12-22 | 2025-12-22 |  |  | 8:00 | 17:00 | 9 | Hold
Electrical | 2025-12-22 | Lijo | Panel | SPB3.7-187/188 | Stand Canopy & alarm system fixing | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-22 | Shahanawaz | [7 empty] | 7:00 | 17:00 | 10
Electrical | 2025-12-22 | Faisal | Panel | DB-363 | Stand replacement, MCCb replacement, Test & PDI | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-22 | Cherith | Panel | SMSP3-021 | 95kv pump inspection & repairing & assemble | 2025-12-22 | 2025-12-24 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-22 | Aman | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-22 | Gihan | Generator | GEN60-041 | Ac alternator copper winding, | 2025-12-22 | 2025-12-26 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-22 | Gulam | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-22 | Gulam | Generator | GEN150-021 | Power cable connection | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 13:00 | 15:00 | 2 | Completed
Electrical | 2025-12-22 | Suhaib | Borehole pump | New 2.2kw pump | 12nos BH pumps inspection, fleet number socket 32a, number tagging. | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-22 | Venu | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-22 | Suhaib | Borehole pump | New 5.5kw pump | 20nos B:H pumps inspection & fleet number tagging. | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 11:00 | 17:00 | 6 | Completed
Electrical | 2025-12-22 | Venu | [7 empty] | 11:00 | 17:00 | 6
Electrical | 2025-12-22 | Saqib | Submersible pump | SMSP3-023 | 75kw pump service & cleaning | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2025-12-22 | Jagdev | Generator | GEN150-021 | Ac alternator & timing cover fixing, | 2025-12-08 | 2025-12-22 | 2025-12-22 |  | 7:30 | 13:00 | 5.5 | Completed
Bay 6 - Generator | 2025-12-22 | Anwar | [7 empty] | 7:30 | 13:00 | 5.5
Bay 6 - Generator | 2025-12-22 | Jagdev | Tank | BFT-325/332/337 | Main cover removed, returned pipe tightened. | 2025-12-22 | 2025-12-22 | 2025-12-22 |  |  |  | 0 | Completed
Bay 6 - Generator | 2025-12-22 | Anwar | [9 empty] | 0
Bay 6 - Generator | 2025-12-22 | Suraj | Generator | GEN200-007 | Load test & final fitting | 2025-11-08 | 2025-12-22 | 2025-12-22 |  | 7:30 | 9:30 | 2 | Completed
Bay 6 - Generator | 2025-12-22 | Suraj | Generator | GEN135-013 | Load test & final fitting | 2025-12-12 | 2025-12-22 | 2025-12-22 |  | 9:30 | 14:00 | 4.5 | Completed
Bay 6 - Generator | 2025-12-22 | Suraj | Generator | GEN150-053 | Load test & final fitting | 2025-12-05 | 2025-12-22 |  |  | 14:00 | 14:30 | 0.5 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Asif | Diesel Driven CP Pump | HD12TCR-002 | Drive chain replacement | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 7:30 | 11:00 | 3.5 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Vinod | [7 empty] | 7:30 | 11:00 | 3.5
Bay 4&5 - Pumps | 2025-12-22 | Jaheer | Diesel Driven CP Pump | CP181820 | ECM filter housing, sensor replacement, radiator cleaning, fan hub inspection. | 2025-12-22 | 2025-12-25 | 2025-12-22 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-22 | Suresh S | Contractor dewatering Pump | CP150X2 | vaccum pump repair for maf | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 8:00 | 15:00 | 7 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Suresh S | Contractor dewatering Pump | CP150-836/632 | Final fitting | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 15:00 | 19:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Mintu | Contractor dewatering Pump | PT175-531 | Engine prepare for assembling | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-22 | Harish | Contractor dewatering Pump | CP150-022 | Pump repair & engine repair | 2025-12-20 | 2025-12-22 | 2025-12-22 |  | 7:30 | 10:30 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-22 | Ismail | Contractor dewatering Pump | PT175-536 | Pump & engine repair & water test | 2025-12-22 | 2025-12-22 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-22 | James | Contractor dewatering Pump | CP150-001 | Pump & engine repair, test failed, pump dismantle | 2025-12-20 | 2025-12-22 |  |  | 11:30 | 18:30 | 7 | Hold
Bay 4&5 - Pumps | 2025-12-22 | Shaji | Other | General work | MCS work & general work | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 10:00 | 11:00 | 1 | Completed
Bay 4&5 - Pumps | 2025-12-22 | James | Contractor dewatering Pump | CP150-001 | Pump repair | 2025-12-22 | 2025-12-22 | 2025-12-22 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-22 | Bharathesha | Contractor dewatering Pump | CP150-923 | Pump prepare for assembling | 2025-12-20 | 2025-12-22 | 2025-12-22 |  | 7:30 | 18:30 | 11 | Completed
Electrical | 2025-12-23 | Fahad | Panel | SPB3.7-180/181 | Test & PDI | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-23 | Lijo | Panel | SPB3.7-188/189 | Alarm system & lock holder fixing | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-23 | Shahanawaz | [7 empty] | 8:00 | 17:00 | 9
Electrical | 2025-12-23 | Faisal | Panel | SPBX4 | Test & PDI | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-23 | Cherith | Panel | SMSP3-021 | 95kv pump inspection & repairing & assemble | 2025-12-22 | 2025-12-24 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-23 | Aman | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-23 | Gihan | Generator | GEN60-041 | Ac alternator re- winding, | 2025-12-22 | 2025-12-26 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-23 | Gulam | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-23 | Suhaib | Borehole pump | New 5.5kw pump | 10nos B:H pumps inspection & fleet number tagging. | 2025-12-22 | 2025-12-23 | 2025-12-23 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-23 | Venu | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2025-12-23 | Suhaib | Borehole pump | SLB/125-03 | 37kw old B:H pump 5nos inspection & water testing | 2025-12-23 | 2025-12-23 |  |  | 13:00 | 17:00 | 4 | Ongoing
Electrical | 2025-12-23 | Venu | [7 empty] | 13:00 | 17:00 | 4
Electrical | 2025-12-23 | Saqib | Submersible pump | SGN-006 | Pump inspection & dismantle | 2025-12-23 | 2025-12-23 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 6 - Generator | 2025-12-23 | Jagdev | Tank | BFT-322/341/345/346 | Main cover removed, returned pipe tightened. | 2025-12-23 | 2025-12-23 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 6 - Generator | 2025-12-23 | Anwar | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-23 | Suraj | [7 empty] | 11:30 | 16:30 | 5
Bay 6 - Generator | 2025-12-23 | Suraj | Generator | GEN150-004 | Ac alternator removing & dismantling | 2025-12-23 | 2025-12-23 |  |  | 7:30 | 11:30 | 4 | Ongoing
Bay 4&5 - Pumps | 2025-12-23 | Asif | Diesel Driven CP Pump | KV550-001 | Pump end swapping | 2025-12-23 | 2025-12-25 |  |  | 7:30 | 9:00 | 1.5 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Vinod | [7 empty] | 7:30 | 19:00 | 11.5
Bay 4&5 - Pumps | 2025-12-23 | Asif | Other | General work | General repair | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 9:00 | 11:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Hanifa | [7 empty] | 9:00 | 11:30 | 2.5
Bay 4&5 - Pumps | 2025-12-23 | Asif | Diesel Driven CP Pump | CD300M015 | wet testing | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 16:00 | 17:30 | 1.5 | Completed
Bay 4&5 - Pumps | 2025-12-23 | SER team | [7 empty] | 16:00 | 17:30 | 1.5
Bay 4&5 - Pumps | 2025-12-23 | Jaheer | Diesel Driven CP Pump | CP181820 | Vaccum pump repairing, fuel line replacement, vaccum testing, cooling fan guard repairing | 2025-12-23 | 2025-12-24 |  |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Bilal | [7 empty] | 8:00 | 19:00 | 11
Bay 4&5 - Pumps | 2025-12-23 | Suresh S | Contractor dewatering Pump | CP150-022/923/001 | vaccum pump repair | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Mintu | Contractor dewatering Pump | PT175-531 | Engine assembling | 2025-12-20 | 2025-12-23 | 2025-12-23 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-23 | Harish | Contractor dewatering Pump | CP150-022 | Pump assembling | 2025-12-20 | 2025-12-23 | 2025-12-23 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-23 | Harish | Contractor dewatering Pump | CP150-844 | Cylinder head dismantling | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 11:30 | 18:30 | 7 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Ismail | Contractor dewatering Pump | PT175-531 | Pump dismantling | 2025-12-20 | 2025-12-23 | 2025-12-23 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-23 | James | Contractor dewatering Pump | CP150-001 | Pump & engine repair, test failed, pump dismantling | 2025-12-20 | 2025-12-23 | 2025-12-23 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Shaji | Other | General work | MCS work & general work | 2025-12-23 | 2025-12-23 | 2025-12-23 |  | 10:00 | 12:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-23 | Bharathesha | Contractor dewatering Pump | CP150-923 | Pump assembling | 2025-12-20 | 2025-12-23 | 2025-12-23 |  | 7:30 | 18:30 | 11 | Completed
Electrical | 2025-12-24 | Fahad | Panel | CPB | 5nos old CPB panels disposal | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-24 | Lijo | [7 empty] | 8:00 | 17:00 | 9
Electrical | 2025-12-24 | Faisal | Panel | SPB3.7-052 | Assemble after paint, test & PDI | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-24 | Cherith | Panel | SMSP3-021 | 95kv pump inspection & repairing & assemble | 2025-12-22 | 2025-12-24 | 2025-12-24 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-24 | Aman | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-24 | Gihan | Generator | GEN60-041 | Ac alternator re- winding, | 2025-12-22 | 2025-12-24 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-24 | Gulam | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-24 | Suhaib | Borehole pump | New 2.2kw pump | 16nos B:H pumps inspection & fleet number tagging socket32a. | 2025-12-24 | 2025-12-26 | 2025-12-24 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-24 | Venu | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-24 | Saqib | Submersible pump | SGN-006 | Pump inspection, repairing & assemble | 23=4/12/2025 | 2025-12-26 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 6 - Generator | 2025-12-24 | Jagdev | Tank | BFT-320/324/329/340 | Main cover removed, returned pipeline & hose fitting | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 6 - Generator | 2025-12-24 | Anwar | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-24 | Suraj | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-24 | Jagdev | Generator | GENJ135-002 | Ac alternator fixing, valave & fuel tank cleaning. | 2025-12-10 | 2025-12-24 | 2025-12-24 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 6 - Generator | 2025-12-24 | Jagdev | Drill rig | DR-20 | Reapir on site | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 7:30 | 13:00 | 5.5 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Asif | Diesel Driven CP Pump | KV550-001 | Pump end swapping | 2025-12-23 | 2025-12-25 | 2025-12-25 |  | 7:30 | 19:00 | 11.5 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Vinod | [7 empty] | 7:30 | 19:00 | 11.5
Bay 4&5 - Pumps | 2025-12-24 | Jaheer | Diesel Driven CP Pump | CD300M-14 | Radiator intercooler dismantling, pump end removing for coupling replacement | 2025-12-24 | 2025-12-30 | 2025-12-30 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Bilal | [7 empty] | 8:00 | 19:00 | 11
Bay 4&5 - Pumps | 2025-12-24 | Suresh S | Contractor dewatering Pump | CP150X3 | vaccum pump repair | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Mintu | Contractor dewatering Pump | PT175-531 | Engine assembling ongoing | 2025-12-20 | 2025-12-24 | 2025-12-24 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-24 | Harish | Contractor dewatering Pump | CP150-022 | Pump assembling | 2025-12-20 | 2025-12-23 |  |  | 7:30 | 11:30 | 4 | Ongoing
Bay 4&5 - Pumps | 2025-12-24 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-24 | Harish | Contractor dewatering Pump | CP150-844 | Engine dismantle & prepare for assemble | 2025-12-23 | 2025-12-24 | 2025-12-24 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Ismail | Contractor dewatering Pump | PT175-522/521/554 | Fuel tank connections fixing, PDI & flowfinity | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-24 | James | Contractor dewatering Pump | CP150-374 | Float Reapir & vaccum pump change. | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 10:00 | 19:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-24 | James | Contractor dewatering Pump | CP150-001 | Pump minor repair & water test | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Shaji | Other | General work | MCS work & general work | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 10:00 | 12:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-24 | Bharathesha | Contractor dewatering Pump | CP150-633 | Pump repair | 2025-12-24 | 2025-12-24 | 2025-12-24 |  | 11:00 | 13:30 | 2.5 | Completed
Electrical | 2025-12-25 | Fahad | Panel | CPB | 5nos old CPB panels disposal | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-25 | Shahanawaz | Panel | SPB3.7-052 | Sensors wiring, site task | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-25 | Faisal | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-25 | Venu | Submersible pump | SMSP3-023 | Parts cleaning, service & pump assembling | 2025-12-24 | 2025-12-26 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-25 | Aman | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-25 | Gihan | Generator | GEN60-041 | Ac alternator re- winding & coils | 2025-12-22 | 2025-12-26 |  |  | 7:30 | 13:00 | 5.5 | Ongoing
Electrical | 2025-12-25 | Gulam | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-25 | Suhaib | Borehole pump | New 2.2kw pump | 10nos B:H pumps inspection & fleet number tagging socket32a. | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-25 | Saqib | Submersible pump | SGN-006 | Pump inspection, repairing & assemble | 2025-12-24 | 2025-12-26 |  |  | 7:30 | 16:30 | 9 | Hold
Electrical | 2025-12-25 | Cherith | Generator | GENJ150-058 | Ac alternator winding, stator washing & service | 2025-12-25 | 2025-12-25 |  |  | 7:30 | 13:00 | 5.5 | Completed
Electrical | 2025-12-25 | Gihan | Generator | GEN200-009 | Hose connections & load test | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 13:00 | 14:00 | 1 | Completed
Electrical | 2025-12-25 | Gihan | Generator | GENJ135-002 | Hose connections & load test | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 14:00 | 15:00 | 1 | Completed
Electrical | 2025-12-25 | Gihan | Generator | GEN250-038 | Hose connections & load test | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 15:00 | 16:00 | 1 | Completed
Bay 6 - Generator | 2025-12-25 | Jagdev | Drill rig | DR-20 | Repair on site | 2025-12-24 | 2025-12-25 | 2025-12-25 |  | 7:30 | 12:00 | 4.5 | Completed
Bay 6 - Generator | 2025-12-25 | Suraj | Generator | GEN200-009 | Final fitting, head test, coolant filling | 2025-12-24 | 2025-12-25 | 2025-12-25 |  | 7:30 | 11:30 | 4 | Completed
Bay 6 - Generator | 2025-12-25 | Anwar | Generator | GENJ135-002 | Final fitting, head test, coolant filling | 2025-12-03 | 2025-12-25 | 2025-12-25 |  | 7:30 | 11:30 | 4 | Completed
Bay 6 - Generator | 2025-12-25 | Anwar | Tank | BFT3-319/331/336/342 | Main & return fuel line fixing | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 11:30 | 16:30 | 5 | Completed
Bay 6 - Generator | 2025-12-25 | Anwar | Generator | GEN250-038 | General repair, heaed test | 2025-12-25 | 2025-12-25 |  |  | 11:30 | 14:00 | 2.5 | Hold
Bay 6 - Generator | 2025-12-25 | Suraj | [7 empty] | 11:30 | 14:00 | 2.5
Bay 6 - Generator | 2025-12-25 | Jagdev | Other | TRAC-001 | General repair, PDI, jack repair | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 16:00 | 18:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Vinod | Diesel Driven CP Pump | KV550-001 | Final fitting | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 7:30 | 12:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Asif | Diesel Driven CP Pump | SCT500-35 | Modification as per site | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Asif | Diesel Driven CP Pump | SCT500-022-023 | Modification as per site | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Vinod | [7 empty] | 14:00 | 16:30 | 2.5
Bay 4&5 - Pumps | 2025-12-25 | Jaheer | Diesel Driven CP Pump | CD300M-14 | Pump installation, Coupling replacement | 2025-12-24 | 2025-12-30 | 2025-12-30 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-25 | Suresh S | Contractor dewatering Pump | CPX3 | vaccum pump repair | 2025-12-24 | 2025-12-25 | 2025-12-25 |  | 8:00 | 15:00 | 7 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Mintu | Contractor dewatering Pump | PT175-531 | Engine assembling ongoing | 2025-12-20 | 2025-12-25 | 2025-12-25 |  | 8:00 | 13:00 | 5 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-25 | Harish | Contractor dewatering Pump | CP150-844 | Engine assembling | 2025-12-20 | 2025-12-25 | 2025-12-25 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-25 | Ismail | Contractor dewatering Pump | PT175-531 | Pump prepare for assembling | 2025-12-23 | 2025-12-25 | 2025-12-25 |  | 7:30 | 10:30 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-25 | Ismail | Contractor dewatering Pump | JP-223 | Pump water test failed, & dismantling | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 10:30 | 18:30 | 8 | Completed
Bay 4&5 - Pumps | 2025-12-25 | James | Contractor dewatering Pump | CP150-374 | Float Reapir & vaccum pump change. | 2025-12-24 | 2025-12-25 |  |  | 10:00 | 19:00 | 9 | Hold
Bay 4&5 - Pumps | 2025-12-25 | Shaji | Other | General work | MCS work & general work | 2025-12-25 | 2025-12-25 | 2025-12-25 |  | 10:00 | 12:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-25 | Bharathesha | Contractor dewatering Pump | CP150-633 | Pump repair | 2025-12-24 | 2025-12-25 |  |  | 11:00 | 13:30 | 2.5 | Hold
Electrical | 2025-12-26 | Fahad | Panel | SPB3.7X8 | Cable gland & sensor cable cutting | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-26 | Shahanawaz | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-26 | Faisal | Other | Site task | Site task | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-26 | Venu | Submersible pump | SM1002/60-276/140 | 30meter cable & joint with socket(125A) & with fitting fixed | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-26 | Aman | Submersible pump | SM1002/60-152 | 30meter cable & joint with socket(125A) & with fitting fixed | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-26 | Gihan | Submersible pump | SM1002/60-195/032 | 30meter cable & joint with socket(125A) & with fitting fixed | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-26 | Gulam | Submersible pump | SM1002/60-191/220 | 30meter cable & joint with socket(125A) & with fitting fixed | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-26 | Saqib | Submersible pump | SM1002/60-196/119 | 30meter cable & joint with socket(125A) & with fitting fixed | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 17:00 | 9.5 | Completed
Electrical | 2025-12-26 | Cherith | Submersible pump | SM1002/60-126 | 30meter cable & joint with socket(125A) & with fitting fixed | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-26 | Cherith | Submersible pump | SMSP3-021/SGN005/SF2250-005/SF300-002/SF300-001 | Pump inspection, checked ok, sent to site | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2025-12-26 | Aman |  |  |  | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 13:00 | 17:00 | 4
Bay 6 - Generator | 2025-12-26 | Anwar | Generator | GEN200-007/009/GEN250-044/012/GEN135-002/250-48/GEN250-54 | Final fitting, battery fixing, PDI & flowfinity | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 12:30 | 5 | Completed
Bay 6 - Generator | 2025-12-26 | Suraj | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-26 | Jagdev | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-26 | Anwar | Tank | BFT3-320/329/324/340 | Hose fitting fix | 2025-12-26 | 2025-12-26 |  |  | 14:00 | 17:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2025-12-26 | Asif | Diesel Driven CP Pump | CD500M-008 | Impeller & wear plate replacement. | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-26 | Vinod | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-26 | Jaheer | Diesel Driven CP Pump | CD300M-14 | Radiator fan drive installation, pump end installing, | 2025-12-26 | 2025-12-30 | 2025-12-30 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-26 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-26 | Suresh S | Contractor dewatering Pump | CPX2/CP001 | vaccum pump repair & final fitting | 2025-12-25 | 2025-12-26 | 2025-12-26 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-26 | Mintu | Contractor dewatering Pump | PT175-531 | Engine assembling ongoing | 2025-12-20 | 2025-12-26 |  |  | 8:00 | 12:00 | 4 | Ongoing
Bay 4&5 - Pumps | 2025-12-26 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-26 | Harish | Contractor dewatering Pump | CP150-844 | Engine assembling ongoing | 2025-12-20 | 2025-12-26 |  |  | 7:30 | 18:30 | 11 | Hold
Bay 4&5 - Pumps | 2025-12-26 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-26 | Ismail | Contractor dewatering Pump | PT175-521 | Pump final fitting, PDI & flowfinity | 2025-12-23 | 2025-12-26 | 2025-12-26 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-26 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-26 | Ismail | Contractor dewatering Pump | JP-223 | Pump water test failed, & dismantling | 2025-12-25 | 2025-12-25 |  |  | 10:30 | 18:30 | 8 | Ongoing
Bay 4&5 - Pumps | 2025-12-26 | James | Contractor dewatering Pump | CP150-374 | Float Reapir & vaccum pump change. Water test | 2025-12-24 | 2025-12-26 | 2025-12-26 |  | 8:00 | 12:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-26 | James | Contractor dewatering Pump | CP150-001 | Pump repair, final fitting, Pdi & flowfinity | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 13:00 | 15:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-26 | James | Contractor dewatering Pump | CP150-845 | Priming tank pressure test | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 15:00 | 17:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-26 | Shaji | Other | General work | MCS work & general work | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 10:00 | 12:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-26 | Bharathesha | Contractor dewatering Pump | CP150-684 | Pump repair & engine repair | 2025-12-26 | 2025-12-26 | 2025-12-26 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-27 | Fahad | Panel | ATS125-008 | Test repair & PDI | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-27 | Fahad | Submersible pump | 6XSM1002 | Pump flange & socket fixing | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 14:00 | 17:00 | 3 | Completed
Electrical | 2025-12-27 | Shahanawaz | Submersible pump | SCP226 | Solar & frame fixing | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-27 | Faisal | Other | Site task | Site task | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-27 | Venu | Submersible pump | SMSP3-023 | Parts cleaning, service & pump assembling | 2025-12-24 | 2025-12-27 |  |  | 7:30 | 13:00 | 5.5 | Hold
Electrical | 2025-12-27 | Aman | [7 empty] | 7:30 | 13:00 | 5.5
Electrical | 2025-12-27 | Gihan | Generator | GEN60-041 | Ac alternator re- winding & coils | 2025-12-22 | 2025-12-27 | 2025-12-27 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-27 | Gulam | Submersible pump | SM1002-058 | Water testing | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-27 | Suhaib | Borehole pump | Old 2.2kw pump | Inspection& repair | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-27 | Saqib | Submersible pump | SM530-611 | Pump inspection, repairing & assemble | 2025-12-27 | 2025-12-29 |  |  | 7:30 | 17:30 | 10 | Ongoing
Electrical | 2025-12-27 | Cherith | Generator | GEN250-051 | Inspection & assembling | 2025-12-27 | 2025-12-27 |  |  | 7:30 | 13:00 | 5.5 | Ongoing
Electrical | 2025-12-27 | Aman | Other | SLT-027/17/30 | Inspection & PDI | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 13:00 | 16:30 | 3.5 | Completed
Electrical | 2025-12-27 | Cherith | [7 empty] | 13:00 | 16:30 | 3.5
Bay 6 - Generator | 2025-12-27 | Suraj | Generator | GEN250-012 | Starting problem, repair & load test | 2025-12-20 | 2025-12-27 | 2025-12-27 |  | 7:30 | 9:30 | 2 | Completed
Bay 6 - Generator | 2025-12-27 | Jagdev | [7 empty] | 7:30 | 9:30 | 2
Bay 6 - Generator | 2025-12-27 | Suraj | Generator | GEN250-057 | Final fitting & load testing | 2025-12-26 | 2025-12-27 |  |  | 9:30 | 11:30 | 2 | Hold
Bay 6 - Generator | 2025-12-27 | Jagdev | [7 empty] | 9:30 | 11:30 | 2
Bay 6 - Generator | 2025-12-27 | Anwar | Tank | BFT3-320/329/324/340 | Hose fixing | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 7:30 | 12:00 | 4.5 | Completed
Bay 6 - Generator | 2025-12-27 | Suraj | Other | TRAC-003 | General repair | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 2:00 | 16:30 | 14.5 | Completed
Bay 6 - Generator | 2025-12-27 | Jagdev | [7 empty] | 2:00 | 16:30 | 14.5
Bay 6 - Generator | 2025-12-27 | Anwar | [7 empty] | 2:00 | 16:30 | 14.5
Bay 4&5 - Pumps | 2025-12-27 | Asif | Diesel Driven CP Pump | HPP140-002 | General repair, washing & testing | 2025-12-27 | 2025-12-30 | 2025-12-30 |  | 7:30 | 13:00 | 5.5 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Vinod | [7 empty] | 7:30 | 16:30 | 9
Bay 4&5 - Pumps | 2025-12-27 | Jaheer | Diesel Driven CP Pump | CD300M-14 | Radiator fan drive installation, pump end installing, | 2025-12-27 | 2025-12-30 | 2025-12-30 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-27 | Suresh S | Contractor dewatering Pump | CP150X3 | 3nos CP pumps vaccum repair | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Mintu | Contractor dewatering Pump | CP150-923 | Pump repair & final fitting | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 8:00 | 10:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-27 | Mintu | Contractor dewatering Pump | CP150-749 | Pump repair & final fitting | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 10:00 | 12:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Mintu | Contractor dewatering Pump | CP150-573 | pump repair | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 13:00 | 19:00 | 6 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Harish | Contractor dewatering Pump | CP150-844 | Engine assembling ongoing | 2025-12-20 | 2025-12-27 | 2025-12-27 |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-27 | James | Contractor dewatering Pump | CP150-845 | Pump repair | 2025-12-26 | 2025-12-27 | 2025-12-27 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Shaji | Other | General work | MCS work & general work | 2025-12-27 | 2025-12-27 | 2025-12-27 |  | 10:00 | 12:00 | 2 | Completed
Bay 4&5 - Pumps | 2025-12-27 | Bharathesha | Contractor dewatering Pump | CP150-684 | Pump repair & engine repair | 2025-12-26 | 2025-12-27 | 2025-12-27 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-29 | Fahad | Panel | Old CPB | 6X old cpb dismantling | 2025-12-29 | 2025-12-29 | 2025-12-29 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-29 | Shahanawaz | Panel | Old CPB | 6X old cpb dismantling | 2025-12-29 | 2025-12-29 | 2025-12-29 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-29 | Lijo | Panel | Old CPB | 6X old cpb dismantling | 2025-12-29 | 2025-12-29 | 2025-12-29 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2025-12-29 | Cherith | Submersible pump | SMSP3-023 | 75kw pump assembling | 2025-12-24 | 2025-12-29 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2025-12-29 | Aman | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2025-12-29 | Gulam | Submersible pump | SM530-624 | Inspection & dismantle | 2025-12-29 | 2025-12-29 | 2025-12-29 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-29 | Suhaib | Borehole pump | Old 2.2kw pump | Inspection& repair | 2025-12-29 | 2025-12-29 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2025-12-29 | Saqib | Submersible pump | SM530-611 | Pump inspection, repairing & assemble | 2025-12-27 | 2025-12-29 |  |  | 7:30 | 17:30 | 10 | Ongoing
Electrical | 2025-12-29 | Gihan | Other | SLT-021/24/18/29 | Inspection & PDI | 2025-12-29 | 2025-12-29 | 2025-12-29 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-29 | Venu | Submersible pump | SM530-388 | Inspection & dismantle | 2025-12-29 | 2025-12-29 | 2025-12-29 |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2025-12-29 | Venu | Submersible pump | SM530-552/330-379 | Rotor repair | 2025-12-29 | 2025-12-30 | 2025-12-30 |  | 13:00 | 16:30 | 3.5 | Completed
Electrical | 2025-12-29 | Gulam | [7 empty] | 13:00 | 16:30 | 3.5
Electrical | 2025-12-29 | Gihan | Submersible pump | SM530X2 | Stator rewinding | 2025-12-29 | 2025-12-30 | 2025-12-30 |  | 13:00 | 17:30 | 4.5 | Completed
Electrical | 2025-12-29 | Saqib | [7 empty] | 13:00 | 17:30 | 4.5
Electrical | 2025-12-29 | Gulam | Other | SWD60AH-002 | Inspection & dismantle | 2025-12-29 | 2025-12-29 |  |  | 16:00 | 18:30 | 2.5 | Ongoing
Electrical | 2025-12-29 | Venu | Other | SWD60AH-001 | Inspection & dismantle | 2025-12-29 | 2025-12-29 |  |  | 16:00 | 18:30 | 2.5 | Ongoing
Bay 6 - Generator | 2025-12-29 | Suraj | Generator | GEN150-004 | Canopy & side doors fitting | 2025-12-23 | 2025-12-29 | 2025-12-29 |  | 7:30 | 11:30 | 4 | Completed
Bay 6 - Generator | 2025-12-29 | Anwar | [7 empty] | 7:30 | 11:30 | 4
Bay 6 - Generator | 2025-12-29 | Suraj | Tank | BFT3-337/333/332/328 | Hose & fittings fixing. | 2025-12-20 | 2025-12-29 | 2025-12-29 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2025-12-29 | Jagdev | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2025-12-29 | Anwar | [7 empty] | 11:30 | 16:30 | 5
Bay 4&5 - Pumps | 2025-12-29 | Asif | Diesel Driven CP Pump | HPP140-002 | Hydraulic oil changing | 2025-12-27 | 2025-12-29 | 2025-12-29 |  | 7:30 | 10:30 | 3 | Completed
Bay 4&5 - Pumps | 2025-12-29 | Vinod | [7 empty] | 7:30 | 10:30 | 3
Bay 4&5 - Pumps | 2025-12-29 | Jaheer | Diesel Driven CP Pump | CD300M-14 | Installation on test bay. | 2025-12-27 | 2025-12-30 | 2025-12-29 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-29 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2025-12-29 | Suresh S | Contractor dewatering Pump | CP150X3 | 3nos CP pumps vaccum repair | 2025-12-27 | 2025-12-27 |  |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2025-12-29 | Mintu | Contractor dewatering Pump | CP150-923 | Pump repair & final fitting | 2025-12-27 | 2025-12-27 |  |  | 8:00 | 10:00 | 2 | Ongoing
Bay 4&5 - Pumps | 2025-12-29 | Shaji | [7 empty] | 10:30 | 11:00 | 0.5
Bay 4&5 - Pumps | 2025-12-29 | Mintu | Contractor dewatering Pump | CP150-749 | Pump repair & final fitting | 2025-12-27 | 2025-12-27 |  |  | 10:00 | 12:00 | 2 | Ongoing
Bay 4&5 - Pumps | 2025-12-29 | Mintu | Contractor dewatering Pump | CP150-573 | pump repair | 2025-12-27 | 2025-12-27 |  |  | 13:00 | 19:00 | 6 | Ongoing
Bay 4&5 - Pumps | 2025-12-29 | Harish | Contractor dewatering Pump | CP150-844 | Engine assembling ongoing | 2025-12-20 | 2025-12-27 |  |  | 7:30 | 18:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2025-12-29 | Shaji | [7 empty] | 11:00 | 12:00 | 1
Bay 4&5 - Pumps | 2025-12-29 | James | Contractor dewatering Pump | CP150-845 | Pump repair | 2025-12-26 | 2025-12-27 |  |  | 8:00 | 19:00 | 11 | Ongoing
Bay 4&5 - Pumps | 2025-12-29 | Shaji | Other | General work | MCS work & general work | 2025-12-27 | 2025-12-27 |  |  | 10:00 | 12:00 | 2 | Ongoing
Bay 4&5 - Pumps | 2025-12-29 | Bharathesha | Contractor dewatering Pump | CP150-684 | Pump repair & engine repair | 2025-12-26 | 2025-12-27 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2025-12-30 | Fahad | Panel | Old CPB | 6X old cpb dismantling | 2025-12-29 | 2025-12-29 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-30 | Shahanawaz | Panel | Old CPB | 6X old cpb dismantling | 2025-12-29 | 2025-12-29 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-30 | Lijo | Panel | Old CPB | 6X old cpb dismantling | 2025-12-29 | 2025-12-29 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-30 | Cherith | Submersible pump | SMSP3-023 | 75kw pump assembling | 2025-12-24 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-30 | Aman | [7 empty] | 6:00 | 10:00 | 4
Electrical | 2025-12-30 | Gulam | Other | SWD60N-002 | Inspection & dismantling | 2025-12-29 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-30 | Suhaib | Borehole pump | Old 2.2kw pump | 10nos Inspection & repair | 2025-12-29 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-30 | Saqib | Submersible pump | SM530X2 | Stator rewinding | 2025-12-29 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-30 | Gihan | [7 empty] | 6:00 | 10:00 | 4
Electrical | 2025-12-30 | Venu | Other | SWD60N-002 | Inspection & dismantling | 2025-12-29 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 6 - Generator | 2025-12-30 | Suraj | Tank | BFT3-337/333/332/328/324/320/340/329 | Hose & fittings fixing. | 2025-12-20 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 6 - Generator | 2025-12-30 | Jagdev | [7 empty] | 6:00 | 10:00 | 4
Bay 6 - Generator | 2025-12-30 | Anwar | [7 empty] | 6:00 | 10:00 | 4
Bay 4&5 - Pumps | 2025-12-30 | Asif | Diesel Driven CP Pump | CD150M-002 | Pump end dismantling | 2025-12-30 | 2026-01-05 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-30 | Vinod | [7 empty] | 6:00 | 10:00 | 4
Bay 4&5 - Pumps | 2025-12-30 | Jaheer | Diesel Driven CP Pump | CD300M-14 | Final fitting airline replacement | 2025-12-30 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-30 | Bilal | [7 empty] | 6:00 | 10:00 | 4
Bay 4&5 - Pumps | 2025-12-30 | Suresh S | Contractor dewatering Pump | CP150-844 | Pump vaccum repair | 2025-12-30 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-30 | Mintu | Contractor dewatering Pump | PT175-109 | Engine prepare for assembling | 2025-12-30 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-30 | Shaji | [7 empty] | 7:00 | 8:00 | 1
Bay 4&5 - Pumps | 2025-12-30 | Harish | Contractor dewatering Pump | CP150-844 | Pump repair ongoing | 2025-12-20 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-30 | Shaji | [7 empty] | 6:00 | 7:00 | 1
Bay 4&5 - Pumps | 2025-12-30 | James | Contractor dewatering Pump | CP150-775 | Pump repair | 2025-12-30 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-30 | Bharathesha | Contractor dewatering Pump | CP150-414 | pump dismantling | 2025-12-30 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-30 | Ismail | Contractor dewatering Pump | PT175-109 | pump dismantling | 2025-12-30 | 2025-12-30 |  |  | 6:00 | 10:00 | 4 | Completed
Electrical | 2025-12-31 | Fahad | Other | flowmeter | 10X flowmeter fleeting & cabeling. | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 8:00 | 16:30 | 8.5 | Completed
Electrical | 2025-12-31 | Faisal | [7 empty] | 8:00 | 16:30 | 8.5
Electrical | 2025-12-31 | Shahanawaz | Panel | DB-041 | Service & repair | 2025-12-31 | 2025-12-31 |  |  | 7:30 | 16:30 | 9 | Hold
Electrical | 2025-12-31 | Lijo | Panel | SPB2.2-057 | Inspection, repair & test | 2025-12-31 | 2025-12-31 |  |  | 8:00 | 16:30 | 8.5 | Ongoing
Electrical | 2025-12-31 | Cherith | Submersible pump | SMSP3-023 | Cable stand making & water testing. | 2025-12-27 | 2025-12-31 | 2025-12-31 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-31 | Aman | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-31 | Gulam | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2025-12-31 | Suhaib | Borehole pump | Old 2.2kw pump | 10nos Inspection & repair | 2025-12-29 | 2025-12-31 | 2025-12-31 |  | 8:00 | 16:30 | 8.5 | Completed
Electrical | 2025-12-31 | Saqib | Submersible pump | SM530 | Stator rewinding | 2025-12-29 | 2025-12-31 | 2025-12-31 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2025-12-31 | Venu | Other | SWD60N-004 | Inspection & dismantling | 2025-12-29 | 2025-12-31 | 2025-12-31 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2025-12-31 | Suraj | Generator | GEN250-057 | Silencer pipe modification, bellows changing & load test. | 2025-12-26 | 2025-12-31 | 2025-12-31 |  | 7:30 | 11:30 | 4 | Completed
Bay 6 - Generator | 2025-12-31 | Anwar | [7 empty] | 7:30 | 11:30 | 4
Bay 6 - Generator | 2025-12-31 | Suraj | Generator | GEN100-044 | General inspection & repair, fuel tank cleaning & load test. | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 11:30 | 16:30 | 5 | Completed
Bay 6 - Generator | 2025-12-31 | Anwar | [7 empty] | 11:30 | 16:30 | 5
Bay 4&5 - Pumps | 2025-12-31 | Asif | Diesel Driven CP Pump | Cp1818-20 | Mid island site | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-31 | Jaheer | Diesel Driven CP Pump | HL130M-07 | General repair, tank cleaning, vaccum testing. | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 8:00 | 12:00 | 4 | Completed
Bay 4&5 - Pumps | 2025-12-31 | Bilal | [7 empty] | 8:00 | 12:00 | 4
Bay 4&5 - Pumps | 2025-12-31 | Vinod | Diesel Driven CP Pump | CD150M-002 | Pump end dismantling | 2025-12-31 | 2025-12-31 | 2025-12-31 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2025-12-31 | Suresh S | Contractor dewatering Pump | CP150-844/CP150X3 | Pump vaccum repair | 2025-12-31 | 2025-12-31 |  |  | 8:00 | 16:30 | 8.5 | Hold
Bay 4&5 - Pumps | 2025-12-31 | Mintu | Contractor dewatering Pump | ACT-166 | Outrigger dismantle & hose repair | 2025-12-30 | 2025-12-31 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-31 | Shaji | [7 empty] | 8:00 | 10:00 | 2
Bay 4&5 - Pumps | 2025-12-31 | Harish | Contractor dewatering Pump | CP150-844 | Pump repair ongoing | 2025-12-20 | 2025-12-31 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-31 | Shaji | [7 empty] | 7:00 | 8:00 | 1
Bay 4&5 - Pumps | 2025-12-31 | James | Contractor dewatering Pump | CP150-775 | Pump repair | 2025-12-30 | 2025-12-31 |  |  | 8:00 | 16:30 | 8.5 | Ongoing
Bay 4&5 - Pumps | 2025-12-31 | Bharathesha | Contractor dewatering Pump | CP150-414 | pump dismantling | 2025-12-30 | 2025-12-31 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2025-12-31 | Ismail | Contractor dewatering Pump | PT175-109 | pump dismantling | 2025-12-30 | 2025-12-31 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-02 | Fahad | Panel | SPB3.7-057 | 10X flowmeter fleeting & cabeling. | 2026-01-02 | 2026-01-02 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-02 | Faisal | Other | FMX3 | 6X150 new flowmeter, cable & socket fixing. | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-02 | Shahanawaz | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2026-01-02 | Cherith | Submersible pump | SMSP3-023 | Cable stand making & water testing. | 2025-12-27 | 2026-01-02 |  |  | 7:30 | 12:00 | 4.5 | Completed
Electrical | 2026-01-02 | Aman | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2026-01-02 | Gulam | [7 empty] | 7:30 | 12:00 | 4.5
Electrical | 2026-01-02 | Ghiyan | Generator | GEN250-051 | Service & assemble | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-02 | Suhaib | Borehole pump | Old 2.2kw pump | 10nos Inspection & repair | 2026-01-02 | 2026-01-02 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-02 | Saqib | Other | SWD60H-004 | Stator rewinding & copper removing | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-02 | Venu | Other | SWD60H-002 | pump parts cleaning | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 12:00 | 4.5 | Ongoing
Bay 6 - Generator | 2026-01-02 | Jagdev | Contractor dewatering Pump | CP1212-009 | Engine dismantling. | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2026-01-02 | Anwar | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2026-01-02 | Suraj | Generator | GEN100-044 | Engine oil service, Engine mounting change | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 10:30 | 3 | Completed
Bay 6 - Generator | 2026-01-02 | Suraj | Generator | GENG100-009 | General inspection & repair, load test failed | 2026-01-02 | 2026-01-02 |  |  | 10:30 | 14:30 | 4 | Hold
Bay 6 - Generator | 2026-01-02 | Suraj | Tank | BFT-015 | Final fitting | 2026-01-02 | 2026-01-02 |  |  | 14:30 | 16:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Vinod | Diesel Driven CP Pump | CD150M-002 | Pump end dismantling | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Jaheer | Diesel Driven CP Pump | CD300M-08 | Clearance adjustment | 2026-01-02 | 2026-01-02 |  |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2026-01-02 | Asif | Other | General work | General work | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 12:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Asif | Diesel Driven CP Pump | SCT500-32 | Pump end swapping with new bareshaft | 2026-01-02 | 2026-01-02 |  |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Suresh S | Contractor dewatering Pump | CP150-297/660/865 | Pump vaccum repair for AUH | 2026-01-02 | 2026-01-02 |  |  | 8:00 | 19:00 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-02 | Mintu | Contractor dewatering Pump | ACT-109 | Engine prepapre for assembling | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 19:00 | 11.5 | Hold
Bay 4&5 - Pumps | 2026-01-02 | Shaji | [7 empty] | 8:00 | 10:00 | 2
Bay 4&5 - Pumps | 2026-01-02 | Mintu | Contractor dewatering Pump | ACT-166 | Outrigger assemble & hose fitting | 2026-01-02 | 2026-01-02 |  |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Harish | Contractor dewatering Pump | CP150-573 | Pump repair, water test & timing setting | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Shaji | [7 empty] | 7:00 | 9:00 | 2
Bay 4&5 - Pumps | 2026-01-02 | Harish | Contractor dewatering Pump | CP150-175 | Pump & engine minor repair | 2026-01-02 | 2026-01-02 |  |  | 14:30 | 18:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-02 | James | Contractor dewatering Pump | CP150-775 | Pump repair | 2026-01-02 | 2026-01-02 |  |  | 8:00 | 16:30 | 8.5 | Hold
Bay 4&5 - Pumps | 2026-01-02 | Bharathesha | Contractor dewatering Pump | CP150-414 | pump assembling & water test | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 18:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-02 | Ismail | Contractor dewatering Pump | PT175-109 | pump assembling. | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 18:30 | 11 | Completed
Electrical | 2026-01-03 | Fahad | Panel | SPB3.7-057/DB041 | Inspection repair & PDI/Repai test & PDI | 2026-01-02 | 2026-01-03 | 2026-01-03 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2026-01-03 | Faisal | Panel | SPB7.5-025 | Modification, adding canopy & safety glass | 2026-01-03 | 2026-01-03 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-03 | Lijo | Panel | SPB7.5-077 | Modification, adding canopy & safety glass | 2026-01-03 | 2026-01-03 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-03 | Cherith | Submersible pump | SWD-60N | pump rotor repiar | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 7:00 | 12:00 | 5 | Completed
Electrical | 2026-01-03 | Aman | [7 empty] | 7:00 | 12:00 | 5
Electrical | 2026-01-03 | Gulam | Generator | GEN250-051 | Ac alternator assembling | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 8:00 | 13:00 | 5 | Completed
Electrical | 2026-01-03 | Ghiyan | [7 empty] | 8:00 | 13:00 | 5
Electrical | 2026-01-03 | Suhaib | Borehole pump | Old 2.2kw pump | 5nos water testing | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2026-01-03 | Saqib | Submersible pump | SM530-624 | Water testing | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 7:30 | 18:30 | 11 | Completed
Electrical | 2026-01-03 | Saqib | Submersible pump | SWD-60-002 | assembling | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 9:00 | 16:30 | 7.5 | Completed
Electrical | 2026-01-03 | Venu | Other | KT22-48/23/026 | General inspection & water testing | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2026-01-03 | Jagdev | Diesel Driven CP Pump | CP1212-009 | Engine dismantling | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2026-01-03 | Shakeel | Generator | GENJ250-043 | Radiator fitting,feul tank cleaning, general repair & load test | 2026-01-03 | 2026-01-03 |  |  | 7:30 | 16:30 | 9 | Hold
Bay 6 - Generator | 2026-01-03 | Anwar | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2026-01-03 | Suraj | Generator | GENG100-009 | Fuel pump & injector removing | 2026-01-02 | 2026-01-03 | 2026-01-03 |  | 7:30 | 11:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Vinod | Diesel Driven CP Pump | CD150M-002 | Pump end dismantling | 2026-01-02 | 2026-01-02 | 2026-01-02 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Jaheer | Diesel Driven CP Pump | CD300M-08 | Clearance adjustment | 2026-01-02 | 2026-01-02 | 2026-01-02 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Bilal | [7 empty] | 8:00 | 17:00 | 9
Bay 4&5 - Pumps | 2026-01-03 | Asif | Other | General work | General work | 2026-01-02 | 2026-01-02 | 2026-01-02 |  | 7:30 | 12:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Asif | Diesel Driven CP Pump | SCT500-32 | Pump end swapping with new bareshaft | 2026-01-02 | 2026-01-02 | 2026-01-02 |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Suresh S | Contractor dewatering Pump | CP150-297/660/865 | Pump vaccum repair for AUH | 2026-01-02 | 2026-01-03 | 2026-01-03 |  | 8:00 | 19:00 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Mintu | Contractor dewatering Pump | PT175-109 | Engine assembling | 2026-01-02 | 2026-01-03 | 2026-01-03 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Shaji | [7 empty] | 8:00 | 10:00 | 2
Bay 4&5 - Pumps | 2026-01-03 | Harish | Contractor dewatering Pump | CP150-175 | Pump & engine repair ongoing | 2026-01-02 | 2026-01-03 | 2026-01-03 |  | 7:30 | 12:30 | 5 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Shaji | [7 empty] | 10:00 | 12:00 | 2
Bay 4&5 - Pumps | 2026-01-03 | Harish | Contractor dewatering Pump | CP150-541 | Pump dismantling | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 12:30 | 16:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-03 | James | Contractor dewatering Pump | CP150-775 | Engine top overhaul | 2026-01-02 | 2026-01-03 | 2026-01-03 |  | 8:00 | 17:00 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Bharathesha | Contractor dewatering Pump | CP150-419 | Engine & pump repair | 2026-01-03 | 2026-01-03 | 2026-01-03 |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-03 | Ismail | Contractor dewatering Pump | PT175-109 | pump assembling ongoing | 2026-01-02 | 2026-01-03 | 2026-01-03 |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2026-01-05 | Fahad | Other | BFM500-001 | Power DB rewiring | 2026-01-05 | 2026-01-05 |  |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2026-01-05 | Faisal | Panel | SPB7.5-025 | Modification, adding canopy & safety glass | 2026-01-03 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-05 | Lijo | Panel | SPB7.5-077 | Modification, adding canopy & safety glass | 2026-01-03 | 2026-01-05 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-05 | Cherith | Other | BFM400-002 | Inspection & repair | 2026-01-05 | 2026-01-05 |  |  | 7:30 | 12:00 | 4.5 | Ongoing
Electrical | 2026-01-05 | Aman | Other | BFM355-008 | Inspection & repair | 2026-01-05 | 2026-01-05 |  |  | 8:30 | 13:00 | 4.5 | Hold
Electrical | 2026-01-05 | Cherith | Generator | GEN100-013 | Ac laternator service ongoing | 2026-01-05 | 2026-01-05 |  |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2026-01-05 | Aman | [7 empty] | 13:00 | 17:00 | 4
Electrical | 2026-01-05 | Gulam | Submersible pump | SMSP3 | 75kw pump rewinding | 2026-01-05 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-05 | Ghiyan | [7 empty] | 7:30 | 16:30 | 9
Electrical | 2026-01-05 | Suhaib | Borehole pump | Old B:H pump | pump cable joint water testing | 2026-01-03 | 2026-01-05 |  |  | 7:30 | 17:00 | 9.5 | Ongoing
Electrical | 2026-01-05 | Afsar | [7 empty] | 7:30 | 17:00 | 9.5
Electrical | 2026-01-05 | Saqib | Submersible pump | SWD-60-002 | assembling | 2026-01-03 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2026-01-05 | Venu | Submersible pump | SMSP3 | 115kw pump dismantling | 2026-01-05 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-05 | Doland | [7 empty] | 7:30 | 17:00 | 9.5
Bay 6 - Generator | 2026-01-05 | Suraj | Diesel Driven CP Pump | GEN250-047 | Engine parts cleaning | 2026-01-05 | 2026-01-05 |  |  | 7:30 | 12:00 | 4.5 | Completed
Bay 6 - Generator | 2026-01-05 | Shakeel | Generator | GENJ250-043 | Radiator fitting,feul tank cleaning, general repair & load test | 2026-01-03 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 6 - Generator | 2026-01-05 | Anwar | [7 empty] | 7:30 | 16:30 | 9
Bay 6 - Generator | 2026-01-05 | Shakeel | Generator | GEN250-038 | Load testing & general checkup, cable connection. | 2026-01-05 | 2026-01-05 |  |  | 7:30 | 10:30 | 3 | Completed
Bay 6 - Generator | 2026-01-05 | Shakeel | Other | General work | Generator shifting & setting | 2026-01-05 | 2026-01-05 |  |  | 10:30 | 1:00 | 14.5 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Vinod | Diesel Driven CP Pump | CD150M-002 | Pump end dismantling | 2026-01-02 | 2026-01-02 |  |  | 7:30 | 16:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-01-05 | Asif | Diesel Driven CP Pump | BA700-001 | Engine repair on site midisland | 2026-01-05 | 2026-01-05 |  |  | 7:30 | 12:00 | 4.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-05 | jagdev | [7 empty] | 7:30 | 12:00 | 4.5
Bay 4&5 - Pumps | 2026-01-05 | Bilal | Diesel Driven CP Pump | HL130M-07 | Final fitting | 2026-01-02 | 2026-01-05 |  |  | 7:30 | 12:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Bilal | Diesel Driven CP Pump | CD150M-002 | Pump firtting | 2026-01-02 | 2026-01-05 |  |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Jaheer | Diesel Driven CP Pump | CD150M-002 | Pump overhaul | 2026-01-05 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Suresh S | Contractor dewatering Pump | CP150-844/414573 | Final fitting, PDI & flowfinity | 2026-01-02 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Mintu | Contractor dewatering Pump | PT175-109 | Engine assembling ongoing | 2026-01-02 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Shaji | [7 empty] | 8:00 | 10:00 | 2
Bay 4&5 - Pumps | 2026-01-05 | Harish | Contractor dewatering Pump | CP150-541 | Pump dismantling & prepare for assembling | 2026-01-02 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Shaji | [7 empty] | 10:00 | 12:00 | 2
Bay 4&5 - Pumps | 2026-01-05 | James | Contractor dewatering Pump | CP150-775 | Engine & pump repair | 2026-01-02 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Bharathesha | Contractor dewatering Pump | CP150-419 | Engine & pump repair | 2026-01-03 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-05 | Ismail | Contractor dewatering Pump | PT175-531 | pump assembling ongoing | 2026-01-02 | 2026-01-05 |  |  | 7:30 | 16:30 | 9 | Completed
Electrical | 2026-01-06 | Fahad | Panel |  |  | 2026-01-06 | 2026-01-06 |  |  | 8:00 | 17:00 | 9 | Completed
Electrical | 2026-01-06 | Faisal | Panel | SPB2.2-061 | Dismantling & replacing the damaged stand canopy | 2026-01-06 | 2026-01-06 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-06 | Lijo | Panel | SPB7.5-025 | Modification, adding canopy & safety glass | 2026-01-06 | 2026-01-06 |  |  | 7:30 | 16:30 | 9 | Ongoing
Electrical | 2026-01-06 | Cherith | Generator | GEN100-013 | Alternator dismantled | 2026-01-06 | 2026-01-07 |  |  | 6:30 | 12:00 | 5.5 | Ongoing
Electrical | 2026-01-06 | Aman | [7 empty] | 6:30 | 12:00 | 5.5
Electrical | 2026-01-06 | Cherith | Other | FM600-002/004 | Inspection & PDI | 2026-01-06 | 2026-01-06 |  |  | 13:00 | 17:00 | 4 | Ongoing
Electrical | 2026-01-06 | Aman | [7 empty] | 13:00 | 17:00 | 4
Electrical | 2026-01-06 | Gulam | Submersible pump | SMSP3 | 75kw pump rewinding | 2026-01-05 | 2026-01-06 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-06 | Ghiyan | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-06 | Suhaib | Borehole pump | Old B:H pump | 20nos pumps inspection & repair | 2026-01-06 | 2026-01-06 |  |  | 7:00 | 17:00 | 10 | Ongoing
Electrical | 2026-01-06 | Afsar | [7 empty] | 7:00 | 17:00 | 10
Electrical | 2026-01-06 | Saqib | Submersible pump | SWD-60-002 | Water testing | 2026-01-06 | 2026-01-09 |  |  | 6:30 | 8:00 | 1.5 | Completed
Electrical | 2026-01-06 | Saqib | Submersible pump | SM530-489 | Dismantle pump | 2026-01-06 | 2026-01-06 |  |  | 8:00 | 15:30 | 7.5 | Completed
Electrical | 2026-01-06 | Venu | Submersible pump | SWD60H-004 | Assembling | 2026-01-06 | 2026-01-07 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-01-06 | Suraj | Generator | GEN200-014 | Engine oil service,water washing & general repair | 2026-01-06 | 2026-01-06 |  |  | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-01-06 | Suraj | Generator | GEN250-047 | Engine parts cleaning | 2026-01-05 | 2026-01-06 |  |  | 10:30 | 15:30 | 5 | Completed
Bay 6 - Generator | 2026-01-06 | Shakeel | Generator | GENJ250-051 | Main alternator fixing & general repair | 2026-01-06 | 2026-01-06 |  |  | 8:00 | 13:00 | 5 | Completed
Bay 6 - Generator | 2026-01-06 | Sayid | [7 empty] | 8:00 | 13:00 | 5
Bay 6 - Generator | 2026-01-06 | Shakeel | Generator | GEN45-005 | Main alternator fixing & general repair | 2026-01-06 | 2026-01-06 |  |  | 14:00 | 17:00 | 3 | Completed
Bay 6 - Generator | 2026-01-06 | Sayid | [7 empty] | 14:00 | 17:00 | 3
Bay 4&5 - Pumps | 2026-01-06 | Vinod | Diesel Driven CP Pump | CD150M-002 | Pump end dismantling | 2026-01-02 | 2026-01-02 |  |  | 14:00 | 16:30 | 2.5 | Completed
Bay 4&5 - Pumps | 2026-01-06 | Asif | Diesel Driven CP Pump | BA700-001 | Engine repair on site midisland | 2026-01-05 | 2026-01-06 |  |  | 14:00 | 12:00 | 22 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | jagdev | [7 empty] | 14:00 | 12:00 | 22
Bay 4&5 - Pumps | 2026-01-06 | Bilal | Diesel Driven CP Pump | CD150M-002 | Pump firtting | 2026-01-02 | 2026-01-06 |  |  | 14:00 | 16:30 | 2.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Vinod | Diesel Driven CP Pump | CD300M-008 | Radiator installation & testing | 2026-01-06 | 2026-01-06 |  |  | 14:00 | 14:00 | 0 | Completed
Bay 4&5 - Pumps | 2026-01-06 | Asif | [7 empty] | 14:00 | 14:00 | 0
Bay 4&5 - Pumps | 2026-01-06 | Jaheer | Diesel Driven CP Pump | CD150M-002 | Pump overhaul | 2026-01-05 | 2026-01-06 |  |  | 14:00 | 16:30 | 2.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Suresh S | Contractor dewatering Pump | CP150-175/CP150X2 | Final fitting, PDI & flowfinity/Vaccum repair | 2026-01-06 | 2026-01-06 |  |  | 14:00 | 12:30 | 22.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Mintu | Contractor dewatering Pump | PT175-109 | Engine assembling ongoing | 2026-01-03 | 2026-01-06 |  |  | 14:00 | 17:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Shaji | [7 empty] | 14:00 | 10:00 | 20
Bay 4&5 - Pumps | 2026-01-06 | Harish | Contractor dewatering Pump | CP150-541 | Pump assembling | 2026-01-06 | 2026-01-06 |  |  | 14:00 | 17:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Shaji | [7 empty] | 14:00 | 12:00 | 22
Bay 4&5 - Pumps | 2026-01-06 | James | Contractor dewatering Pump | CP150-775 | Engine & pump repair ongoing, load test failed. | 2025-12-29 | 2026-01-06 |  |  | 14:00 | 17:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Bharathesha | Contractor dewatering Pump | CP150-419 | Pump prepare for water testing, load test failed. | 2026-01-03 | 2026-01-06 |  |  | 14:00 | 17:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Shaji | [7 empty] | 14:00 | 12:00 | 22
Bay 4&5 - Pumps | 2026-01-06 | Ismail | Contractor dewatering Pump | PT175-531 | pump assembling ongoing | 2025-12-29 | 2026-01-06 |  |  | 14:00 | 17:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-06 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-07 | Fahad | Panel | SPB2.2-061 | Damaged canopy & stand Replaced, repair test & PDI | 2026-01-07 | 2026-01-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-07 | Faisal | Panel | SPB7.5-025 | Modification, adding canopy & safety glass | 2026-01-06 | 2026-01-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-07 | Cherith | Generator | GEN100-013 | Alternator dismantled | 2026-01-06 | 2026-01-07 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-07 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-07 | Gulam | Generator | GEN45-003 | Power cable connection | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 6:30 | 8:30 | 2 | Completed
Electrical | 2026-01-07 | Ghiyan | Submersible pump | SMSP3 | 75kw pump rewinding | 2026-01-05 | 2026-01-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-07 | Suhaib | Borehole pump | Old B:H pump | 20nos pumps inspection & repair | 2026-01-06 | 2026-01-07 |  |  | 7:30 | 17:30 | 10 | Ongoing
Electrical | 2026-01-07 | Afsar | [7 empty] | 7:30 | 17:30 | 10
Electrical | 2026-01-07 | Saqib | Submersible pump | SM530 | Pump repair | 2026-01-06 | 2026-01-07 |  |  | 8:00 | 15:30 | 7.5 | Ongoing
Electrical | 2026-01-07 | Venu | Submersible pump | SWD60H | Pump repair | 2026-01-06 | 2026-01-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-07 | Jagdev | Drill Rig | DR-020 | Repair on site, Drive track repair | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-01-07 | Suraj | Tank | BFT3-329/324/326/342 | Engine parts cleaning | 2025-12-24 | 2026-01-07 | 2026-01-07 |  | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-01-07 | Suraj | Tank | BFT3-331/319/345 | Hose & fittings fixing. | 2026-01-07 | 2026-01-07 |  |  | 10:00 | 15:30 | 5.5 | Ongoing
Bay 6 - Generator | 2026-01-07 | Shakeel | Generator | GENJ250-047 | Ac alternator motor removing | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 8:00 | 10:00 | 2 | Completed
Bay 6 - Generator | 2026-01-07 | Anwar | [7 empty] | 8:00 | 10:00 | 2
Bay 6 - Generator | 2026-01-07 | Shakeel | Tank | BFT3-341/336/322 | Hose & fittings fixing. | 2026-01-07 | 2026-01-07 |  |  | 10:30 | 17:30 | 7 | Ongoing
Bay 6 - Generator | 2026-01-07 | Anwar | [7 empty] | 10:30 | 17:30 | 7
Bay 6 - Generator | 2026-01-07 | Jagdev | Diesel Driven CP Pump | CD150 | Spare engine, general repair | 2026-01-07 | 2026-01-07 |  |  | 10:30 | 15:30 | 5 | Ongoing
Bay 4&5 - Pumps | 2026-01-07 | Bilal | Diesel Driven CP Pump | CD150M-002 | Installation test bay, wet testing | 2026-01-07 | 2026-01-15 | 2026-01-15 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Vinod | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-07 | Asif | Other | Other | General work | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Asif | Diesel Driven CP Pump | SCT600-01 | Gearbox removing | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 10:00 | 17:30 | 7.5 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Jaheer | Other | Drydock | Site work | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 6:30 | 16:30 | 10 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Suresh S | Contractor dewatering Pump | PT175-515/CP150V074 | Final assembling PDI, flowfinity/Vaccum repair | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Mintu | Contractor dewatering Pump | PT175-109 | Engine assembling ongoing | 2026-01-03 | 2026-01-07 | 2026-01-07 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Shaji | [7 empty] | 6:30 | 8:30 | 2
Bay 4&5 - Pumps | 2026-01-07 | Harish | Contractor dewatering Pump | CP150-259 | Pump assembling | 2026-01-06 | 2026-01-07 | 2026-01-07 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-07 | James | Contractor dewatering Pump | CP150-775 | pump assembling & water test | 2025-12-29 | 2026-01-06 | 2026-01-06 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Bharathesha | Contractor dewatering Pump | CP150-419 | Pump prepare for water testing, | 2026-01-03 | 2026-01-07 | 2026-01-07 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-07 | Bharathesha | Contractor dewatering Pump | CP150-845 | Pump dismantled, prepare for assemble | 2026-01-07 | 2026-01-07 | 2026-01-07 |  | 10:00 | 17:30 | 7.5 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Ismail | Contractor dewatering Pump | PT175-531 | pump assembling ongoing | 2025-12-29 | 2026-01-07 | 2026-01-07 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-07 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-08 | Fahad | Other | DB-184 | Repairing & testing | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-08 | Lijo | Panel | SPB2.2-034 | Repairing & testing | 2026-01-08 | 2026-01-08 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-08 | Faisal | Panel | SPB7.5-025 | Modification & adding ELECB & safety glass | 2026-01-08 | 2026-01-08 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-08 | Cherith | Other | FM150-064/024/050 | Inspection & repair | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 13:00 | 17:00 | 4 | Completed
Electrical | 2026-01-08 | Aman | [7 empty] | 13:00 | 17:00 | 4
Electrical | 2026-01-08 | Gulam | Submersible pump | SM530-379 | Repair pump | 2026-01-08 | 2026-01-08 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-08 | Ghiyan | Submersible pump | SMSP3 | 75kw pump rewinding | 2026-01-05 | 2026-01-08 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-08 | Suhaib | Borehole pump | Old B:H pump | 20nos pumps inspection & repair | 2026-01-06 | 2026-01-08 |  |  | 7:30 | 17:30 | 10 | Ongoing
Electrical | 2026-01-08 | Afsar | [7 empty] | 7:30 | 17:30 | 10
Electrical | 2026-01-08 | Saqib | Submersible pump | SM530-552 | Pump repair | 2026-01-06 | 2026-01-08 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-08 | Venu | Submersible pump | SWD60H-002 | Pump repair | 2026-01-06 | 2026-01-08 | 2026-01-08 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-08 | Venu | Other | SSD22-022 | inspection & dismantling | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 8:30 | 17:30 | 9 | Completed
Bay 6 - Generator | 2026-01-08 | Jagdev | Contractor dewatering Pump | CD150 | Spare engine starting & general repair | 2026-01-07 | 2026-01-08 | 2026-01-08 |  | 6:30 | 8:30 | 2 | Completed
Bay 6 - Generator | 2026-01-08 | Suraj | Tank | BFT3-338/323/336 | Main Cover removing, suction pipe tighten, hose & fittings fixing. | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 6:30 | 11:00 | 4.5 | Completed
Bay 6 - Generator | 2026-01-08 | Shakeel | Generator | GEN45-005 | Canopy fitting, Load test & final fitting | 2026-01-06 | 2026-01-08 | 2026-01-08 |  | 8:30 | 11:30 | 3 | Completed
Bay 6 - Generator | 2026-01-08 | Anwar | [7 empty] | 8:30 | 11:30 | 3
Bay 6 - Generator | 2026-01-08 | Shakeel | Generator | GEN250-047 | Parts cleaning, washing & General work | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 15:30 | 17:30 | 2 | Completed
Bay 6 - Generator | 2026-01-08 | Anwar | [7 empty] | 15:30 | 17:30 | 2
Bay 6 - Generator | 2026-01-08 | Jagdev | Contractor dewatering Pump | DR-20/CP150-190/v022/V006 | Repair on site | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 8:30 | 14:00 | 5.5 | Completed
Bay 6 - Generator | 2026-01-08 | Anwar | Generator | GEN250-047 | Engine parts cleaning. | 2026-01-06 | 2026-01-08 | 2026-01-08 |  | 13:00 | 15:30 | 2.5 | Completed
Bay 6 - Generator | 2026-01-08 | Suraj | [7 empty] | 13:00 | 15:30 | 2.5
Bay 4&5 - Pumps | 2026-01-08 | Asif | Diesel Driven CP Pump | CD300M-008 | Coolant leakage repairing, PDI | 2026-01-07 | 2026-01-15 | 2026-01-15 |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Vinod | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-08 | Asif | Diesel Driven CP Pump | SCT600-02 | Gearbox removing | 2026-01-07 | 2026-01-08 | 2026-01-08 |  | 8:30 | 13:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Vinod | [7 empty] | 8:30 | 13:00 | 4.5
Bay 4&5 - Pumps | 2026-01-08 | Bilal | Diesel Driven CP Pump | CD150M-002 | Discharge manifold & fuel connection installation. | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 8:30 | 10:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Jaheer | Diesel Driven CP Pump | KV550 | Impeller removing | 2026-01-08 | 2026-01-08 |  |  | 10:30 | 17:30 | 7 | Ongoing
Bay 4&5 - Pumps | 2026-01-08 | Bilal | [7 empty] | 10:30 | 17:30 | 7
Bay 4&5 - Pumps | 2026-01-08 | Suresh S | Contractor dewatering Pump | CP150X3 | Vaccum pump repair | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 6:30 | 17:00 | 10.5 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Mintu | Contractor dewatering Pump | PT175-541 | Engine dismantling ongoing | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Shaji | [7 empty] | 6:30 | 8:30 | 2
Bay 4&5 - Pumps | 2026-01-08 | Harish | Contractor dewatering Pump | CP150-259 | Pump assembling | 2026-01-06 | 2026-01-08 | 2026-01-08 |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-08 | James | Contractor dewatering Pump | CP150-775 | pump minor repair | 2025-12-29 | 2026-01-08 | 2026-01-08 |  | 6:30 | 9:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Harish | Contractor dewatering Pump | JP232 | Pump & engine repair ongoing | 2026-01-08 | 2026-01-08 | 2026-01-08 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Bharathesha | Contractor dewatering Pump | CP150-845 | Pump assembling | 2026-01-07 | 2026-01-08 | 2026-01-08 |  | 10:00 | 17:30 | 7.5 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-08 | Ismail | Contractor dewatering Pump | PT175-109 | pump assembling &water test | 2026-01-04 | 2026-01-08 | 2026-01-08 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-08 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-09 | Fahad | Panel | ATS400-021 | Repairing & testing | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-09 | Lijo | Panel | SPB2.2-034 | Repairing & testing | 2026-01-08 | 2026-01-09 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-09 | Faisal | Panel | SPB7.5-025 | Modification & adding ELECB & safety glass | 2026-01-08 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-09 | Cherith | Generator | GEN250-047 | inspection & dismantling | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-09 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-09 | Gulam | Submersible pump | SM530-379 | Repair & assembling | 2026-01-08 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-09 | Ghiyan | Generator | GEN60-041 | Inspection & assembling | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-09 | Donald | Submersible pump | SM530-286 | Repairing & assemble | 2026-01-09 | 2026-01-10 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-09 | Suhaib | Borehole pump | Old B:H pump | 20nos pumps inspection & repair | 2026-01-06 | 2026-01-09 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-09 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-09 | Saqib | Submersible pump | SM530-334 | Re-Winding | 2026-01-09 | 2026-01-12 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-09 | Venu | Submersible pump | SM530-552 | Repairing & assemble | 2026-01-09 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-01-09 | Jagdev | Generator | GEN250-047 | Engine parts cleaning | 2026-01-06 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Hold
Bay 6 - Generator | 2026-01-09 | Suraj | [7 empty] | 6:30 | 15:30 | 9
Bay 6 - Generator | 2026-01-09 | Jagdev | Drill Rig | DR-20 | Repair on site | 2026-01-09 | 2026-01-09 |  |  | 9:00 | 12:00 | 3 | Completed
Bay 6 - Generator | 2026-01-09 | Shakeel | Other | General work | general work | 2026-01-09 | 2026-01-09 |  |  | 8:30 | 12:30 | 4 | Completed
Bay 6 - Generator | 2026-01-09 | Anwar | [7 empty] | 8:30 | 12:30 | 4
Bay 6 - Generator | 2026-01-09 | Shakeel | Generator | GENS100-066 | Genera repair, fuel tank cleaning, cable connection & water test | 2026-01-09 | 2026-01-09 |  |  | 13:30 | 17:30 | 4 | Completed
Bay 6 - Generator | 2026-01-09 | Anwar | [7 empty] | 13:30 | 17:30 | 4
Bay 6 - Generator | 2026-01-09 | Ghiyan | [7 empty] | 13:30 | 17:30 | 4
Bay 4&5 - Pumps | 2026-01-09 | Asif | Other | 0il seperator/01/02/03 | Inspection & filter replacement | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 12:00 | 5.5 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Vinod | [7 empty] | 6:30 | 12:00 | 5.5
Bay 4&5 - Pumps | 2026-01-09 | Asif | Diesel Driven CP Pump | KV550 | Impeller removing | 2026-01-09 | 2026-01-09 |  |  | 12:00 | 15:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-09 | Vinod | [7 empty] | 12:00 | 15:30 | 3.5
Bay 4&5 - Pumps | 2026-01-09 | Jaheer | Diesel Driven CP Pump | Vaccum pump | Vaccum pump repairing | 2026-01-09 | 2026-01-09 |  |  | 8:30 | 10:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Bilal | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-09 | Jaheer | Diesel Driven CP Pump | CP108-04 | Washing & oil sump removing | 2026-01-09 | 2026-01-09 |  |  | 10:30 | 17:30 | 7 | Ongoing
Bay 4&5 - Pumps | 2026-01-09 | Bilal | [7 empty] | 10:30 | 17:30 | 7
Bay 4&5 - Pumps | 2026-01-09 | Suresh S | Contractor dewatering Pump | CP150X4 | Vaccum pump repair | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Mintu | Contractor dewatering Pump | PT175-541 | Engine assemblingg ongoing | 2026-01-08 | 2026-01-09 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Shaji | [7 empty] | 6:30 | 8:30 | 2
Bay 4&5 - Pumps | 2026-01-09 | Harish | Contractor dewatering Pump | CP150-614 | Engine cylinder head removing & dismantling | 2026-01-09 | 2026-01-09 |  |  | 10:30 | 17:30 | 7 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-09 | James | Contractor dewatering Pump | CP150-856 | pump prepare for assembling | 2026-01-08 | 2026-01-09 |  |  | 6:30 | 9:30 | 3 | Ongoing
Bay 4&5 - Pumps | 2026-01-09 | Harish | Contractor dewatering Pump | JP232 | Pump & engine repair ongoing | 2026-01-08 | 2026-01-09 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling | 2026-01-07 | 2026-01-09 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-09 | Ismail | Contractor dewatering Pump | PT175-531 | pump repair &water test | 2026-01-04 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-09 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-09 | Ismail | Contractor dewatering Pump | PT175-541 | Pump repair & engine testing | 2026-01-09 | 2026-01-09 |  |  | 15:30 | 17:30 | 2 | Completed
Electrical | 2026-01-10 | Fahad | Panel | SPB-022 | Repairing & testing | 2026-01-09 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-10 | Lijo | Panel | SPB2.2-034 | Repairing & testing | 2026-01-08 | 2026-01-10 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-10 | Faisal | Panel | SPB7.5-025 | Modification & adding ELECB & safety glass | 2026-01-08 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-10 | Cherith | Generator | GEN150-013 | inspection & assemble | 2026-01-09 | 2026-01-10 | 2026-01-10 |  | 6:30 | 12:00 | 5.5 | Completed
Electrical | 2026-01-10 | Aman | [7 empty] | 6:30 | 12:00 | 5.5
Electrical | 2026-01-10 | Gulam | Submersible pump | SM530-286 | Repair & assemble | 2026-01-10 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-10 | Ghiyan | Generator | GEN60-041 | Inspection & assembling | 2026-01-09 | 2026-01-10 | 2026-01-10 |  | 6:30 | 12:00 | 5.5 | Completed
Electrical | 2026-01-10 | Donald | Submersible pump | SM1002-146 | Repairing & assemble | 2026-01-09 | 2026-01-10 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-10 | Suhaib | Borehole pump | Old B:H pump | 8nos B:H pumps water testing | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-10 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-10 | Saqib | Submersible pump | SM530-334 | Re-Winding | 2026-01-09 | 2026-01-12 | 2026-01-12 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-10 | Venu | Other | KTZ2-62-74 | 13nos new pumps inspection & 16amp socket fixing | 2026-01-10 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-10 | Jagdev | Generator | GEN250-047 | Engine assembling, cylinder head & block cleaning | 2026-01-06 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-10 | Suraj | [7 empty] | 7:30 | 15:30 | 8
Bay 6 - Generator | 2026-01-10 | Suraj | Tank | BFT3-332 | Flowfintity | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 6:30 | 7:00 | 0.5 | Completed
Bay 6 - Generator | 2026-01-10 | Shakeel | Generator | GEN100-066 | Water pump & belt fixed, load test failed. | 2026-01-10 | 2026-01-10 |  |  | 8:30 | 13:00 | 4.5 | Ongoing
Bay 6 - Generator | 2026-01-10 | Anwar | [7 empty] | 8:30 | 13:00 | 4.5
Bay 6 - Generator | 2026-01-10 | Shakeel | Other | General work | General work | 2026-01-10 | 2026-01-10 |  |  | 14:00 | 17:30 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-10 | Asif | Diesel Driven CP Pump | KV550 | Impeller removing, defuser installation. | 2026-01-09 | 2026-01-10 | 2026-01-10 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-10 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-10 | Jaheer | Diesel Driven CP Pump | CD225M-03 | Pump end overhauling | 2026-01-09 | 2026-01-10 | 2026-01-10 |  | 15:30 | 17:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-10 | Bilal | [7 empty] | 15:30 | 17:30 | 2
Bay 4&5 - Pumps | 2026-01-10 | Suresh S | Contractor dewatering Pump | PT175/CP150X2 | Final fitting & PDI/Vaccum pump repair for MAF | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-10 | Mintu | Contractor dewatering Pump | PT175-541 | Engine assemblingg ongoing | 2026-01-08 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-10 | Shaji | [7 empty] | 6:30 | 8:30 | 2
Bay 4&5 - Pumps | 2026-01-10 | Harish | Contractor dewatering Pump | CP150-614 | Engine prepare for top overhaul | 2026-01-09 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-10 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-10 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling | 2026-01-07 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-10 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-10 | Ismail | Contractor dewatering Pump | PT175-541 | Engine fitting & water test | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-10 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-10 | James | Contractor dewatering Pump | CP150-856 | Pump assembling | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-01-12 | Fahad | Panel | SPB-022 | Repairing & testing | 2026-01-09 | 2026-01-12 | 2026-01-12 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-12 | Lijo | Panel | SPB2.2-034 | Repairing & testing | 2026-01-08 | 2026-01-10 |  |  | 8:00 | 17:00 | 9 | Ongoing
Electrical | 2026-01-12 | Faisal | Panel | SPB7.5-025 | Modification & adding ELECB & safety glass fixing | 2026-01-08 | 2026-01-10 | 2026-01-10 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-12 | Cherith | Generator | GENJ150-058 | inspection & assemble | 2026-01-12 | 2026-01-12 |  |  | 6:30 | 13:00 | 6.5 | Ongoing
Electrical | 2026-01-12 | Aman | [7 empty] | 6:30 | 13:00 | 6.5
Electrical | 2026-01-12 | Gulam | Submersible pump | SM530-286 | Repair & assemble | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-12 | Ghiyan | Submersible pump | SMSP3 | 75kw pump rewinding & connection | 2026-01-12 | 2026-01-14 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-12 | Donald | Submersible pump | SM1002-146 | Repairing & assemble | 2026-01-12 | 2026-01-12 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-12 | Suhaib | Borehole pump | Old B:H pump | 15nos B:H pumps inspection & repair | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-12 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-12 | Saqib | Submersible pump | SM530-429 | Re-Winding | 2026-01-12 | 2026-01-13 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-12 | Venu | Submersible pump | SM530-334 | Repair & assemble | 2026-01-12 | 2026-01-12 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-12 | Jagdev | Generator | GEN250-047 | Engine assembling onging | 2026-01-06 | 2026-01-12 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-12 | Suraj | Generator | GEN100-13 | Ac alternator fixing | 2026-01-12 | 2026-01-12 |  |  | 6:30 | 9:30 | 3 | Ongoing
Bay 6 - Generator | 2026-01-12 | Suraj | Tank | BFT3-332 | Flowfintity | 2026-01-10 | 2026-01-10 |  |  | 6:30 | 7:00 | 0.5 | Ongoing
Bay 6 - Generator | 2026-01-12 | Shakeel | Generator | GEN100-013 | Ac alternator final fitting. | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 8:30 | 13:00 | 4.5 | Completed
Bay 6 - Generator | 2026-01-12 | Anwar | [7 empty] | 8:30 | 13:00 | 4.5
Bay 6 - Generator | 2026-01-12 | Shakeel | Generator | GEN60-041 | Ac alternator fix, fuel tank cleaning. | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 14:00 | 17:30 | 3.5 | Completed
Bay 6 - Generator | 2026-01-12 | Anwar | [7 empty] | 14:00 | 17:30 | 3.5
Bay 4&5 - Pumps | 2026-01-12 | Asif | Diesel Driven CP Pump | CD300M-029 | Coupling fixing, vaccum testing | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 6:30 | 9:00 | 2.5 | Completed
Bay 4&5 - Pumps | 2026-01-12 | Vinod | [7 empty] | 6:30 | 9:00 | 2.5
Bay 4&5 - Pumps | 2026-01-12 | Asif | Diesel Driven CP Pump | CP108-001 | Coupling fan replacement, vaccum testing | 2026-01-12 | 2026-01-12 | 2026-01-12 |  | 9:00 | 13:00 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-12 | Vinod | [7 empty] | 9:00 | 13:00 | 4
Bay 4&5 - Pumps | 2026-01-12 | Jaheer | Diesel Driven CP Pump | CD225M-03 | Pump end overhauling | 2026-01-09 | 2026-01-15 | 2026-01-15 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-12 | Bilal | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-12 | Suresh S | Contractor dewatering Pump | PT175/CP150X2 | Final fitting & PDI/Vaccum pump repair for MAF | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-12 | Mintu | Contractor dewatering Pump | PT175-541 | Engine assemblingg ongoing | 2026-01-08 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-12 | Shaji | [7 empty] | 6:30 | 8:30 | 2
Bay 4&5 - Pumps | 2026-01-12 | Harish | Contractor dewatering Pump | CP150-614 | Engine prepare for top overhaul | 2026-01-09 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-12 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-12 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling | 2026-01-07 | 2026-01-10 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-12 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-12 | Ismail | Contractor dewatering Pump | PT175-531 | Engine fitting & water test | 2026-01-12 | 2026-01-12 |  |  | 6:30 | 10:00 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-12 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-12 | James | Contractor dewatering Pump | CP150-856 | Pump assembling | 2026-01-10 | 2026-01-10 | 2026-01-10 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-01-13 | Fahad | Panel | SPB7.5-003 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-13 | Lijo | Panel | SPB7.5-023 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-13 | Sulaiman | Panel | General work | Making lock, holders, fleet tagginf & stickers | 2026-01-13 | 2026-01-13 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-13 | Lijo | Generator | GEN250-047 | inspection & dismantle | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-13 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-13 | Saqib | Submersible pump | SM530-429 | Rewinding & connection | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 6:30 | 10:00 | 3.5 | Completed
Electrical | 2026-01-13 | Cherith | Submersible pump | SMSP-3 | 75kw pump rewinding & connection | 2026-01-13 | 2026-01-15 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-13 | Ghiyan | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-13 | Donald | Submersible pump | SM1002-146 | Cable gland & water testing | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-01-13 | Gulam | [7 empty] | 8:30 | 13:00 | 4.5
Electrical | 2026-01-13 | Suhaib | Borehole pump | Old B:H pump | 15nos B:H pumps inspection & repair | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-13 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-13 | Venu | Submersible pump | SM530-344 | Repair & assemble | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-13 | Saqib | Submersible pump | SM530-480 | Re-winding | 2026-01-13 | 2026-01-13 |  |  | 10:00 | 15:30 | 5.5 | Ongoing
Bay 6 - Generator | 2026-01-13 | Jagdev | Generator | GEN250-047 | Engine assembling onging | 2026-01-06 | 2026-01-13 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-13 | Suraj | [7 empty] | 6:30 | 9:30 | 3
Bay 6 - Generator | 2026-01-13 | Shakeel | Generator | GENJ150-058 | Ac alternator fix | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 8:30 | 12:30 | 4 | Completed
Bay 6 - Generator | 2026-01-13 | Anwar | [7 empty] | 8:30 | 12:30 | 4
Bay 6 - Generator | 2026-01-13 | Shakeel | Generator | GENJ150-058 | Electrical work & load test | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 14:00 | 17:30 | 3.5 | Completed
Bay 6 - Generator | 2026-01-13 | Anwar | [7 empty] | 14:00 | 17:30 | 3.5
Bay 4&5 - Pumps | 2026-01-13 | Asif | Diesel Driven CP Pump | KV550 | Pump end assembling | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 6:30 | 11:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-01-13 | Vinod | [7 empty] | 6:30 | 11:00 | 4.5
Bay 4&5 - Pumps | 2026-01-13 | Jaheer | Diesel Driven CP Pump | CD225M-03 | Installation on test bay, water & vaccum testing | 2026-01-13 | 2026-01-15 | 2026-01-15 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-13 | Bilal | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-13 | Suresh S | Contractor dewatering Pump | JP223/CP150X2 | Final fitting /Vaccum pump repair for MAF | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-13 | Mintu | Contractor dewatering Pump | PT175X11 | Musambic pump hose repair & final checkup | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-13 | Shaji | [7 empty] | 6:30 | 8:30 | 2
Bay 4&5 - Pumps | 2026-01-13 | Harish | Contractor dewatering Pump | CP150-614 | Engine assembling | 2026-01-09 | 2026-01-13 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-13 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-13 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling | 2026-01-09 | 2026-01-13 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-13 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-13 | Ismail | Contractor dewatering Pump | CP250 | pump repair | 2026-01-13 | 2026-01-13 |  |  | 6:30 | 10:00 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-01-13 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-13 | James | Contractor dewatering Pump | CP150-856 | Pump repair, water test | 2026-01-13 | 2026-01-13 | 2026-01-13 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-01-14 | Fahad | Panel | SPB7.5-003 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-14 | Lijo | Panel | SPB7.5-023 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-14 | Sulaiman | Panel | General work | General work, Making lock, holders, fleet tagginf & stickers | 2026-01-14 | 2026-01-14 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-14 | Lijo | Generator | GEN250-047 | Ac alternator all winding, washing, cleaning, overheating. | 2026-01-14 | 2026-01-14 |  |  | 8:30 | 12:00 | 3.5 | Ongoing
Electrical | 2026-01-14 | Aman | [7 empty] | 8:30 | 12:00 | 3.5
Electrical | 2026-01-14 | Saqib | Submersible pump | SM530-480 | Rewinding & lead connection, overheating, vernishing | 2026-01-14 | 2026-01-14 |  |  | 6:30 | 11:00 | 4.5 | Ongoing
Electrical | 2026-01-14 | Gulam | Submersible pump | SMSP3-018 | 75kw pump rewinding & connection | 2026-01-13 | 2026-01-15 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-14 | Ghiyan | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-14 | Donald | Submersible pump | SM1002-146 | Water testing | 2026-01-14 | 2026-01-14 |  |  | 8:30 | 10:30 | 2 | Ongoing
Electrical | 2026-01-14 | Venu | [7 empty] | 8:30 | 10:30 | 2
Electrical | 2026-01-14 | Suhaib | Borehole pump | Old B:H pump | 10nos 2.2/3.7/4kw B:H pumps inspection & repair, water test. | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-14 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-14 | Lijo | Generator | GEN150-058 | Power cable & breaker cleaning & service. | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 9:30 | 10:30 | 1 | Completed
Electrical | 2026-01-14 | Venu | Submersible pump | SM530-624 | Inspection & repair | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 10:30 | 15:30 | 5 | Completed
Electrical | 2026-01-14 | Donald | Submersible pump | SM702-021 | Inspection & dismantle repair. | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 10:30 | 17:30 | 7 | Completed
Bay 6 - Generator | 2026-01-14 | Jagdev | Generator | GEN250-047 | Engine assembling onging | 2026-01-06 | 2026-01-14 |  |  | 6:30 | 15:30 | 9 | Hold
Bay 6 - Generator | 2026-01-14 | Suraj | [7 empty] | 6:30 | 15:30 | 9
Bay 6 - Generator | 2026-01-14 | Anwar | Generator | GENG100-009 | Fuel pump & injector fitting/ waiting for timing cover gasket | 2026-01-14 | 2026-01-14 |  |  | 8:30 | 12:30 | 4 | Ongoing
Bay 4&5 - Pumps | 2026-01-14 | Jaheer | Diesel Driven CP Pump | CD225M-03 | Installation on test bay, water & vaccum testing. | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-14 | Bilal | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-14 | Asif | Diesel Driven CP Pump | CP108-004 | Engine top end dismantling | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-14 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-14 | Suresh S | Contractor dewatering Pump | PT175-541/CP150856 | Final fitting | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-14 | Mintu | Contractor dewatering Pump | PT175X11 | 4Xclutch assembly | 2026-01-14 | 2026-01-14 | 2026-01-14 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-14 | Shaji | [7 empty] | 13:00 | 17:30 | 4.5
Bay 4&5 - Pumps | 2026-01-14 | Harish | Contractor dewatering Pump | CP150-614 | Engine assembling ongoing | 2026-01-09 | 2026-01-14 | 2026-01-14 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-14 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-14 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling ongoing | 2026-01-09 | 2026-01-14 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-14 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-14 | Ismail | Contractor dewatering Pump | CP250-001/007 | pump repair & water test/ pump repair | 2026-01-14 | 2026-01-14 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-14 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-14 | James | Contractor dewatering Pump | CP150-265 | Pump repair, water test | 2026-01-14 | 2026-01-14 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-15 | Fahad | Panel | SPB7.5-003 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-15 | Lijo | Panel | SPB7.5-023 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-15 | Sulaiman | Panel | SCP226/238 | General work, Making lock, holders, fleet tagginf & stickers | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-15 | Lijo | Submersible pump | SM1002-060/22 | Inspection & reapir | 2026-01-15 | 2026-01-15 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-15 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-15 | Saqib | Submersible pump | SM702-021 | Copper winding removing. | 2026-01-15 | 2026-01-15 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-15 | Donald | Submersible pump | SM1002-060/275 | Inspection & reapir | 2026-01-15 | 2026-01-15 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-15 | Cherith | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-15 | Ghiyan | Submersible pump | SMSP3-018 | 75kw pump rewinding and connection | 2026-01-15 | 2026-01-15 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-15 | Gulam | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-15 | Suhaib | Borehole pump | Old B:H pump | 10nos B:H pumps inspection & repair, water test. | 2026-01-15 | 2026-01-15 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-15 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-15 | Venu | Submersible pump | SM530-426 | Inspection & repair | 2026-01-15 | 2026-01-15 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-15 | Jagdev | Generator | GEN250-047 | Engine assembling onging | 2026-01-06 | 2026-01-15 |  |  | 6:30 | 15:30 | 9 | Hold
Bay 6 - Generator | 2026-01-15 | Suraj | [7 empty] | 6:30 | 15:30 | 9
Bay 6 - Generator | 2026-01-15 | Jagdev | Drill Rig | DR-020 | Repair on site | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 10:00 | 14:30 | 4.5 | Completed
Bay 6 - Generator | 2026-01-15 | Suraj | Generator | GEN150-037 | Engine parts cleaning. | 2026-01-15 | 2026-01-15 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-15 | Anwar | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-15 | Jaheer | Diesel Driven CP Pump | CD5E-002/001 | Installation on test bay, water & vaccum testing. | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-15 | Bilal | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-15 | Asif | Diesel Driven CP Pump | SCT500-32 | pump end dismantling. | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-15 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-15 | Suresh S | Contractor dewatering Pump | CP150-297/PT175X11 | All oil draining/ Vaccum pump repair. | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-15 | Mintu | Contractor dewatering Pump | JP-223 | Engine repair | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-15 | Shaji | [7 empty] | 13:00 | 15:30 | 2.5
Bay 4&5 - Pumps | 2026-01-15 | Harish | Contractor dewatering Pump | CP150-614 | Engine assembling ongoing | 2026-01-09 | 2026-01-14 | 2026-01-14 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-15 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-15 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling ongoing | 2026-01-09 | 2026-01-15 | 2026-01-15 |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-15 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-15 | Ismail | Contractor dewatering Pump | CP250-001 | Pump dismantling | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 12:30 | 17:30 | 5 | Completed
Bay 4&5 - Pumps | 2026-01-15 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-15 | James | Contractor dewatering Pump | CP150-265 | Pump repair, water test | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-01-16 | Fahad | Panel | SPB7.5-003 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-16 | Lijo | Panel | SPB7.5-023 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-16 | Sulaiman | Panel | DB-184 | Inspection,service & repair | 2026-01-15 | 2026-01-15 | 2026-01-15 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-16 | Lijo | Generator | GEN250-047 | Inspection & assemble | 2026-01-16 | 2026-01-16 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-16 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-16 | Saqib | Submersible pump | SM702-021 | Rewinding | 2026-01-16 | 2026-01-17 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-16 | Donald | Submersible pump | SM1002-060/275 | Inspection & reapir | 2026-01-16 | 2026-01-17 | 2026-01-17 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-16 | Gulam | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-16 | Ghiyan | Submersible pump | SMSP3-018 | 75kw pump rewinding and connection | 2026-01-15 | 2026-01-16 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-16 | Cherith | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-16 | Suhaib | Borehole pump | New B:H pump | 15nos 2.2kw pumps inspection & repair, water test. | 2026-01-16 | 2026-01-16 | 2026-01-16 |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-01-16 | Afsar | [7 empty] | 8:30 | 13:00 | 4.5
Electrical | 2026-01-16 | Venu | Submersible pump | SM530-426 | Inspection & repair | 2026-01-16 | 2026-01-16 | 2026-01-16 |  | 6:30 | 9:00 | 2.5 | Completed
Bay 6 - Generator | 2026-01-16 | Jagdev | Generator | GEN250-047 | Engine assembling onging | 2026-01-06 | 2026-01-16 | 2026-01-16 |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-01-16 | Suraj | Generator | GEN150-021 | Water p[ump fixing, fuel tank cleaning, load test. | 2026-01-16 | 2026-01-16 |  |  | 6:30 | 10:00 | 3.5 | Hold
Bay 6 - Generator | 2026-01-16 | Anwar | Generator | GEN150-037 | Engine parts cleaning, washing | 2026-01-15 | 2026-01-16 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-01-16 | Jaheer | Diesel Driven CP Pump | SCT600-002 | Engine removing from frame. | 2026-01-16 | 2026-01-16 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-16 | Bilal | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-16 | Asif | Diesel Driven CP Pump | SCT600-001 | Engine removing from frame. | 2026-01-16 | 2026-01-16 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-16 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-16 | Suresh S | Contractor dewatering Pump | ZD900-032E | Pump repair & water test. | 2026-01-16 | 2026-01-16 | 2026-01-16 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-16 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling. | 2026-01-09 | 2026-01-16 | 2026-01-16 |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-16 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-16 | Harish | Contractor dewatering Pump | CP150-614 | Pump dismantling. | 2026-01-09 | 2026-01-16 | 2026-01-16 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-16 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-16 | Ismail | Contractor dewatering Pump | CP250-001 | Pump dismantling ongoing. | 2026-01-15 | 2026-01-16 | 2026-01-16 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-16 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-16 | Mintu | Contractor dewatering Pump | Spare engine for mozambic | Engine assembling | 2026-01-15 | 2026-01-16 | 2026-01-16 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-16 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-16 | James | Contractor dewatering Pump | CP150-265 | Pump prepare for assembling | 2026-01-14 | 2026-01-16 | 2026-01-16 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-01-17 | Fahad | Panel | SPB7.5-003 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-17 | Lijo | Panel | SPB7.5-023 | Modification, rewinding,adding ELC & safety glasses. | 2026-01-13 | 2026-01-18 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-17 | Sulaiman | Panel | DB-184 | Inspection,service & repair | 2026-01-15 | 2026-01-15 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-17 | Lijo | Submersible pump | SM1002-142 | Inspection & dismantle | 2026-01-17 | 2026-01-17 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-17 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-17 | Saqib | Submersible pump | SM702-021 | Rewinding | 2026-01-16 | 2026-01-17 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-17 | Donald | Submersible pump | SM1002 275/022 | Pump water testing | 2026-01-17 | 2026-01-17 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-17 | Gulam | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-17 | Ghiyan | Submersible pump | SMSP3-018 | 75kw pump rewinding and connection | 2026-01-15 | 2026-01-17 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-17 | Cherith | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-17 | Suhaib | Borehole pump | New B:H pump | 14nos 2.2kw pumps inspection & fleet number tagging | 2026-01-16 | 2026-01-17 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-17 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-17 | Venu | Submersible pump | SM530-429 | Inspection & repair | 2026-01-17 | 2026-01-17 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-17 | Sulemam | Generator | GENJ60-003 | Inspection & dismantle | 2026-01-17 | 2026-01-17 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 6 - Generator | 2026-01-17 | Jagdev | Diesel Driven CP Pump | CD150 spare engine | Final fitting | 2026-01-17 | 2026-01-17 |  |  | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-01-17 | Suraj | Generator | GEN150-021 | canopy & radiator removing | 2026-01-16 | 2026-01-17 |  |  | 6:30 | 10:30 | 4 | Ongoing
Bay 6 - Generator | 2026-01-17 | Suraj | Generator | GEN100-013 | Load testing, fuel tank cleaning, final fitting | 2026-01-17 | 2026-01-17 |  |  | 10:30 | 15;30 | #VALUE! | Completed
Bay 6 - Generator | 2026-01-17 | Anwar | Generator | GEN150-037 | Engine parts cleaning, washing | 2026-01-15 | 2026-01-17 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-17 | JAGDEV | [7 empty] | 10:30 | 15;30 | #VALUE!
Bay 4&5 - Pumps | 2026-01-17 | Jaheer | Diesel Driven CP Pump | CD50E-002 | Water testing | 2026-01-17 | 2026-01-21 |  |  | 8:30 | 1:00 | 16.5 | Completed
Bay 4&5 - Pumps | 2026-01-17 | Bilal | [7 empty] | 8:30 | 1:00 | 16.5
Bay 4&5 - Pumps | 2026-01-17 | Asif | Diesel Driven CP Pump | CP108-004 | Engine top end repairing | 2026-01-17 | 2026-01-21 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-17 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-17 | Suresh S | Contractor dewatering Pump | ZD900-032E | Pump repair & water test. | 2026-01-16 | 2026-01-17 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-01-17 | Bharathesha | Contractor dewatering Pump | CP150-184 | Engine assembling. | 2026-01-09 | 2026-01-17 |  |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-17 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-17 | Harish | Contractor dewatering Pump | CP150-614 | Pump dismantling. | 2026-01-09 | 2026-01-16 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-17 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-17 | Ismail | Contractor dewatering Pump | CP250-001 | Pump dismantling ongoing. | 2026-01-15 | 2026-01-16 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-17 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-17 | Mintu | Contractor dewatering Pump | Spare engine for mozambic | Engine assembling | 2026-01-15 | 2026-01-16 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-17 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-17 | James | Contractor dewatering Pump | CP150-265 | Pump prepare for assembling | 2026-01-14 | 2026-01-16 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-19 | Fahad | Panel | SPB7.5-003 | Safety glass, canopy fixing, test & PDI | 2026-01-13 | 2026-01-20 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-19 | Lijo | Panel | SPB7.5-023 | Safety glass, canopy fixing, test & PDI | 2026-01-13 | 2026-01-20 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-19 | Sulaiman | Panel | CPBX3 | repair test & PDI | 2026-01-19 | 2026-01-19 | 2026-01-19 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-19 | Lijo | Generator | GENJ60-003 | Inspection & servicing | 2026-01-19 | 2026-01-19 |  |  | 8:30 | 13:00 | 4.5 | Ongoing
Electrical | 2026-01-19 | Aman | [7 empty] | 8:30 | 13:00 | 4.5
Electrical | 2026-01-19 | Saqib | Submersible pump | SM702-021 | Rewinding | 2026-01-16 | 2026-01-19 | 2026-01-19 |  | 6:30 | 13:00 | 6.5 | Completed
Electrical | 2026-01-19 | Donald | Submersible pump | SM1002 60/142 | Inspection & reapair | 2026-01-19 | 2026-01-19 |  |  | 6:30 | 15:30 | 9 | Hold
Electrical | 2026-01-19 | Gulam | [7 empty] | 6:30 | 15:30 | 9
Electrical | 2026-01-19 | Ghiyan | Generator | GENJ60-003 | Excide rotor rewinding | 2026-01-19 | 2026-01-19 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-19 | Suhaib | Borehole pump | Old B:H pump | 7nos BH pumps water testing | 2026-01-19 | 2026-01-19 |  |  | 8:30 | 13:00 | 4.5 | Ongoing
Electrical | 2026-01-19 | Afsar | [7 empty] | 8:30 | 13:00 | 4.5
Electrical | 2026-01-19 | Venu | Submersible pump | SM530-480 | Inspection & repair | 2026-01-17 | 2026-01-19 |  |  | 6:30 | 15:30 | 9 | Hold
Electrical | 2026-01-19 | Donald | Other | Spider light | SLT018/21/30/32/027/017 6nos tower light for each 30meter cable & 6nos male socket | 2026-01-19 | 2026-01-19 | 2026-01-19 |  | 12:00 | 15:30 | 3.5 | Completed
Electrical | 2026-01-19 | Gulam | [7 empty] | 15:30 | 15:30 | 0
Electrical | 2026-01-19 | Venu | [7 empty] | 15:30 | 15:30 | 0
Bay 6 - Generator | 2026-01-19 | Jagdev | Drill Rig | DR-025 | Motor repair | 2026-01-19 | 2026-01-19 | 2026-01-19 |  | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-01-19 | Anwar | Generator | GEN150-037 | Engine parts cleaning, washing | 2026-01-15 | 2026-01-17 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 6 - Generator | 2026-01-19 | Suraj | [7 empty] | 8:30 | 15:30 | 7
Bay 4&5 - Pumps | 2026-01-19 | Jaheer | Diesel Driven CP Pump | CD50E-002 | Water testing | 2026-01-17 | 2026-01-21 | 2026-01-21 |  | 8:30 | 1:00 | 16.5 | Completed
Bay 4&5 - Pumps | 2026-01-19 | Bilal | [7 empty] | 8:30 | 1:00 | 16.5
Bay 4&5 - Pumps | 2026-01-19 | Jaheer | Diesel Driven CP Pump | CD50E-001/004 | Parts cleaning, cramic coating | 2026-01-19 | 2026-01-31 | 2026-01-31 |  | 14:00 | 17:30 | 3.5 | Completed
Bay 4&5 - Pumps | 2026-01-19 | Bilal | [7 empty] | 14:00 | 17:30 | 3.5
Bay 4&5 - Pumps | 2026-01-19 | Asif | Diesel Driven CP Pump | CP108-004 | Engine top end repairing | 2026-01-17 | 2026-01-21 | 2026-01-21 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-19 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-19 | Suresh S | Contractor dewatering Pump | ZD900-032E | Pump dismantle & welding | 2026-01-16 | 2026-01-19 | 2026-01-19 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-19 | James | Contractor dewatering Pump | CP150-265 | Pump overhaul | 2026-01-09 | 2026-01-17 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-19 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-19 | Harish | Contractor dewatering Pump | CP150-184 | Pump repair ongoing | 2026-01-09 | 2026-01-19 | 2026-01-19 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-19 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-19 | Ismail | Contractor dewatering Pump | CP250-001 | Pump assembling | 2026-01-15 | 2026-01-19 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-01-19 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-19 | Mintu | Contractor dewatering Pump | Pressure washer | Engine repair for site maintenance | 2026-01-17 | 2026-01-19 | 2026-01-19 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-19 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-20 | Fahad | Panel | SPB7.5-003 | Safety glass, canopy fixing, test & PDI | 2026-01-13 | 2026-01-20 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-20 | Lijo | Panel | SPB7.5-023 | Safety glass, canopy fixing, test & PDI | 2026-01-13 | 2026-01-20 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-20 | Sulaiman | Panel | SPB3.7 | Dispatching panels | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-20 | Lijo | Generator | GENJ60-003 | Inspection & servicing | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-01-20 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-20 | Saqib | Submersible pump | SSD22-002 | Copper cable removing & rewinding | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-20 | Donald | Submersible pump | SM1002-142 | Inspection & reapair | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 9:00 | 15:30 | 6.5 | Completed
Electrical | 2026-01-20 | Gulam | [7 empty] | 9:00 | 15:30 | 6.5
Electrical | 2026-01-20 | Ghiyan | Generator | GENJ60-003 | Excide rotor rewinding | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-20 | Suhaib | Borehole pump | Old B:H pump | 15nos BH pumps inspection & repair | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-20 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-20 | Venu | Submersible pump | SM530-480 | Inspection & repair | 2026-01-17 | 2026-01-20 | 2026-01-20 |  | 9:00 | 15:30 | 6.5 | Completed
Electrical | 2026-01-20 | Donald | Other | Spider light | SLT018/21/30/32/027/017 6nos tower light for each 30meter cable & 6nos male socket | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 6:30 | 9:00 | 2.5 | Completed
Electrical | 2026-01-20 | Gulam | [7 empty] | 6:30 | 9:00 | 2.5
Electrical | 2026-01-20 | Venu | [7 empty] | 6:30 | 9:00 | 2.5
Bay 6 - Generator | 2026-01-20 | Suraj | Generator | GENJ150-058 | Final fitting | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 8:30 | 10:30 | 2 | Completed
Bay 6 - Generator | 2026-01-20 | Anwar | Generator | GEN150-037 | Engine parts cleaning. | 2026-01-15 | 2026-01-20 |  |  | 6:30 | 15:30 | 9 | Hold
Bay 6 - Generator | 2026-01-20 | Suraj | Generator | GENJ250-043 | Final fitting, PDI & flowfinity | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 10:30 | 13:30 | 3 | Completed
Bay 6 - Generator | 2026-01-20 | Suraj | Generator | GEN150-004 | General repair, load test | 2026-01-20 | 2026-01-20 |  |  | 13:30 | 17:30 | 4 | Hold
Bay 6 - Generator | 2026-01-20 | Hjagdev | Other | ABI-14/17-001 | Gearbox repaired onsite. | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 13:30 | 13:30 | 0 | Completed
Bay 4&5 - Pumps | 2026-01-20 | Martino | Diesel Driven CP Pump | CP108-004 | Vaccum pump & fleet number repairing | 2026-01-20 | 2026-01-21 | 2026-01-21 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-20 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-20 | Jaheer | Diesel Driven CP Pump | KV500-24 | Washing pump end flashing, cpoupling inspection & valve repairing | 2026-01-19 | 2026-01-31 | 2026-01-31 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-20 | Bilal | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-20 | Asif | Other | General work | Engine top end repairing | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-20 | Suresh S | Contractor dewatering Pump | ZD900-032E | Pump dismantle & welding, coating | 2026-01-16 | 2026-01-20 | 2026-01-20 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-20 | James | Contractor dewatering Pump | CP150-265 | Pump water test & engine repair. | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-20 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-20 | Harish | Contractor dewatering Pump | CP150-184 | Pump assembling | 2026-01-19 | 2026-01-20 |  |  | 6:30 | 10:30 | 4 | Ongoing
Bay 4&5 - Pumps | 2026-01-20 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-20 | Ismail | Contractor dewatering Pump | CP150-250 | Engine cylinder head repair | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-20 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-20 | Mintu | Contractor dewatering Pump | Pressure washer | Pressure washer Engine repair for site maintenance | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-20 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-20 | Mintu | Contractor dewatering Pump | PT175-550 | Pump dismantle for SWI | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-21 | Fahad | Panel | SPB7.5-109 | Modification, adding ELCB & safety glass | 2026-01-21 | 2026-01-24 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-21 | Lijo | Panel | SPB2.2-034 | Repair, test & PDI | 2026-01-21 | 2026-01-21 |  |  | 8:30 | 17:30 | 9 | Hold
Electrical | 2026-01-21 | Sulaiman | Panel | SPB7.5-085 | Modification, adding ELCB & safety glass | 2026-01-21 | 2026-01-24 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-21 | Cherith | Generator | GENJ60-003 | Inspection & assemble | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-01-21 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-21 | Donald | Submersible pump | SM1002-101 | Inspection & repair | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-21 | Ghiyan | Submersible pump | SM530-551 | Rewinding | 2026-01-21 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-21 | Suhaib | Borehole pump | Old B:H pump | 15nos BH pumps inspection & repair | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-21 | Afsar | Borehole pump | Old B:H pump | 5nos pump water testing | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-01-21 | Venu | Submersible pump | SM530-430 | Inspection & repair | 2026-01-21 | 2026-01-21 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-21 | Saqib | Submersible pump | SSD22-002 | Rewinding | 2026-01-21 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-21 | Gulam | Submersible pump | SM530-299 | Inspection & repair | 2026-01-21 | 2026-01-21 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-21 | Jagdev | Generator | GEN250-047 | Engine & ac alternator motor fix, radiator fix. | 2026-01-21 | 2026-01-21 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-21 | Anwar | [7 empty] | 6:30 | 8:30 | 2
Bay 6 - Generator | 2026-01-21 | Anwar | Generator | GEN80-014 | General repair, load test | 2026-01-21 | 2026-01-21 |  |  | 8:30 | 10:30 | 2 | Hold
Bay 6 - Generator | 2026-01-21 | Suraj | [7 empty] | 8:30 | 10:30 | 2
Bay 6 - Generator | 2026-01-21 | Anwar | Generator | GEN60-027 | General repair, load test, water test | 2026-01-21 | 2026-01-21 |  |  | 13:30 | 13:30 | 0 | Hold
Bay 6 - Generator | 2026-01-21 | Suraj | [7 empty] | 10:30 | 13:30 | 3
Bay 6 - Generator | 2026-01-21 | Anwar | Generator | GEN45-010 | General repair, load test, water test | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 9:00 | 14:00 | 5 | Completed
Bay 6 - Generator | 2026-01-21 | Suraj | [7 empty] | 9:00 | 14:00 | 5
Bay 6 - Generator | 2026-01-21 | Suraj | Generator | GEN60-027/028 | General repair, load test, water testing | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 14:00 | 17:30 | 3.5 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Martino | Diesel Driven CP Pump | CD225M-03 | Final fitting & vaccum testing | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 10:30 | 12:00 | 1.5 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Vinod | [7 empty] | 6:30 | 12:00 | 5.5
Bay 4&5 - Pumps | 2026-01-21 | Jaheer | Diesel Driven CP Pump | CD50E-001 | Repairing & water testing | 2026-01-21 | 2026-01-22 | 2026-01-22 |  | 8:30 | 13:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Bilal | [7 empty] | 8:30 | 13:00 | 4.5
Bay 4&5 - Pumps | 2026-01-21 | Asif | Other | General work | Engine top end repairing | 2026-01-21 | 2026-01-21 | 2026-01-21 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Suresh S | Contractor dewatering Pump | ZD900-032E | Pump dismantle & welding, coating | 2026-01-16 | 2026-01-20 | 2026-01-20 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-21 | James | Contractor dewatering Pump | CP150-265 | Pump water test & engine repair. | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-21 | Harish | Contractor dewatering Pump | CP150-184 | Pump assembling | 2026-01-19 | 2026-01-20 | 2026-01-20 |  | 6:30 | 10:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Shaji | [7 empty] | 8:30 | 10:30 | 2
Bay 4&5 - Pumps | 2026-01-21 | Ismail | Contractor dewatering Pump | CP150-250 | Engine cylinder head repair | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-21 | Mintu | Contractor dewatering Pump | Pressure washer | Pressure washer Engine repair for site maintenance | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-21 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Bay 4&5 - Pumps | 2026-01-21 | Mintu | Contractor dewatering Pump | PT175-550 | Pump dismantle for SWI | 2026-01-20 | 2026-01-20 | 2026-01-20 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-22 | Fahad | Panel | SPB7.5-163 | Modification, adding ELCB & safety glass | 2026-01-21 | 2026-01-24 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-22 | Lijo | Panel | DB-197 | Repair, test & PDI | 2026-01-22 | 2026-01-22 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-22 | Sulaiman | Panel | SPB7.5-163 | Modification, adding ELCB & safety glass | 2026-01-22 | 2026-01-22 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-22 | Cherith | Borehole pump | BFM400-002 | Inspection & repair | 2026-01-22 | 2026-01-22 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-22 | Aman | Generator | GENJ250-040 | copper cable removing for rewinding | 2026-01-22 | 2026-01-22 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-22 | Donald | Submersible pump | SM1002-186 | Inspection & repair | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-22 | Ghiyan | Submersible pump | SM530-551 | Rewinding | 2026-01-21 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-22 | Suhaib | Borehole pump | Old B:H pump | 14nos 3.7kw pumps inspection & fleet number tagging | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-01-22 | Afsar | [7 empty] | 8:30 | 13:00 | 4.5
Electrical | 2026-01-22 | Venu | Submersible pump | SM530-430 | Inspection & repair | 2026-01-21 | 2026-01-22 | 2026-01-22 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-22 | Saqib | Submersible pump | SSD22-002 | Rewinding | 2026-01-21 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-22 | Gulam | Generator | GEN250-047 | Inspection & repair | 2026-01-22 | 2026-01-22 |  |  | 8:30 | 12:00 | 3.5 | Ongoing
Bay 6 - Generator | 2026-01-22 | Anwar | Generator | GEN250-047 | Final fitting | 2026-01-22 | 2026-01-22 |  |  | 6:30 | 13:00 | 6.5 | Ongoing
Bay 6 - Generator | 2026-01-22 | Suraj | Generator | GEN150-004 | Load test | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 8:30 | 10:30 | 2 | Completed
Bay 6 - Generator | 2026-01-22 | Suraj | Generator | GEN80-014 | General repair, load test, | 2026-01-22 | 2026-01-22 |  |  | 10:30 | 13:30 | 3 | Ongoing
Bay 6 - Generator | 2026-01-22 | Suraj | Generator | GEN100-040 | General repair, load test, | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 13:30 | 17:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Martino | Diesel Driven CP Pump | AD1500-004 | Dsiccant changing. | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Vinod | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-22 | Jaheer | Diesel Driven CP Pump | CP1818-013 | Vaccum pump repair | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Bilal | Diesel Driven CP Pump | AD1500-004 | Activation carbon change. | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Suresh S | Contractor dewatering Pump | ZD900-032E | Pump dismantle & welding, coating | 2026-01-16 | 2026-01-22 | 2026-01-22 |  | 8:30 | 10:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Suresh S | Contractor dewatering Pump | PT175X11 | Frame & panel board removing. | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-22 | James | Contractor dewatering Pump | BL150-066 | Pump repair & water test. | 2026-01-21 | 2026-01-23 | 2026-01-23 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-22 | James | Contractor dewatering Pump | CP150-692 | pump dismantling | 2026-01-22 | 2026-01-22 | 2026-01-22 |  | 13:30 | 17:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Ismail | Contractor dewatering Pump | CP150-250 | Engine & pump assembling ongoing | 2026-01-20 | 2026-01-22 | 2026-01-22 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-22 | Mintu | Contractor dewatering Pump | PT175-550 | Pump end coating & assembling | 2026-01-20 | 2026-01-22 | 2026-01-22 |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-22 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-23 | Fahad | Panel | SPB7.5-163 | Modification, adding ELCB & safety glass | 2026-01-21 | 2026-01-24 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-23 | Lijo | Panel | SPB7.5-023 | Controol wiring | 2026-01-22 | 2026-01-23 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-23 | Sulaiman | Panel | SPB7.5-163 | Modification, adding ELCB & safety glass | 2026-01-22 | 2026-01-23 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-23 | Cherith | Generator | GENJ250-040 | copper cable removing for rewinding | 2026-01-23 | 2026-01-23 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-23 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-23 | Cherith | Other | FM200-125 | Inspection & repair | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 10:00 | 12:00 | 2 | Completed
Electrical | 2026-01-23 | Donald | Submersible pump | SM1002-086 | Inspection & repair | 2026-01-23 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-23 | Gulam | Submersible pump | AGT-001/002 | Inspection & testing | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 8:30 | 12:00 | 3.5 | Completed
Electrical | 2026-01-23 | Donald | Submersible pump | SM702-021 | pump rotor repiar | 2026-01-23 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-23 | Suhaib | Borehole pump | Old B:H pump | 15nos pumps inspection & repairing | 2026-01-23 | 2026-01-23 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-23 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-23 | Venu | Submersible pump | SM530-411/291 | Cable gland/pump dismantling | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-23 | Saqib | Submersible pump | SSD22-002 | Rewinding | 2026-01-21 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-23 | Ghiyan | Submersible pump | SM530-551 | Rewinding | 2026-01-23 | 2026-01-23 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-23 | Anwar | Generator | GEN250-047 | Final fitting | 2026-01-22 | 2026-01-22 |  |  | 6:30 | 13:00 | 6.5 | Ongoing
Bay 6 - Generator | 2026-01-23 | Suraj | Generator | GEN150-004 | Load test | 2026-01-22 | 2026-01-22 |  |  | 8:30 | 10:30 | 2 | Ongoing
Bay 6 - Generator | 2026-01-23 | Suraj | Generator | GEN80-014 | General repair, load test, | 2026-01-22 | 2026-01-22 |  |  | 10:30 | 13:30 | 3 | Ongoing
Bay 6 - Generator | 2026-01-23 | Suraj | Generator | GEN100-040 | General repair, load test, | 2026-01-22 | 2026-01-22 |  |  | 13:30 | 17:30 | 4 | Ongoing
Bay 4&5 - Pumps | 2026-01-23 | Jaheer | Diesel Driven CP Pump | AD1500-004 | Activated value, element filter change. | 2026-01-23 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-23 | Martino | Diesel Driven CP Pump | AD1500-004 | Desiccant change | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Vinod | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-23 | Harish | Contractor dewatering Pump | CP150-184 | Final fitting | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Harish | Contractor dewatering Pump | CP150-259 | pump assembling | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Suresh S | Contractor dewatering Pump | PT175X11 | Frame removing & fitting. | 2026-01-23 | 2026-01-23 | 2026-01-23 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-23 | James | Contractor dewatering Pump | CP150-692 | Pump dismantling | 2026-01-22 | 2026-01-23 | 2026-01-23 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-23 | Bharathesha | Contractor dewatering Pump | CP150-539 | Engine dismantling ongoing | 2026-01-22 | 2026-01-23 | 2026-01-23 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Ismail | Contractor dewatering Pump | CP150-250 | Engine prepare for assembling ongoing | 2026-01-20 | 2026-01-23 | 2026-01-23 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-23 | Mintu | Contractor dewatering Pump | PT175-550 | Pump end preparing and assembling | 2026-01-20 | 2026-01-23 | 2026-01-23 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-23 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-24 | Fahad | Panel | SPB7.5-163 | Modification, adding ELCB & safety glass | 2026-01-21 | 2026-01-24 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-24 | Lijo | Panel | SPB7.5-023 | Controol wiring | 2026-01-22 | 2026-01-24 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-24 | Sulaiman | Panel | SPB7.5-163 | Modification, adding ELCB & safety glass | 2026-01-22 | 2026-01-24 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-24 | Cherith | Generator | GENJ250-040 | copper cable removing for rewinding | 2026-01-23 | 2026-01-24 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-24 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-24 | Cherith | Other | FM200-125 | Inspection & repair | 2026-01-23 | 2026-01-23 |  |  | 10:00 | 12:00 | 2 | Ongoing
Electrical | 2026-01-24 | Donald | Submersible pump | SM1002-101/186/086SM530-430/411/291 SM1002-101/186/086 | water testing | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-24 | Gulam | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-24 | Ghiyan | Submersible pump | SM530-551 | Rewinding | 2026-01-23 | 2026-01-24 | 2026-01-24 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-24 | Suhaib | Borehole pump | Old B:H pump | 15nos pumps inspection & repairing, cable joint pump | 2026-01-24 | 2026-01-24 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-24 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-24 | Venu | Submersible pump | SM530-551 | Pump dismantle & repair | 2026-01-24 | 2026-01-26 | 2026-01-26 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-24 | Venu | Submersible pump | SM530-358 | Pump dismantle | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 13:00 | 15:30 | 2.5 | Completed
Electrical | 2026-01-24 | Saqib | Submersible pump | SSD22-002 | Rewinding | 2026-01-21 | 2026-01-24 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-24 | Anwar | Generator | GENP100-124 | Load test | 2026-01-24 | 2026-01-24 |  |  | 8:30 | 13:30 | 5 | Ongoing
Bay 6 - Generator | 2026-01-24 | Suraj | Generator | GENP100-127 | General repair | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 8:30 | 13:30 | 5 | Completed
Bay 6 - Generator | 2026-01-24 | Anwar | Generator | GEN80-014 | Fuel line repair, load test | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 1:30 | 15:30 | 14 | Completed
Bay 6 - Generator | 2026-01-24 | Suraj | [7 empty] | 1:30 | 15:30 | 14
Bay 6 - Generator | 2026-01-24 | Suraj | Generator | GENJ100-008 | General repair, starting problem, load test | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 15:30 | 17:30 | 2 | Completed
Bay 6 - Generator | 2026-01-24 | Jagdev | Generator | GEN250-047 | Inlet manifold & door fixing | 2026-01-24 | 2026-01-24 |  |  | 9:30 | 15:30 | 6 | Ongoing
Bay 4&5 - Pumps | 2026-01-24 | Martino | Diesel Driven CP Pump | AD1500-004 | Actuator pipe connecting & intercooler fixing | 2026-01-23 | 2026-01-31 | 2026-01-31 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-24 | Zaheer | Diesel Driven CP Pump | AD1500-004 | Air motor repair | 2026-01-24 | 2026-01-31 | 2026-01-31 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Vinod | Diesel Driven CP Pump | CD225M-03 |  | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 8:30 | 13:30 | 5 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Suresh S | Contractor dewatering Pump | CP150X3 | Pump repair | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 6:30 | 16:30 | 10 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Suresh S | Contractor dewatering Pump | PT175X11 | Frame & panel board removing & refitting | 2026-01-24 | 2026-01-24 | 2026-01-24 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Bharathesha | Contractor dewatering Pump | CP150-539 | Engine prepare for assembling | 2026-01-22 | 2026-01-29 | 2026-01-29 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Harish | Contractor dewatering Pump | CP150-259 | Pump assembling & water test | 2026-01-22 | 2026-01-24 | 2026-01-24 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-24 | James | Contractor dewatering Pump | CP150-692 | Pump prepare for assembling | 2026-01-22 | 2026-01-24 | 2026-01-24 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-24 | Ismail | Contractor dewatering Pump | CP150-250 | Engine prepare for assembling ongoing | 2026-01-20 | 2026-01-24 | 2026-01-24 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-24 | Mintu | Contractor dewatering Pump | PT175-550 | Pump assembling | 2026-01-20 | 2026-01-24 | 2026-01-24 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-24 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-26 | Fahad | Panel | CPB1.1-002 | Wiring power & control | 2026-01-25 | 2026-01-28 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-26 | Lijo | Panel | SPB7.5-023 | Control wiring | 2026-01-22 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-26 | Faisal | Panel | SPB7.5-163 | Sensors wiring & canopy fixing | 2026-01-21 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-26 | Cherith | Generator | GENJ250-040 | copper cable removing for rewinding | 2026-01-26 | 2026-01-28 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-26 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-26 | Donald | Submersible pump | SM1002-273 | Inspection & repair | 2026-01-26 | 2026-01-26 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-26 | Ghiyan | Submersible pump | SM530-380 | Rewinding | 2026-01-26 | 2026-01-27 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-26 | Suhaib | Borehole pump | Old B:H pump | 25nos pumps inspection & repairing, scrap | 2026-01-24 | 2026-01-26 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-26 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-26 | Venu | Submersible pump | SM530-551 | Pump assemble | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-26 | Gulam | Submersible pump | SDW40N-1005/004 | Inspection & dismantle | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-26 | Saqib | Submersible pump | SSD22-002 | Rewinding | 2026-01-21 | 2026-01-26 | 2026-01-26 |  | 8:30 | 13:00 | 4.5 | Completed
Bay 6 - Generator | 2026-01-26 | Anwar | Generator | GENP100-124 | Load test | 2026-01-24 | 2026-01-24 |  |  | 8:30 | 13:30 | 5 | Ongoing
Bay 6 - Generator | 2026-01-26 | Jagdev | Generator | GEN150-037 | Engine parts cleaning, washing | 2026-01-26 | 2026-01-26 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-26 | Suraj | [7 empty] | 8:30 | 17:30 | 9
Bay 6 - Generator | 2026-01-26 | Anwar | Generator | GEN250-047 | Manifold & safety guard fixing | 2026-01-24 | 2026-01-26 | 2026-01-26 |  | 6:30 | 10:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Zaheer | Diesel Driven CP Pump | AD1500-004 | Actuator pipe connecting & water separator connecting | 2026-01-23 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-26 | Martino | Diesel Driven CP Pump | CP1818-013 | Vaccum pump repair | 2026-01-26 | 2026-01-26 | 2026-01-26 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Vinod | Diesel Driven CP Pump | KV550-01 | Insppection, washing, repair | 2026-01-26 | 2026-01-28 | 2026-01-28 |  | 8:30 | 13:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Suresh S | Contractor dewatering Pump | CP150X3 | Pump repair | 2026-01-24 | 2026-01-26 | 2026-01-26 |  | 6:30 | 16:30 | 10 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Suresh | Contractor dewatering Pump | PT175X11 | Frame & panel board removing & refitting | 2026-01-24 | 2026-01-26 | 2026-01-26 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Bharathesha | Contractor dewatering Pump | CP150-539 | Engine prepare for assembling | 2026-01-22 | 2026-01-26 | 2026-01-26 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Harish | Contractor dewatering Pump | CP150-259 | Pump assembling & water test | 2026-01-22 | 2026-01-26 | 2026-01-26 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-26 | James | Contractor dewatering Pump | CP150-692 | Pump assembling & water test | 2026-01-22 | 2026-01-26 | 2026-01-26 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-26 | Ismail | Contractor dewatering Pump | CP150-250 | Engine assembling ongoing | 2026-01-20 | 2026-01-26 | 2026-01-26 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-26 | Mintu | Contractor dewatering Pump | PT175-550 | Pump assembling | 2026-01-20 | 2026-01-24 | 2026-01-24 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-26 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-27 | Fahad | Panel | CPB1.1-002 | Wiring power & control | 2026-01-25 | 2026-01-28 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-27 | Lijo | Panel | SPB7.5-023 | Control wiring | 2026-01-22 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-27 | Faisal | Panel | SPB7.5-163 | Sensors wiring & canopy fixing | 2026-01-21 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-27 | Cherith | Generator | GENJ250-040 | winding cutting & copper cable removing | 2026-01-26 | 2026-01-28 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-27 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-27 | Donald | Submersible pump | SM1002-273 | Inspection & repair | 2026-01-26 | 2026-01-27 |  |  | 6:30 | 8:30 | 2 | Completed
Electrical | 2026-01-27 | Ghiyan | Submersible pump | SM530-380 | Rewinding | 2026-01-26 | 2026-01-27 |  |  | 6:30 | 9:30 | 3 | Completed
Electrical | 2026-01-27 | Suhaib | Borehole pump | Old B:H pump | 15nos pumps inspection & repairing, | 2026-01-24 | 2026-01-27 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-27 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-27 | Venu | Submersible pump | SM530-238 | Pump assemble | 2026-01-26 | 2026-01-27 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-27 | Gulam | Submersible pump | SM250-047 | HCCB fixing, power cable connection. | 2026-01-27 | 2026-01-27 |  |  | 8:30 | 12:00 | 3.5 | Completed
Electrical | 2026-01-27 | Saqib | Submersible pump | SWD60H-003 | Rewinding | 2026-01-27 | 2026-01-29 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-27 | Anwar | Generator | GENP100-124 | Load test | 2026-01-24 | 2026-01-24 |  |  | 8:30 | 13:30 | 5 | Ongoing
Bay 6 - Generator | 2026-01-27 | Jagdev | Generator | GEN150-037 | Engine parts cleaning, washing | 2026-01-26 | 2026-01-27 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-27 | Suraj | Drill Rig | DR-17 | Hydraulic hose tightened, bonnet jack changing. | 2026-01-27 | 2026-01-27 | 2026-01-27 |  | 10:30 | 12:00 | 1.5 | Completed
Bay 6 - Generator | 2026-01-27 | Anwar | [7 empty] | 10:30 | 12:00 | 1.5
Bay 6 - Generator | 2026-01-27 | Suraj | Other | General work | General work | 2026-01-27 | 2026-01-27 | 2026-01-27 |  | 13:00 | 15:00 | 2 | Completed
Bay 6 - Generator | 2026-01-27 | Suraj | Generator | GENJ100-008 | Final fitting, fuel water seperator changing, | 2026-01-27 | 2026-01-27 | 2026-01-27 |  | 15:30 | 17:30 | 2 | Completed
Bay 6 - Generator | 2026-01-27 | Jagdev | Other | VHH4 | General repair onsite. | 2026-01-27 | 2026-01-27 | 2026-01-27 |  | 14:00 | 17:00 | 3 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Zaheer | Diesel Driven CP Pump | AD1500-004 | Actuator pipe connecting & water separator connecting | 2026-01-23 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-27 | Martino | Diesel Driven CP Pump | Gate Valve | Insppection, washing, repair | 2026-01-26 | 2026-01-27 | 2026-01-27 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Vinod | Diesel Driven CP Pump | Gate Valve | Insppection, washing, repair | 2026-01-26 | 2026-01-27 | 2026-01-27 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Suresh S | Contractor dewatering Pump | CP150X3 | Vaccum Pump repair | 2026-01-24 | 2026-01-27 | 2026-01-27 |  | 6:30 | 16:30 | 10 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Suresh | Contractor dewatering Pump | PT175X11 | Frame & panel board removing & refitting | 2026-01-24 | 2026-01-27 | 2026-01-27 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Bharathesha | Contractor dewatering Pump | CP150-539 | Engine assembling | 2026-01-22 | 2026-01-27 | 2026-01-27 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Harish | Contractor dewatering Pump | CP150-259 | Cylinder head repair | 2026-01-22 | 2026-01-27 | 2026-01-27 |  | 8:30 | 9:30 | 1 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Harish | Contractor dewatering Pump | PT175-552 | Pump remove & SWI making | 2026-01-22 | 2026-01-27 | 2026-01-27 |  | 9:30 | 17:30 | 8 | Completed
Bay 4&5 - Pumps | 2026-01-27 | James | Contractor dewatering Pump | CP150-692 | Minor repair & water test | 2026-01-22 | 2026-01-27 | 2026-01-27 |  | 6:30 | 9:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-27 | Ismail | Contractor dewatering Pump | CP150-250 | Pump assembling | 2026-01-20 | 2026-01-27 | 2026-01-27 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-27 | Mintu | Contractor dewatering Pump | CP150-882 | Pump & engine repair | 2026-01-27 | 2026-01-27 | 2026-01-27 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-27 | Shaji | [7 empty] | 14:00 | 16:00 | 2
Electrical | 2026-01-28 | Fahad | Panel | CPB1.1-002 | Wiring power & control | 2026-01-25 | 2026-01-28 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-28 | Lijo | Panel | SPB7.5-023 | Control wiring | 2026-01-22 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-28 | Faisal | Panel | SPB7.5-163 | Sensors wiring & canopy fixing | 2026-01-21 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-28 | Cherith | Generator | GENJ250-040 | winding cutting & copper cable removing | 2026-01-26 | 2026-01-28 |  |  | 6:30 | 17:30 | 11 | Hold
Electrical | 2026-01-28 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-28 | Cherith | Other | SGN-006 | Pump assemble | 2026-01-28 | 2026-01-28 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-01-28 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-01-28 | Donald | Submersible pump | SHD50-004 | Inspection & dismantle | 2026-01-28 | 2026-01-28 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-28 | Ghiyan | Submersible pump | SM530-299 | Rewinding | 2026-01-28 | 2026-01-28 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-28 | Suhaib | Borehole pump | Old B:H pump | 20nos pumps inspection, dismantle & scrap | 2026-01-28 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-28 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-28 | Venu | Submersible pump | SM530-380/238 | Water testing, rotor repair & assemble | 2026-01-28 | 2026-01-28 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-28 | Gulam | Submersible pump | SWD40N-003 | Pump assemble | 2026-01-28 | 2026-01-28 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-28 | Saqib | Submersible pump | SWD60H-003 | Rewinding | 2026-01-27 | 2026-01-29 | 2026-01-29 |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-01-28 | Anwar | Generator | GENP100-124 | Load test | 2026-01-24 | 2026-01-24 |  |  | 8:30 | 13:30 | 5 | Ongoing
Bay 6 - Generator | 2026-01-28 | Jagdev | Generator | GEN150-037 | Engine assembling | 2026-01-27 | 2026-01-28 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-28 | Suraj | Generator | GENG100-009 | Fan hub bearing changing, fan fix, load test. | 2026-01-24 | 2026-01-28 |  |  | 8:30 | 12:00 | 3.5 | Hold
Bay 6 - Generator | 2026-01-28 | Anwar | [7 empty] | 8:30 | 12:00 | 3.5
Bay 6 - Generator | 2026-01-28 | Suraj | Generator | GENJ60-003 | Ac alternator & fuel pump fix. | 2026-01-28 | 2026-01-28 | 2026-01-28 |  | 13:30 | 17:30 | 4 | Completed
Bay 6 - Generator | 2026-01-28 | Anwar | [7 empty] | 13:30 | 17:30 | 4
Bay 6 - Generator | 2026-01-28 | Suraj | Other | LB-004 | Load bank repairing & cover removing | 2026-01-28 | 2026-01-28 | 2026-01-28 |  | 12:00 | 15:00 | 3 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Zaheer | Diesel Driven CP Pump | AD1500-004 | Actuator pipe connecting & water separator connecting | 2026-01-23 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-28 | Martino | Diesel Driven CP Pump | Gate Valve | Insppection, washing, repair | 2026-01-26 | 2026-01-27 | 2026-01-27 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Vinod | Diesel Driven CP Pump | Gate Valve | Insppection, washing, repair | 2026-01-26 | 2026-01-27 | 2026-01-27 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Suresh S | Contractor dewatering Pump | CP150-882/860/v002 | Vaccum Pump repair | 2026-01-28 | 2026-01-28 | 2026-01-28 |  | 6:30 | 16:30 | 10 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Suresh | Contractor dewatering Pump | PT175X11 | Frame & panel board removing & refitting | 2026-01-24 | 2026-01-28 | 2026-01-28 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Mintu | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-28 | Bharathesha | Contractor dewatering Pump | CP150-539 | Pump dismantling | 2026-01-22 | 2026-01-28 | 2026-01-28 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Harish | Contractor dewatering Pump | PT175-552 | Pump prepare for assembling | 2026-01-22 | 2026-01-28 | 2026-01-28 |  | 9:30 | 15:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-28 | James | Contractor dewatering Pump | CP150-692 | Minor repair & water test | 2026-01-22 | 2026-01-27 | 2026-01-27 |  | 6:30 | 9:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-28 | James | Contractor dewatering Pump | CP150V-002 | Pump dismantling. | 2026-01-28 | 2026-01-28 | 2026-01-28 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Ismail | Contractor dewatering Pump | CP150-250 | Pump assembling waiting for parts | 2026-01-20 | 2026-01-28 | 2026-01-28 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-28 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-28 | Ismail | Contractor dewatering Pump | CP150-882 | Pump end repair | 2026-01-27 | 2026-01-28 | 2026-01-28 |  | 9:30 | 15:30 | 6 | Completed
Electrical | 2026-01-29 | Fahad | Panel | CPB1.1-002 | Wiring power & control | 2026-01-26 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-29 | Lijo | Panel | SPB7.5-023 | Repair, test & PDI | 2026-01-22 | 2026-01-31 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-29 | Faisal | Panel | SPB7.5-085 | Modification, adding, ELCB safety glass & rewiring. | 2026-01-29 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-29 | Cherith | Submersible pump | SGN-006 | Inspection & assemble | 2026-01-28 | 2026-01-29 | 2026-01-29 |  | 6:30 | 13:00 | 6.5 | Completed
Electrical | 2026-01-29 | Aman | [7 empty] | 6:30 | 13:00 | 6.5
Electrical | 2026-01-29 | Cherith | Submersible pump | SMSP3-021 | 95kw pump fixing | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 13:00 | 17:30 | 4.5 | Completed
Electrical | 2026-01-29 | Aman | [7 empty] | 13:00 | 17:30 | 4.5
Electrical | 2026-01-29 | Suleman | [7 empty] | 13:00 | 17:30 | 4.5
Electrical | 2026-01-29 | Donald | Submersible pump | SSD22-002 | Rotor repairing & assemble | 2026-01-29 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-29 | Ghiyan | Submersible pump | SM530-299 | Rewinding | 2026-01-27 | 2026-01-29 | 2026-01-29 |  | 6:30 | 12:00 | 5.5 | Completed
Electrical | 2026-01-29 | Suhaib | Borehole pump | Old B:H pump | 20nos pumps inspection, dismantle & scrap | 2026-01-28 | 2026-01-29 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-29 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-29 | Venu | Submersible pump | SM530-380 | Pump assemble | 2026-01-28 | 2026-01-29 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-29 | Gulam | Submersible pump | SWD40H-003 | Pump assemble | 2026-01-28 | 2026-01-29 | 2026-01-29 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-29 | Saqib | Generator | GEN60-003 | Inspection & power cable connection. | 2026-01-27 | 2026-01-29 | 2026-01-29 |  | 6:30 | 13:00 | 6.5 | Completed
Bay 6 - Generator | 2026-01-29 | Anwar | Generator | GENP100-124 | Load test | 2026-01-24 | 2026-01-24 |  |  | 8:30 | 13:30 | 5 | Ongoing
Bay 6 - Generator | 2026-01-29 | Jagdev | Generator | GEN150-037 | Engine assembling | 2026-01-27 | 2026-01-29 |  |  | 8:30 | 15:30 | 7 | Ongoing
Bay 6 - Generator | 2026-01-29 | Jagdev | Other | SCRLF19-001 | steering hydraulic cylinder seal changing | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 6:30 | 8:30 | 2 | Completed
Bay 6 - Generator | 2026-01-29 | Anwar | [7 empty] | 6:30 | 8:30 | 2
Bay 6 - Generator | 2026-01-29 | Suraj | Generator | GENJ60-003 | Ac alternator & fuel pump fix. | 2026-01-28 | 2026-01-29 | 2026-01-29 |  | 8:30 | 15:30 | 7 | Completed
Bay 6 - Generator | 2026-01-29 | Anwar | [7 empty] | 8:30 | 15:30 | 7
Bay 6 - Generator | 2026-01-29 | Suraj | Other | LB-004 | Load bank repairing & cover removing | 2026-01-28 | 2026-01-28 |  |  | 12:00 | 15:00 | 3 | Ongoing
Bay 6 - Generator | 2026-01-29 | Suraj | Other | General work | General work | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 15:30 | 17:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Zaheer | Diesel Driven CP Pump | AD1500-004 | Actuator pipe connecting &load test | 2026-01-23 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-29 | Martino | Diesel Driven CP Pump | CD50-004 | Pump repair | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Vinod | Other | Gate Valve | Insppection, washing, repair | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Harish | Contractor dewatering Pump | CP150V-002 | 3XVaccum Pump repair, completely rusty | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 6:30 | 9:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Suresh | Contractor dewatering Pump | PT175XMozambique | Frame & panel board removing & refitting | 2026-01-24 | 2026-01-29 | 2026-01-29 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Mintu | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-29 | Bharathesha | Contractor dewatering Pump | CP150-539 | Pump assembling | 2026-01-22 | 2026-01-29 | 2026-01-29 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Harish | Contractor dewatering Pump | PT175-552 | Pump prepare for assembling | 2026-01-22 | 2026-01-29 | 2026-01-29 |  | 9:30 | 15:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-29 | James | Contractor dewatering Pump | CP150V-002 | pump assemble | 2026-01-27 | 2026-01-29 | 2026-01-29 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-29 | James | Contractor dewatering Pump | BL150-88 | Engine repairing ongoing | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 11:30 | 15:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Ismail | Contractor dewatering Pump | CP150-882 | Pump end repair | 2026-01-27 | 2026-01-29 | 2026-01-29 |  | 6:30 | 11:30 | 5 | Completed
Bay 4&5 - Pumps | 2026-01-29 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-29 | Ismail | Contractor dewatering Pump | PT175-550 | Pump assembling, connecting rod. | 2026-01-29 | 2026-01-29 | 2026-01-29 |  | 11:30 | 15:30 | 4 | Completed
Electrical | 2026-01-30 | Fahad | Panel | CPB1.1-002 | Wiring power & control | 2026-01-26 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-30 | Lijo | Panel | SPB7.5-023 | Repair, test & PDI | 2026-01-29 | 2026-01-31 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-30 | Faisal | Panel | SPB7.5-085 | Modification, adding, ELCB safety glass & rewiring. | 2026-01-29 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-30 | Cherith | Generator | GENJ250-040 | Copper cable removing. | 2026-01-30 | 2026-01-31 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-30 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-30 | Donald | Submersible pump | SSD22-002 | Pump assembling | 2026-01-29 | 2026-01-30 |  |  | 6:30 | 9:30 | 3 | Ongoing
Electrical | 2026-01-30 | Ghiyan | Other | LB-004 | Inspection & repair | 2026-01-30 | 2026-01-30 |  |  | 6:30 | 10:00 | 3.5 | Completed
Electrical | 2026-01-30 | Suhaib | Borehole pump | Old B:H pump | 15nos pumps inspection & repair, 4nos pump water testing, 4nos pump cable joint | 2026-01-30 | 2026-01-30 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-30 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-30 | Venu | Submersible pump | SWD60H-003 | Rotor repairing & assemble | 2026-01-30 | 2026-01-31 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-30 | Saqib | Borehole pump | SWD40N-004 | Rewinding | 2026-01-30 | 2026-01-31 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-30 | Jagdev | Generator | GEN150-037 | Engine assembling | 2026-01-27 | 2026-01-30 |  |  | 8:30 | 15:30 | 7 | Ongoing
Bay 6 - Generator | 2026-01-30 | Suraj | Generator | GENJ100-009 | Canopy& radiator removing | 2026-01-30 | 2026-01-30 |  |  | 8:30 | 13:30 | 5 | Completed
Bay 6 - Generator | 2026-01-30 | Anwar | [7 empty] | 8:30 | 13:30 | 5
Bay 4&5 - Pumps | 2026-01-30 | Zaheer | Diesel Driven CP Pump | CP1818-020 | Radiator change | 2026-01-30 | 2026-02-02 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-30 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-30 | Martino | Diesel Driven CP Pump | CP1212-001 | General repair | 2026-01-30 | 2026-02-01 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-30 | Vinod | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-30 | Harish | Contractor dewatering Pump | CP150 | 1XVaccum Pump repair. | 2026-01-30 | 2026-01-30 |  |  | 6:30 | 9:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-01-30 | Suresh | Contractor dewatering Pump | PT175XMozambique | Frame & panel board removing & refitting ongoing | 2026-01-24 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-30 | Mintu | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-01-30 | Bharathesha | Contractor dewatering Pump | CP150-539 | Pump assembling ongoing | 2026-01-22 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-01-30 | Harish | Contractor dewatering Pump | PT175-552 | Pump prepare for assembling & gearbox assembling | 2026-01-27 | 2026-01-30 |  |  | 9:30 | 15:30 | 6 | Ongoing
Bay 4&5 - Pumps | 2026-01-30 | James | Contractor dewatering Pump | BL150-088 | pump assemble | 2026-01-27 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-30 | Shaji | [7 empty] | 13:00 | 14:00 | 1
Bay 4&5 - Pumps | 2026-01-30 | Ismail | Contractor dewatering Pump | PT175-550 | Pump end repair | 2026-01-27 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-30 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Electrical | 2026-01-31 | Fahad | Panel | CPB1.1-002 | Wiring power & control | 2026-01-26 | 2026-01-30 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-31 | Fahad | Panel | SPB95-002 | FFD Dismantling for Testing | 2026-01-31 | 2026-01-31 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-31 | Giyan | Submersible pump | SM530-134 | Re Winding | 2026-01-31 | 2026-01-31 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-01-31 | Lijo | Panel | SPB7.5-023 | Repair, test & PDI | 2026-01-29 | 2026-01-31 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-31 | Faisal | Panel | SPB7.5-085 | Modification, adding, ELCB safety glass & rewiring. | 2026-01-29 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-31 | Cherith | Generator | GENJ250-040 | Copper cable removing. | 2026-01-30 | 2026-01-31 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-01-31 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-31 | Donald | Submersible pump | SSD22-002 | Pump assembling | 2026-01-29 | 2026-01-31 |  |  | 6:30 | 9:30 | 3 | Ongoing
Electrical | 2026-01-31 | Ghiyan | Submersible pump | SM530-134 | Rewinding | 2026-01-30 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-01-31 | Afsar |  | Old B:H pump | 15nos scrap pump Inspection & repairing | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-01-31 | Suhaib | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-01-31 | Venu | Submersible pump | SWD60H-003 | pump assemble | 2026-01-30 | 2026-01-31 |  |  | 6:30 | 9:00 | 2.5 | Ongoing
Electrical | 2026-01-31 | Saqib | Borehole pump | SWD40N-004 | Rewinding | 2026-01-30 | 2026-01-31 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-01-31 | Jagdev | Generator | GEN150-037 | Engine assembling | 2026-01-27 | 2026-01-30 |  |  | 8:30 | 15:30 | 7 | Ongoing
Bay 6 - Generator | 2026-01-31 | Suraj | Generator | GEN250-051 | Engine oil service, general repair, radiator washing, | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-01-31 | Anwar | [7 empty] | 8:30 | 10:30 | 2
Bay 6 - Generator | 2026-01-31 | Suraj | Tank | BFT3-323/336 | Return adaptor fitting, final fitting | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 10:30 | 13:30 | 3 | Completed
Bay 6 - Generator | 2026-01-31 | Suraj | Generator | GEN100-40 | Final fitting, breaker cover fitting | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 13:30 | 15:30 | 2 | Completed
Bay 6 - Generator | 2026-01-31 | Suraj | Other | General work | General work | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 15:30 | 17:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Zaheer | Diesel Driven CP Pump | CP1818-020 | Radiator change | 2026-01-30 | 2026-02-02 | 2026-02-02 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-01-31 | Martino | Diesel Driven CP Pump | CP1212-001 | General repair | 2026-01-30 | 2026-02-01 | 2026-02-01 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Vinod | Diesel Driven CP Pump | CP1818-020 | General repair | 2026-01-30 | 2026-02-01 | 2026-02-01 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Mintu | Contractor dewatering Pump | PT-552 | Engine repair | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Suresh | Contractor dewatering Pump | Mozambique pump | Frame & panel board removing fabrication work & refitting | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Bharathesha | Contractor dewatering Pump | CP150-539 | Pump assembling ongoing | 2026-01-22 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Harish | Contractor dewatering Pump | PT175-552 | Pump prepare for assembling & gearbox assembling | 2026-01-27 | 2026-01-31 | 2026-01-31 |  | 9:30 | 15:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-01-31 | ISmail | Contractor dewatering Pump | CP150-250 | Pump assembling ongoing | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-01-31 | Shaji | [7 empty] | 10:30 | 12:00 | 1.5
Bay 4&5 - Pumps | 2026-01-31 | James | Contractor dewatering Pump | CP150X3 | Valve casing cleaning & fiber coating | 2026-01-31 | 2026-01-31 | 2026-01-31 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-02 | Fahad | Panel | 5XSCP | Inspection & repair | 2026-01-02 | 2026-01-02 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-02 | Lijo | Panel | CPB13.8/175 | Repair & solar fixing | 2026-01-02 | 2026-01-02 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-02 | Faisal | Panel | SPB7.5-085 | Modification, adding, ELCB safety glass & rewiring. | 2026-01-29 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-02 | Cherith | Generator | GENJ250-040 | Copper cable removing. | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 6:30 | 17:30 | 11 | Completed
Electrical | 2026-02-02 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-02-02 | Donald | Submersible pumps | SGN-006 | Water testing | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 6:30 | 10:00 | 3.5 | Completed
Electrical | 2026-02-02 | Venu | [7 empty] | 6:30 | 10:00 | 3.5
Electrical | 2026-02-02 | Ghiyan | Submersible pump | SM530-134 | Rewinding | 2026-02-02 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-02 | Afsar | Borehole pump | Old B:H pump | 15nos scrap pump Inspection & repairing, 4nos cable joints. | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-02 | Suhaib | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-02-02 | Saqib | Borehole pump | SWD40N-004 | Rewinding | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-02-02 | Jagdev | Generator | GEN150-037 | Engine assembling | 2026-01-27 | 2026-02-02 | 2026-02-02 |  | 8:30 | 15:30 | 7 | Completed
Bay 6 - Generator | 2026-02-02 | Suraj | Generator | GEN200-004 | Engine dismantling. | 2026-02-02 | 2026-02-02 |  |  | 8:30 | 17:30 | 9 | Hold
Bay 6 - Generator | 2026-02-02 | Mamun | [7 empty] | 8:30 | 17:30 | 9
Bay 6 - Generator | 2026-02-02 | Suraj | Generator | GEN150-037 | Foam sheet fixing | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 4:30 | 17:30 | 13 | Completed
Bay 4&5 - Pumps | 2026-02-02 | Zaheer | Diesel Driven CP Pump | CP1818-020 | Vaccum test, final fitting & PDI | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-02 | Bilal | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-02 | Martino | Diesel Driven CP Pump | CP1212-026 | Pump overhauling | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-02 | Vinod | Diesel Driven CP Pump | [6 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-02-02 | Mintu | Contractor dewatering Pump | ZD900-033 | Engine repair | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-02 | Suresh | Contractor dewatering Pump | CP150-507 | pump dismantling | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-02 | Bharathesha | Contractor dewatering Pump | CP150-507 | Engine dismantling. | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-02 | Harish | Contractor dewatering Pump | PT175-552 | Pump assembling | 2026-01-29 | 2026-02-02 | 2026-02-02 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-02 | ISmail | Contractor dewatering Pump | CP150-250 | Pump assembling ongoing | 2026-01-31 | 2026-02-02 | 2026-02-02 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-02 | Shaji | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-02 | James | Contractor dewatering Pump | ZD900-033 | Pump dismantling | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-03 | Fahad | Panel | SPB3.7-169 | Repair, test & PDI | 2026-01-03 | 2026-01-03 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-03 | Lijo | Panel | CPB3.7-171 | Repair & solar fixing | 2026-01-03 | 2026-01-03 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-03 | Faisal | Panel | SPB7.5-085 | Modification, adding, ELCB safety glass & rewiring. | 2026-01-29 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-03 | Cherith | Other | FM200X4/300X4 | Inspection, power & PDI | 2026-02-03 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-03 | Aman | Other | FM150X4/300X4 | Inspection, power & PDI | 2026-02-03 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-03 | Donald | Submersible pumps | SM1002-273/SSD22-002 | Water testing | 2026-02-03 | 2026-02-03 |  |  | 6:30 | 10:00 | 3.5 | Completed
Electrical | 2026-02-03 | Venu | [7 empty] | 6:30 | 10:00 | 3.5
Electrical | 2026-02-03 | Afsar | Borehole pump | Old B:H pump | 9nos pump Inspection & water tesring | 2026-02-03 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-03 | Suhaib | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-02-03 | Saqib | Submersible pumps | SM530-134 | Rewinding | 2026-02-03 | 2026-02-04 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-02-03 | Jagdev | Generator | GEN150-037 | Engine & ac alternator fixing. | 2026-01-27 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Hold
Bay 6 - Generator | 2026-02-03 | Anwar | [7 empty] | 6:30 | 10:00 | 3.5
Bay 6 - Generator | 2026-02-03 | Suraj | Diesel Driven CP Pump | ZD900-065 | pump assembling | 2026-02-02 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 6 - Generator | 2026-02-03 | Anwar | [7 empty] | 10:00 | 15:30 | 5.5
Bay 4&5 - Pumps | 2026-02-03 | Zaheer | Diesel Driven CP Pump | CD180M-22 | Inspection & general repair | 2026-02-03 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Bilal | Diesel Driven CP Pump | AC375-012 | Oil Service, general checkup | 2026-02-03 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Martino | Diesel Driven CP Pump | CP1212-026 | Pump overhauling | 2026-02-03 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Vinod | Diesel Driven CP Pump | CP1212S17-001 | Pump overhauling | 2026-02-03 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Mintu | Contractor dewatering Pump | ZD900-033 | Engine repair ongoing | 2026-02-02 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Suresh | Contractor dewatering Pump | CP150-507 | Pump prepare for assembling | 2026-02-02 | 2026-02-03 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Bharathesha | Contractor dewatering Pump | CP150-507 | Engine prepare for assembling | 2026-02-02 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Harish | Contractor dewatering Pump | PT175-552 | Pump assembling ongoing | 2026-01-29 | 2026-02-03 |  |  | 9:30 | 15:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Harish | Contractor dewatering Pump | CP150-882 | Final fitting & minor repair | 2026-02-03 | 2026-02-03 |  |  | 6:30 | 8:00 | 1.5 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Harish | Contractor dewatering Pump | CP150-259 | Final fitting & minor repair | 2026-02-03 | 2026-02-03 |  |  | 8:00 | 9:30 | 1.5 | Completed
Bay 4&5 - Pumps | 2026-02-03 | ISmail | Contractor dewatering Pump | CP150-250 | Pump assembling ongoing | 2026-01-31 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-03 | Shaji | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-03 | James | Contractor dewatering Pump | ZD900-033 | Pump prepare for assembling | 2026-02-02 | 2026-02-03 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-04 | Fahad | Panel | SPB3.7-021 | Repair, test & PDI | 2026-01-04 | 2026-01-04 | 2026-01-04 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-04 | Suleman | Panel | SPB3.7-054 | Repair, test & PDI | 2026-01-04 | 2026-01-04 | 2026-01-04 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-04 | Faisal | Panel | DB299/059 | Repair, test & PDI | 2026-01-04 | 2026-01-04 | 2026-01-04 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-04 | Cherith | Other | FM-150/200/300 | 8nos flowmeter inspection & PDI | 2026-02-03 | 2026-02-04 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-04 | Aman | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-02-04 | Ghiyan | Submersible pump | SM530 | Rewinding | 2026-01-04 | 2026-01-04 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-04 | Donald | Submersible pumps | SSD18-002 | inspection & dismantling | 2026-01-04 | 2026-01-04 | 2026-01-04 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-04 | Venu | Borehole pump | SWD60H-003 | Pump aassembling | 2026-01-04 | 2026-01-04 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-04 | Afsar | Borehole pump | Old B:H pump | 15nos pump Inspection & scrap/ 4nos pump cable joint | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-04 | Suhaib | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-02-04 | Saqib | Submersible pump | SM1002 | Rewinding | 2026-02-04 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-04 | Jagdev | Generator | GEN150-037 | Engine & ac alternator fixing, canopy fixing | 2026-01-27 | 2026-01-04 | 2026-01-04 |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-02-04 | Suraj | Generator | GEN60-80/63/077/065 | Water washing, general repair & load test | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 8:30 | 17:30 | 9 | Completed
Bay 6 - Generator | 2026-02-04 | Anwar | [7 empty] | 6:30 | 15:30 | 9
Bay 6 - Generator | 2026-02-04 | Suraj | Generator | GEN100-013 | Final fitting | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 15:30 | 17:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Zaheer | Diesel Driven CP Pump | CD180M-22 | Muffler change & general repair work. | 2026-02-04 | 2026-02-07 | 2026-02-07 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Bilal | Diesel Driven CP Pump | CD300M-015 | Inspection & overhauling | 2026-02-04 | 2026-02-08 | 2026-02-08 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Vinod | Diesel Driven CP Pump | CP1212S17-001 | Pump assembling | 2026-02-04 | 2026-02-06 | 2026-02-06 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Mintu | Contractor dewatering Pump | ZD900-033 | Engine repair ongoing | 2026-02-02 | 2026-02-04 | 2026-02-04 |  | 6:30 | 10:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Suresh | Contractor dewatering Pump | CP150-507 | Pump prepare for assembling | 2026-02-02 | 2026-02-03 | 2026-02-03 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Bharathesha | Contractor dewatering Pump | CP150-507 | Engine assembling | 2026-02-02 | 2026-02-04 | 2026-02-04 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Suresh | Contractor dewatering Pump | CP150-054 | Pump repair & water test | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Harish | Contractor dewatering Pump | PT175-552 | Pump assembling, water testing & engine repair | 2026-01-29 | 2026-02-04 | 2026-02-04 |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Mintu | [7 empty] | 10:30 | 12:30 | 2
Bay 4&5 - Pumps | 2026-02-04 | Harish | Contractor dewatering Pump | CP150V-015 | Pump repair & water test | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 12:30 | 15:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Mintu | Other | SCRLFT19-001 | hydraulic hose repair | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 13:30 | 14:00 | 0.5 | Completed
Bay 4&5 - Pumps | 2026-02-04 | ISmail | Contractor dewatering Pump | CP150-250 | Pump assembling ongoing | 2026-01-31 | 2026-02-04 | 2026-02-04 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Shaji | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-04 | ISmail | Contractor dewatering Pump | CP150V-062 | Engine & pump repair ongoing | 2026-02-02 | 2026-02-04 | 2026-02-04 |  | 14:00 | 17:30 | 3.5 | Completed
Bay 4&5 - Pumps | 2026-02-04 | Mintu | [7 empty] | 12:30 | 15:30 | 3
Bay 4&5 - Pumps | 2026-02-04 | James | Contractor dewatering Pump | ZD900-033 | Pump assembling | 2026-02-02 | 2026-02-04 | 2026-02-04 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-05 | Fahad | Panel | SPB2.2-020 | Repair, test & PDI | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-05 | Suleman | Panel | SPB7.5-025/003 | Repair, test & PDI | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-05 | Faisal | Panel | SPB2.2-034 | Repair, test & PDI | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-05 | Cherith | Other | FM-150/200/300 | Inspection & PDI | 2026-02-05 | 2026-02-05 |  |  | 8:30 | 12:00 | 3.5 | Ongoing
Electrical | 2026-02-05 | Aman | [7 empty] | 8:30 | 12:00 | 3.5
Electrical | 2026-02-05 | Cherith | Generator | GENJ250-040 | Cleaning & paper instenciling | 2026-02-05 | 2026-02-05 |  |  | 12:00 | 17:30 | 5.5 | Ongoing
Electrical | 2026-02-05 | Aman | [7 empty] | 12:00 | 17:30 | 5.5
Electrical | 2026-02-05 | Ghiyan | Generator | GEN60-013/003 | Pwer cable connection. | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-05 | Donald | Submersible pumps | SM1002-019 | inspection & dismantling | 2026-01-04 | 2026-01-05 | 2026-01-05 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-05 | Venu | Submersible pumps | SWD60N-003 | Pump aassembling | 2026-01-04 | 2026-01-05 | 2026-01-05 |  | 6:30 | 12:00 | 5.5 | Completed
Electrical | 2026-02-05 | Venu | Submersible pumps | SM530/419 | Inspection & dismantle | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 12:00 | 15:30 | 3.5 | Completed
Electrical | 2026-02-05 | Suhaib | Borehole pump | Old B:H pump | 15nos pump inspection & prepare for scrap. | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-05 | Saqib | Submersible pump | SM1002-179 | Rewinding | 2026-02-04 | 2026-01-05 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-05 | Suraj | Generator | GEN60-41 | Coolant connection, pipe fitting, starting & voltage setting, load test | 2026-02-05 | 2026-02-05 |  |  | 8:30 | 11:30 | 3 | Ongoing
Bay 6 - Generator | 2026-02-05 | Anwar | [7 empty] | 8:30 | 11:30 | 3
Bay 6 - Generator | 2026-02-05 | Suraj | Generator | GEN60-27 | Final fitting | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 15:30 | 16:30 | 1 | Completed
Bay 6 - Generator | 2026-02-05 | Suraj | Other | General work | General work | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 16:30 | 17:30 | 1 | Completed
Bay 6 - Generator | 2026-02-05 | Anwar | Generator | GENG100-009 | radiator fixed | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | 11:30 | 15:30 | 4 | Completed
Bay 6 - Generator | 2026-02-05 | Mamun | Diesel Driven CP Pump | CD180M-22 | Installation on test bay for water test. | 2026-02-05 | 2026-02-07 | 2026-02-07 |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-02-05 | Anwar | [7 empty] | 8:30 | 17:30 | 9
Bay 4&5 - Pumps | 2026-02-05 | Zaheer | Diesel Driven CP Pump | CP1212S17-001 | Pump assembling | 2026-02-05 | 2026-02-06 | 2026-02-06 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-05 | Bilal | Diesel Driven CP Pump | CP1212S17-026 | Seramle coating | 2026-02-05 | 2026-02-06 | 2026-02-06 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Martino | Diesel Driven CP Pump | CD300M-015 | Mechanical seal change | 2026-02-05 | 2026-02-08 | 2026-02-08 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Mintu | Contractor dewatering Pump | CP150V-062 | Engine & pump repair ongoing | 2026-02-02 | 2026-02-05 | 2026-02-05 |  | 14:30 | 17:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Suresh | Contractor dewatering Pump | CP150V-073 | Pump repair & water test | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Bharathesha | Contractor dewatering Pump | CP150-507 | Engine assembling | 2026-02-02 | 2026-02-05 | 2026-02-05 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Suresh | Contractor dewatering Pump | CP150-054 | Pump repair & water test | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Harish | Contractor dewatering Pump | CP150-309 | Pump dismantling | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 8:30 | 15:30 | 7 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Harish | Contractor dewatering Pump | CP150-692 | final fitting | 2026-02-05 | 2026-02-05 | 2026-02-05 |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Harish | Contractor dewatering Pump | CP150V-015 | Pump repair & water test | 2026-02-04 | 2026-02-04 | 2026-02-04 |  | 12:30 | 15:30 | 3 | Completed
Bay 4&5 - Pumps | 2026-02-05 | ISmail | Contractor dewatering Pump | CP150-250 | Pump water test & repair | 2026-01-31 | 2026-02-05 | 2026-02-05 |  | 6:30 | 12:30 | 6 | Completed
Bay 4&5 - Pumps | 2026-02-05 | Shaji | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-05 | James | Contractor dewatering Pump | ZD900-033 | Pump assembling ongoing | 2026-02-02 | 2026-02-05 | 2026-02-05 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-06 | Fahad | Panel | SPB3.7-109 | Repair, test & PDI | 2026-01-06 | 2026-01-06 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-06 | Suleman | Panel | SPB7.5-194 | Repair, test & PDI | 2026-01-06 | 2026-01-06 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-06 | Faisal | Panel | SPB3.7-029 | Repair, test & PDI | 2026-01-06 | 2026-01-06 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-06 | Cherith | Generator | GENJ250-040 | Cleaning & paper instenciling | 2026-02-05 | 2026-02-06 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-02-06 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-02-06 | Ghiyan | Submersible pump | SM530-611 | Rewinding & connection. | 2026-01-04 | 2026-01-06 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-06 | Donald | Submersible pump | SM1002-019 | Water Test | 2026-01-05 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-06 | Venu | Submersible pump | SM530/419 | Servicing & pump assemble | 2026-01-06 | 2026-01-06 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-06 | Suhaib | Borehole pump | Old B:H pump | 15nos pump inspection & repair. | 2026-02-06 | 2026-02-07 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-06 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-02-06 | Saqib | Submersible pump | SM1002-179 | Rewinding | 2026-02-04 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-06 | Jagdev | Generator | GEN7-008 | General repair, gasket setting | 2026-01-06 | 2026-01-06 |  |  | 6:30 | 8:30 | 2 | Completed
Bay 6 - Generator | 2026-02-06 | Jagdev | Generator | GENS100-067 | General repair, fuel tank cleaning,load test | 2026-01-06 | 2026-01-06 |  |  | 8:30 | 15:30 | 7 | Hold
Bay 6 - Generator | 2026-02-06 | Suraj | Generator | GEN60-41 | Silencer bellow changing, load test | 2026-01-24 | 2026-02-06 |  |  | 8:30 | 11:30 | 3 | Hold
Bay 6 - Generator | 2026-02-06 | Anwar | [7 empty] | 8:30 | 11:30 | 3
Bay 6 - Generator | 2026-02-06 | Suraj | Generator | GENJ60-003 | Load test | 2026-01-05 | 2026-02-06 |  |  | 11:30 | 13:30 | 2 | Completed
Bay 6 - Generator | 2026-02-06 | Anwar | [7 empty] | 11:30 | 13:30 | 2
Bay 6 - Generator | 2026-02-06 | Suraj | Other | General work | General work | 2026-01-06 | 2026-01-06 |  |  | 13:30 | 15:30 | 2 | Completed
Bay 6 - Generator | 2026-02-06 | Suraj | Generator | GEN80-014 | Final fitting | 2026-01-06 | 2026-01-06 |  |  | 15:30 | 17:30 | 2 | Completed
Bay 6 - Generator | 2026-02-06 | Mamun | Diesel Driven CP Pump | CD180M-22 | Fuel tank clean & vaccum test | 2026-02-06 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 6 - Generator | 2026-02-06 | Anwar | Diesel Driven CP Pump | CD300M-015 | water test | 2026-02-06 | 2026-02-07 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | Zaheer | Diesel Driven CP Pump | SCT700-01 | Engine removing | 2026-02-06 | 2026-02-15 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-06 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-06 | Bilal | Diesel Driven CP Pump | SCT700-01 | Engine removing | 2026-02-06 | 2026-02-15 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-06 | Martino | Diesel Driven CP Pump | CD300M-015 | Installation, water & vaccum test | 2026-02-06 | 2026-02-06 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | Mintu | Contractor dewatering Pump | CP150V-040 | Cylinder head dismantling | 2026-02-02 | 2026-02-06 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-06 | Suresh | Contractor dewatering Pump | CP150V-073 | Pump repair & water test | 2026-02-05 | 2026-02-05 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | Bharathesha | Contractor dewatering Pump | CP150-507 | Engine fixing on pump with all connections. | 2026-02-02 | 2026-02-06 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | Suresh | Contractor dewatering Pump | CP150V-004 | Pump repair & water test | 2026-02-06 | 2026-02-06 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | Harish | Contractor dewatering Pump | CP150-309 | Pump prepapre for assembling | 2026-02-05 | 2026-02-06 |  |  | 8:30 | 15:30 | 7 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | Harish | Contractor dewatering Pump | PT175-552 | final fitting | 2026-02-06 | 2026-02-06 |  |  | 6:30 | 8:30 | 2 | Completed
Bay 4&5 - Pumps | 2026-02-06 | Harish | Contractor dewatering Pump | CP150V-015 | Pump repair & water test | 2026-02-04 | 2026-02-04 |  |  | 12:30 | 15:30 | 3 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | ISmail | Contractor dewatering Pump | ZD900-065 | Pump water test & repair | 2026-02-06 | 2026-02-06 |  |  | 6:30 | 10:00 | 3.5 | Ongoing
Bay 4&5 - Pumps | 2026-02-06 | Shaji | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-06 | James | Contractor dewatering Pump | ZD900-033 | Pump repair & water test | 2026-02-02 | 2026-02-06 |  |  | 6:30 | 10:30 | 4 | Completed
Electrical | 2026-02-07 | Suleman | Panel | SPB7.5-194 | Repair, test & PDI | 2026-01-06 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-07 | Faisal | Panel | SPB3.7-029 | Repair, test & PDI | 2026-01-06 | 2026-01-06 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-07 | Cherith | Generator | GENJ250-040 | Cleaning & paper instenciling | 2026-02-05 | 2026-02-06 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-02-07 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-02-07 | Ghiyan | Submersible pump | SM530-611 | Rewinding & connection. | 2026-01-04 | 2026-01-06 |  |  | 6:30 | 12:00 | 5.5 | Ongoing
Electrical | 2026-02-07 | Donald | Submersible pump | SM1002-019 | Water Test | 2026-01-05 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-07 | Venu | Submersible pump | SM530/419 | Servicing & pump assemble | 2026-01-06 | 2026-01-06 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-07 | Suhaib | Borehole pump | Old B:H pump | 15nos pump inspection & repair. | 2026-02-06 | 2026-02-07 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-07 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-02-07 | Saqib | Submersible pump | SM1002-179 | Rewinding | 2026-02-04 | 2026-02-07 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-07 | Jagdev | Generator | GENS100-067 | General repair, fuel tank cleaning,load test | 2026-01-06 | 2026-01-07 | 2026-01-07 |  | 8:30 | 10:30 | 2 | Completed
Bay 6 - Generator | 2026-02-07 | Suraj | Generator | GEN60-41 | Radiator Cleaning | 2026-01-24 | 2026-02-07 | 2026-02-07 |  | 10:30 | 2:30 | 16 | Completed
Bay 6 - Generator | 2026-02-07 | Anwar | [7 empty] | 8:30 | 11:30 | 3
Bay 6 - Generator | 2026-02-07 | Suraj | Generator | GENJ60-003 | Load test | 2026-01-05 | 2026-02-06 | 2026-02-06 |  | 11:30 | 13:30 | 2 | Completed
Bay 6 - Generator | 2026-02-07 | Anwar | [7 empty] | 11:30 | 13:30 | 2
Bay 6 - Generator | 2026-02-07 | Suraj | Other | General work | General work | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 13:30 | 15:30 | 2 | Completed
Bay 6 - Generator | 2026-02-07 | Suraj | Generator | GEN80-014 | Final fitting | 2026-01-06 | 2026-01-06 | 2026-01-06 |  | 15:30 | 17:30 | 2 | Completed
Bay 6 - Generator | 2026-02-07 | Anwar | Diesel Driven CP Pump | CD300M-015 | water test | 2026-02-06 | 2026-02-07 | 2026-02-07 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Zaheer | Diesel Driven CP Pump | SCT700-01 | Engine removing | 2026-02-06 | 2026-02-15 | 2026-02-15 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Vinod | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-07 | Vinod | Diesel Driven CP Pump | SCT700-01 | Engine removing | 2026-02-06 | 2026-02-15 | 2026-02-15 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Martino | Diesel Driven CP Pump | CD300M-015 | Installation, water & vaccum test | 2026-02-06 | 2026-02-06 | 2026-02-06 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Martino | Diesel Driven CP Pump | CP108-004 | Installation, water & vaccum test | 2026-02-06 | 2026-02-08 | 2026-02-08 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Martino | Diesel Driven CP Pump | CP108-004 | Water Test | 2026-02-06 | 2026-02-07 | 2026-02-07 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Mintu | Contractor dewatering Pump | CP150V-040 | Cylinder head dismantling | 2026-02-02 | 2026-02-07 | 2026-02-07 |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Bharathesha | Contractor dewatering Pump | CP150-507 | Engine fixing on pump with all connections. | 2026-02-02 | 2026-02-07 | 2026-02-07 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Harish | Contractor dewatering Pump | CP150-309 | Pump prepapre for assembling | 2026-02-05 | 2026-02-06 |  |  | 8:30 | 15:30 | 7 | Ongoing
Bay 4&5 - Pumps | 2026-02-07 | ISmail | Contractor dewatering Pump | ZD900-065 | Pump water test & repair | 2026-02-06 | 2026-02-06 | 2026-02-06 |  | 6:30 | 10:00 | 3.5 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Shaji | [7 empty] | 6:30 | 15:30 | 9
Bay 4&5 - Pumps | 2026-02-07 | James | Contractor dewatering Pump | ZD900-033 | Pump repair & water test | 2026-02-02 | 2026-02-06 | 2026-02-06 |  | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-02-07 | Jagdev | Generator | GEN150-037 | Raduiator Fixing, Fuel Tank Cleaning & Valve Clearance | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 6:30 | 11:30 | 5 | Completed
Bay 6 - Generator | 2026-02-07 | Suraj | Generator | GENG80-005 | Genearal Repair | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 11:30 | 3:30 | 16 | Completed
Electrical | 2026-02-07 | Faisal | Panel | SPB3.7-097 | Repair, test & PDI | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-07 | Suleman | Panel | 3XSPB Panel | PDI & Dispatching | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Harish | Contractor dewatering Pump | ZD900-032E | Final Fitting PDI & Flow testing | 2026-02-07 | 2026-02-07 | 2026-02-07 |  | 6:30 | 10:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Suresh | Contractor dewatering Pump | CP150V-004 | Pump repair & water test | 2026-02-06 | 2026-02-07 | 2026-02-07 |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-07 | Shaji | Contractor dewatering Pump |  | Pump repair & water test | 2026-02-06 | 2026-02-07 | 2026-02-07 |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-06 | James | Contractor dewatering Pump | CP150-309 | Pump Repair | 2026-02-06 | 2026-02-06 |  |  | 8:30 | 15:30 | 7 | Completed
Electrical | 2026-02-09 | Fahad | Panel | SPB3.7-058 | Repair, test & PDI | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-09 | Suleman | Panel | DB-091 | 3XSPB PDI & dispatching | 2026-01-09 | 2026-01-09 |  |  | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-09 | Faisal | Panel | SPB3.7-094 | Repair, test & PDI | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 15:30 | 9 | Ongoing
Electrical | 2026-02-09 | Cherith | Generator | GENJ250-040 | Slot paper & coil making | 2026-02-05 | 2026-02-11 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-02-09 | Aman | [7 empty] | 6:30 | 17:30 | 11
Electrical | 2026-02-09 | Gihan | Submersible pump | SM530-611 | Rewinding & connection. | 2026-01-05 | 2026-01-09 |  |  | 6:30 | 12:00 | 5.5 | Completed
Electrical | 2026-02-09 | Gihan | Submersible pump | SM530-355 | Winding cutting & cleaning. | 2026-01-09 | 2026-01-09 |  |  | 13:00 | 15:30 | 2.5 | Ongoing
Electrical | 2026-02-09 | Donald | Submersible pump | SSD18-002 | Inspection & pump parts cleaning. | 2026-01-09 | 2026-01-09 |  |  | 6:30 | 12:00 | 5.5 | Ongoing
Electrical | 2026-02-09 | Donald | Submersible pump | SM1002-019 | Water testing | 2026-01-09 | 2026-01-09 |  |  | 13:00 | 15:30 | 2.5 | Completed
Electrical | 2026-02-09 | Venu | Submersible pump | SM530-546 | Rotor repairing & assemble | 2026-01-09 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-09 | Suhaib | Borehole pump | Old B:H pump | 15nos pump inspection & repair. | 2026-02-09 | 2026-02-09 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-09 | Afsar | [7 empty] | 8:30 | 17:30 | 9
Electrical | 2026-02-09 | Saqib | Submersible pump | SM1002-179 | Rewinding & connection. | 2026-02-04 | 2026-02-09 |  |  | 6:30 | 12:00 | 5.5 | Completed
Electrical | 2026-02-09 | Saqib | Submersible pump | SM1002-200 | Winding cutting & cleaning. | 2026-02-09 | 2026-02-09 |  |  | 13:00 | 15:30 | 2.5 | Ongoing
Bay 6 - Generator | 2026-02-09 | Suraj | Generator | GEN150-021 | Radiator fixing & fuel tank cleaning. | 2026-01-09 | 2026-01-09 |  |  | 8:30 | 13:30 | 5 | Ongoing
Bay 6 - Generator | 2026-02-09 | Jagdev | Generator | GEN150-037 | Panel board & air filter modification. | 2026-01-27 | 2026-02-09 |  |  | 6:30 | 8:30 | 2 | Completed
Bay 6 - Generator | 2026-02-09 | Anwar | [7 empty] | 6:30 | 8:30 | 2
Bay 6 - Generator | 2026-02-09 | Jagdev | Generator | GENJ100-008 | Fuel pump & injector removing | 2026-02-09 | 2026-02-09 |  |  | 8:30 | 12:00 | 3.5 | Completed
Bay 6 - Generator | 2026-02-09 | Anwar | [7 empty] | 8:30 | 12:00 | 3.5
Bay 6 - Generator | 2026-02-09 | Suraj | Generator | GEN240-010/015 | PDI & flowfinity/ bracket cover bolt welding. | 2026-01-09 | 2026-01-09 |  |  | 13:30 | 14:30 | 1 | Completed
Bay 6 - Generator | 2026-02-09 | Suraj | Other | General work | General work & system work. | 2026-01-09 | 2026-01-09 |  |  | 16:30 | 17:30 | 1 | Ongoing
Bay 6 - Generator | 2026-02-09 | Mamun | Diesel Driven CP Pump | HL260M-004 | Inspection & fuel tank cleaning. | 2026-02-09 | 2026-02-09 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-09 | Anwar | Diesel Driven CP Pump | CD300M-015 | water test | 2026-02-09 | 2026-02-09 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-09 | Zaheer | Diesel Driven CP Pump | SCT700-01 | Making a new SKD PUMP | 2026-02-06 | 2026-02-15 |  |  | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-02-09 | Vinod | [7 empty] | 6:30 | 17:30 | 11
Bay 4&5 - Pumps | 2026-02-09 | Bilal | Diesel Driven CP Pump | SCT700-01 | Making a new SKD PUMP | 2026-02-06 | 2026-02-15 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-09 | Martino | Diesel Driven CP Pump | CD300M-015 | Installation, water & vaccum test | 2026-02-09 | 2026-02-09 |  |  | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-09 | Mintu | Contractor dewatering Pump | CP150V-040 | Cylinder head assembling | 2026-02-02 | 2026-02-09 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-09 | Bharathesha | Contractor dewatering Pump | CP150x2 | Engine fixing on pump with all connections. | 2026-02-09 | 2026-02-09 |  |  | 6:30 | 14:30 | 8 | Completed
Bay 4&5 - Pumps | 2026-02-09 | Harish | Contractor dewatering Pump | CP150-704 | Engine dismantling. | 2026-02-09 | 2026-02-09 |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-09 | ISmail | Contractor dewatering Pump | CP150V-004 | Pump & engine repair | 2026-02-06 | 2026-02-09 |  |  | 6:30 | 14:30 | 8 | Completed
Bay 4&5 - Pumps | 2026-02-09 | Shaji | [7 empty] | 6:30 | 14:30 | 8
Bay 4&5 - Pumps | 2026-02-09 | ISmail | Contractor dewatering Pump | CP150-250 | Final fitting | 2026-02-09 | 2026-02-09 |  |  | 14:30 | 15:30 | 1 | Completed
Bay 4&5 - Pumps | 2026-02-09 | James | Contractor dewatering Pump | CP150-661 | Floaded engine dismantling. | 2026-02-09 | 2026-02-09 |  |  | 8:30 | 15:30 | 7 | Completed
Electrical | 2026-02-10 | Lijo | Panel | SPB3.7-029 | Repair & test | 2026-01-10 | 2026-01-10 |  |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-02-10 | Shahanawaz | Panel | SPB3.7-058 | Repair & test | 2026-01-10 | 2026-01-10 |  |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-02-10 | Sulaiman | Panel | SCP141-228 | Repair & test | 2026-01-10 | 2026-01-10 |  |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-02-10 | Cherith | Generator | GENJ250-040 | Slot paper & coil making | 2026-02-05 | 2026-02-11 |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-02-10 | Aman | " | " | Slot paper & coil making | 2026-02-05 | 2026-02-11 |  |  | 6:30 | 17:30 | 11 | "
Electrical | 2026-02-10 | Gihan | Submersible pump | SM530-353 | Winding stator cleaning & slot paper making | 2026-01-09 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Hold
Electrical | 2026-02-10 | Donald | Submersible pump | SSD18-002 | Rotor repairing & assemble | 2026-01-10 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-10 | Venu | Submersible pump | SM530-546 | Pump assemble & water testing. | 2026-01-09 | 2026-01-10 |  |  | 6:30 | 15:30 | 9 | Completed
Electrical | 2026-02-10 | Suhaib | Borehole pump | Old B:H pump | 20nos pump inspection & repair scrap. | 2026-01-10 | 2026-01-10 |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-10 | Afsar | " | " | 20nos pump inspection & repair scrap. | 2026-01-10 | 2026-01-10 |  |  | 8:30 | 17:30 | 9 | "
Electrical | 2026-02-10 | Saqib | Submersible pump | SM1002-200 | Winding stator cleaning & slot paper making | 2026-02-09 | 2026-02-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-10 | Jagdev | Generator | GENS100-067 | Safety Guard removing, radiator washing. | 2026-02-07 | 2026-02-10 |  |  | 6:30 | 8:30 | 2 | Completed
Bay 6 - Generator | 2026-02-10 | Anwar | " | " | Safety Guard removing, radiator washing. | 2026-02-07 | 2026-02-10 |  |  | 6:30 | 8:30 | 2 | "
Bay 6 - Generator | 2026-02-10 | Suraj | Generator | GEN150-021 | Load test, coolant change. | 2026-02-09 | 2026-02-10 |  |  | 8:30 | 10:30 | 2 | Completed
Bay 6 - Generator | 2026-02-10 | Anwar | " | " | Load test, coolant change. | 2026-02-09 | 2026-02-10 |  |  | 8:30 | 10:30 | 2 | "
Bay 6 - Generator | 2026-02-10 | Suraj | Generator | GENG100-009 | Oil Cooler & silencer fitting, load test | 2026-01-27 | 2026-02-10 |  |  | 10:30 | 15:30 | 5 | Completed
Bay 6 - Generator | 2026-02-10 | Anwar | " | " | General work & system work. | 2026-01-27 | 2026-02-10 |  |  | 10:30 | 15:30 | 5 | "
Bay 6 - Generator | 2026-02-10 | Jagdev | Generator | GENJ100-017 | Genera repair, fuel tank & radiator cleaning, Load test | 2026-02-10 | 2026-02-10 |  |  | 8:30 | 12:30 | 4 | Completed
Bay 6 - Generator | 2026-02-10 | Jagdev | Generator | GENG100-024 | Genera repair, fuel tank & radiator cleaning, Load test | 2026-02-10 | 2026-02-10 |  |  | 12:30 | 15:30 | 3 | Completed
Bay 6 - Generator | 2026-02-10 | Suraj | " | " | Genera repair, fuel tank & radiator cleaning, Load test | 2026-02-10 | 2026-02-10 |  |  | 15:30 | 17:30 | 2 | "
Bay 6 - Generator | 2026-02-10 | Martino | Diesel Driven CP Pump | HL260M-004 | Inspection & fuel tank cleaning & vaccum test | 2026-02-10 | 2026-02-13 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 6 - Generator | 2026-02-10 | Anwar | " | " | water test | 2026-02-10 | 2026-02-13 |  |  | 8:30 | 17:30 | 9 | "
Bay 4&5 - Pumps | 2026-02-10 | Zaheer | Diesel Driven CP Pump | SKD250 | Making a new SKD PUMP | 2026-02-10 | 2026-02-15 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-10 | Vinod | " | " |  | 2026-02-10 | 2026-02-15 |  |  | 6:30 | 17:30 | 11 | "
Bay 4&5 - Pumps | 2026-02-10 | Bilal | Diesel Driven CP Pump | SKD250 | Making a new SKD PUMP | 2026-02-10 | 2026-02-15 |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-10 | Mamun | Diesel Driven CP Pump | SKD250 | Making a new SKD PUMP | 2026-02-10 | 2026-02-15 |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-10 | Mintu | Contractor dewatering Pump | CP150V-040 | Engine top over hauling ongoing | 2026-02-07 | 2026-02-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-10 | Shaji | " | " | [5 empty] | 6:30 | 8:30 | 2
Bay 4&5 - Pumps | 2026-02-10 | Bharathesha | Contractor dewatering Pump | CP150x2 | Engine fixing on pump with all connections. | 2026-02-10 | 2026-02-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-10 | Harish | Contractor dewatering Pump | CP150-704 | Engine dismantling & pump repair | 2026-02-09 | 2026-02-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-10 | ISmail | Contractor dewatering Pump | CP150-507 | Pump overhauling | 2026-02-10 | 2026-02-10 |  |  | 10:30 | 17:30 | 7 | Completed
Bay 4&5 - Pumps | 2026-02-10 | Shaji | " | " | Pump overhauling | 2026-02-10 | 2026-02-10 |  |  | 8:30 | 10:30 | 2 | "
Bay 4&5 - Pumps | 2026-02-10 | Ismail | Contractor dewatering Pump | CP150-707 | Engine & pump minor repair |  |  |  |  | 6:30 | 10:30 | 4 | Completed
Bay 4&5 - Pumps | 2026-02-10 | James | Contractor dewatering Pump | CP150-661 | Floaded engine dismantling. | 2026-02-09 | 2026-02-10 |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-10 | Shaji | " | " | Pump overhauling | 2026-02-09 | 2026-02-10 |  |  | 13:00 | 14:00 | 1 | "
Bay 4&5 - Pumps | 2026-02-10 | Shaji | Other | General/System work | MCS work order | 2026-02-10 | 2026-02-10 |  |  | 14:00 | 15:30 | 1.5 | Ongoing
Bay 4&5 - Pumps | 2026-02-10 | Shaji | Contractor dewatering Pump | CP150-783 | [5 empty] | 10:30 | 12:30 | 2 | Completed
Electrical | 2026-02-11 | Vergelin Lijo | Panel | SPB3.7-134 | Repair & test |  |  |  |  | 8:30 | 10:30 | 2 | Completed
Electrical | 2026-02-11 | Mohammad Shahanwaz | " | " | Repair & test |  |  |  |  | 10:30 | 13:30 | 3 | "
Electrical | 2026-02-11 | Mohammad Shahanwaz | Panel | DB-166 | Repair & test |  |  |  |  | 8:30 | 13:00 | 4.5 | Completed
Electrical | 2026-02-11 | Mohammad Shahanwaz | Panel | SPB2.2-020 | Repair & test |  |  |  |  | 14:00 | 17:30 | 3.5 | Completed
Electrical | 2026-02-11 | Vergelin Lijo | Panel | SPB7.5-194 | Repair & test |  |  |  |  | 10:30 | 13:00 |  | Completed
Electrical | 2026-02-11 | Vergelin Lijo | Panel | SLP138/175 | Repair & test |  |  |  |  | 13:00 | 17:30 |  | Ongoing
Electrical | 2026-02-11 | Suleman Jehan Zeb | " | " | Repair & test |  |  |  |  | 13:00 | 17:30 |  | "
Electrical | 2026-02-11 | Charith Madusanka | Generator | GENJ250-040 | Coil making for rewinding |  |  |  |  | 6:30 | 17:30 | 11 | Ongoing
Electrical | 2026-02-11 | Amanur Rub Farooqui | " | " | Slot paper & coil making |  |  |  |  | 6:30 | 17:30 | 11 | "
Electrical | 2026-02-11 | Charith Madusanka | Other | FM200/300/700 | Inspection & PDI |  |  |  |  | 8:30 | 17:30 |  | Ongoing
Electrical | 2026-02-11 | Amanur Rub Farooqui | " | " | Inspection & PDI |  |  |  |  | 8:30 | 17:30 |  | "
Electrical | 2026-02-11 | Donald | Submersible pump | SSD18-002 | Pump water testing |  |  |  |  | 6:30 | 8:30 | 2 | Completed
Electrical | 2026-02-11 | Venu Maranattu | " | " | Pump water testing |  |  |  |  | 6:30 | 8:30 | 2 | "
Electrical | 2026-02-11 | Venu Maranattu | Submersible pump | SM530-355 | Rotor repairing & pump assemble |  |  |  |  | 8:30 | 15;30 |  | Ongoing
Electrical | 2026-02-11 | Donald | Submersible pump | SM1002-276 | Inspection& pump repair |  |  |  |  | 8:30 | 15;30 |  | Ongoing
Electrical | 2026-02-11 | Afsar Khan Zar Ali Khan | Borehole pump | Old B:H pump | 15nos pump inspection & repair scrap. |  |  |  |  | 8:30 | 17:30 | 9 | Completed
Electrical | 2026-02-11 | Suhaib Puthan Peedikakkal | " | " | 15nos pump inspection & repair scrap. |  |  |  |  | 8:30 | 17:30 | 9 | "
Electrical | 2026-02-11 | Saqib Khan | Submersible pump | SM1002-200 | Coil making for rewinding |  |  |  |  | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-11 | Jagdev Singh | Generator | GENG100-024 | Ac alternator cleaning & service, general repair |  |  |  |  | 6:30 | 12:30 | 6 | Completed
Bay 6 - Generator | 2026-02-11 | Suraj Sunil | Generator | GEN200-014 | Engine oil service, radiator cleaning & washing. |  |  |  |  | 8:30 | 13:30 | 5 | Ongoing
Bay 6 - Generator | 2026-02-11 | Saeed Anwar | " | " | Load test, coolant change. |  |  |  |  | 8:30 | 13:30 | 5 | "
Bay 6 - Generator | 2026-02-11 | Suraj Sunil | Generator | GEN60-041 | Engine block cleaning, load test |  |  |  |  | 13:30 | 17:30 | 4 | Completed
Bay 6 - Generator | 2026-02-11 | Saeed Anwar | " | " | General work & system work. |  |  |  |  | 13:30 | 15:30 | 2 | "
Bay 6 - Generator | 2026-02-11 | Jagdev Singh | Generator | GENS100-067 | Safety guard fixing & final fitting. |  |  |  |  | 8:30 | 12:30 | 4 | Completed
Bay 6 - Generator | 2026-02-11 | Martino Archin Buabin | Diesel Driven CP Pump | HL260M-004 | Water & vaccum test. |  |  |  |  | 8:30 | 17:30 | 9 | Completed
Bay 6 - Generator | 2026-02-11 | Saeed Anwar | " | " | Water & vaccum test. |  |  |  |  | 8:30 | 17:30 | 9 | "
Bay 4&5 - Pumps | 2026-02-11 | Vinod Vijayan | Diesel Driven CP Pump | SKD250 | Making a new SKD PUMP |  |  |  |  | 6:30 | 15:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-11 | Jahir Nurul Islam | " | " | Making a new SKD PUMP |  |  |  |  | 6:30 | 15:30 | 9 | "
Bay 4&5 - Pumps | 2026-02-11 | Mohammad Moniruzzaman | Diesel Driven CP Pump | SKD250 | Pump alignment |  |  |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-11 | Muhammad Billal | Diesel Driven CP Pump | SKD250 | Ready water picks |  |  |  |  | 8:30 | 17:30 | 9 | Completed
Bay 4&5 - Pumps | 2026-02-11 | Haras Hussaon | Contractor dewatering Pump | CP150V-073/015/054 | Final fitting |  |  |  |  | 6:30 | 11:00 | 4.5 | Completed
Bay 4&5 - Pumps | 2026-02-11 | Shaj Muthiraparamibil Balan | " | " | [5 empty] | 6:30 | 8:30 | 2 | "
Bay 4&5 - Pumps | 2026-02-11 | Mintu Kumar | Contractor dewatering Pump | CP150-661 | Engine & pump prepare for assembling. |  |  |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-11 | James Adukutwah | " | " | Engine dismantling & pump repair |  |  |  |  | 6:30 | 17:30 | 11 | "
Bay 4&5 - Pumps | 2026-02-11 | Bharathesha Shubhakara Jain | Contractor dewatering Pump | CP150-539 | Pump prepare for assembling. |  |  |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-11 | Haras Hussaon | Contractor dewatering Pump | CP150V-004/062 | Fuel tank cleaning, final fitting. |  |  |  |  | 11:00 | 16:00 | 5 | Completed
Bay 4&5 - Pumps | 2026-02-11 | Ismail Mostofa | Contractor dewatering Pump | CP150-507 | Pump assembling. |  |  |  |  | 6:30 | 17:30 | 11 | Completed
Bay 4&5 - Pumps | 2026-02-11 | Shaj Muthiraparamibil Balan | Other | General/System work | General work & system work. |  |  |  |  | 8:30 | 15:30 | 7 | Completed
Electrical | 2026-02-12 | Vergelin Lijo | Panel | SCP-138 | Repair & test | 8:30 | 10:30 | 2 | Completed | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-12 | Mohammad Shahanwaz | Panel | SCP-175 | Repair & test | 8:30 | 13:00 | 4.5 | Completed | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-12 | Charith Madusanka | Other | FM300/700 | Inspection & PDI | 6:30 | 17:30 | 11 | Ongoing | 6:30 | 13:00 | 6.5 | Ongoing
Electrical | 2026-02-12 | Amanur Rub Farooqui | " | " | Slot paper & coil making | 6:30 | 17:30 | 11 | " | 6:30 | 13:00 | 6.5 | "
Electrical | 2026-02-12 | Charith Madusanka | Other | FM200/300/700 | Inspection & PDI | 8:30 | 17:30 |  | Ongoing | 8:30 | 17:30 |  | Ongoing
Electrical | 2026-02-12 | Amanur Rub Farooqui | " | " | Inspection & PDI | 8:30 | 17:30 |  | " | 8:30 | 17:30 |  | "
Electrical | 2026-02-12 | Donald | Submersible pump | SM1002-276 | Inspection & pump repair | 6:30 | 8:30 | 2 | Completed | 6:30 | 12:00 | 5.5 | Completed
Electrical | 2026-02-12 | Venu Maranattu | Submersible pump | SM530-355 | Rotor repairing & pump assemble | 8:30 | 15;30 |  | Ongoing | 8:30 | 12:00 | 3.5 | Completed
Electrical | 2026-02-12 | Donald | Submersible pump | SM1002-276 | Inspection& pump repair | 8:30 | 15;30 |  | Ongoing | 8:30 | 12:00 | 3.5 | Ongoing
Electrical | 2026-02-12 | Donald | Submersible pump | SF300-001 | Inspection & PDI |  |  |  |  | 12:00 | 15:30 | 3.5 | Ongoing
Electrical | 2026-02-12 | Venu Maranattu | " | " | Inspection & PDI |  |  |  |  | 12:00 | 15:30 | 3.5 | "
Electrical | 2026-02-12 | Afsar Khan Zar Ali Khan | Borehole pump | Old B:H pump | 15nos pump inspection & repair scrap. | 8:30 | 17:30 | 9 | Completed | 8:30 | 17:30 | 9 | Ongoing
Electrical | 2026-02-12 | Suhaib Puthan Peedikakkal | " | " | 15nos pump inspection & repair scrap. | 8:30 | 17:30 | 9 | " | 8:30 | 17:30 | 9 | "
Electrical | 2026-02-12 | Saqib Khan | Submersible pump | SM1002-200 | Rewinding & connection. | 6:30 | 15:30 | 9 | Ongoing | 6:30 | 15:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-12 | Suraj Sunil | Generator | GENG100-024 | Ac alternator cleaning & service, general repair | 6:30 | 12:30 | 6 | Completed | 6:30 | 12:30 | 6 | Completed
Bay 6 - Generator | 2026-02-12 | Suraj Sunil | Generator | GEN150-021 | Fuel tank cleaning & washing. | 8:30 | 13:30 | 5 | Ongoing | 6:30 | 10:30 | 4 | Completed
Bay 6 - Generator | 2026-02-12 | Saeed Anwar | " | " | Load test, coolant change. | 8:30 | 13:30 | 5 | " | 6:30 | 10:30 | 4 | "
Bay 6 - Generator | 2026-02-12 | Suraj Sunil | Generator | GENJ60-065 | General repair & Load test | 13:30 | 17:30 | 4 | Completed | 13:30 | 15:30 | 2 | Ongoing
Bay 6 - Generator | 2026-02-12 | Saeed Anwar | " | " | General repair & Load test | 13:30 | 15:30 | 2 | " | 13:30 | 15:30 | 2 | "
Bay 6 - Generator | 2026-02-12 | Suraj Sunil | Generator | GEN80-016 | General repair & Load test | 8:30 | 12:30 | 4 | Completed | 15:30 | 17:30 | 2 | Ongoing
Bay 6 - Generator | 2026-02-12 | Martino Archin Buabin | Diesel Driven CP Pump | HL260M-004 | Water & vaccum test. | 8:30 | 17:30 | 9 | Completed | 8:30 | 17:30 | 9 | Ongoing
Bay 6 - Generator | 2026-02-12 | Saeed Anwar | " | " | Water & vaccum test. | 8:30 | 17:30 | 9 | " | 8:30 | 17:30 | 9 | "
Bay 4&5 - Pumps | 2026-02-12 | Vinod Vijayan | Diesel Driven CP Pump | SKD250 | Making a new SKD PUMP | 6:30 | 15:30 | 9 | Completed | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-12 | Jahir Nurul Islam | " | " | Making a new SKD PUMP | 6:30 | 15:30 | 9 | " | 6:30 | 15:30 | 9 | "
Bay 4&5 - Pumps | 2026-02-12 | Mohammad Moniruzzaman | Diesel Driven CP Pump | SKD250 | Pump alignment | 6:30 | 17:30 | 11 | Completed | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-02-12 | Muhammad Billal | Diesel Driven CP Pump | SKD250 | Ready water picks | 8:30 | 17:30 | 9 | Completed | 8:30 | 17:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-12 | Bharathesha Shubhakara Jain | Diesel Driven CP Pump | CP150-706/845 | Vaccum pump repair |  |  |  |  | 10:30 | 17:30 | 7 | Ongoing
Bay 4&5 - Pumps | 2026-02-12 | Bharathesha Shubhakara Jain | Diesel Driven CP Pump | CP150-539 | Pump assemble & water testing. |  |  |  |  | 6:30 | 10:00 | 3.5 | Completed
Bay 4&5 - Pumps | 2026-02-12 | Haras Hussaon | Contractor dewatering Pump | CP150V-309 | Pump prepare for assembling. | 6:30 | 11:00 | 4.5 | Completed | 6:30 | 15:30 | 9 | Ongoing
Bay 4&5 - Pumps | 2026-02-12 | Shaj Muthiraparamibil Balan | " | " |  | 6:30 | 8:30 | 2 | " | 6:30 | 8:30 | 2 | "
Bay 4&5 - Pumps | 2026-02-12 | Mintu Kumar | Contractor dewatering Pump | CP150-661 | Engine & pump prepare for assembling. | 6:30 | 17:30 | 11 | Completed | 6:30 | 17:30 | 11 | Ongoing
Bay 4&5 - Pumps | 2026-02-12 | James Adukutwah | " | " | Engine dismantling & pump repair | 6:30 | 17:30 | 11 | " | 6:30 | 17:30 | 11 | "
Bay 4&5 - Pumps | 2026-02-12 | Ismail Mostofa | Contractor dewatering Pump | CP150V-062 | Fuel tank cleaning & repair final fitting. | 6:30 | 17:30 | 11 | Completed | 6:30 | 9:00 | 2.5 | Completed
Bay 4&5 - Pumps | 2026-02-12 | Ismail Mostofa | Contractor dewatering Pump | CP150-879 | pump dismantling. |  |  |  |  | 11:30 | 17:30 | 6 | Ongoing
Bay 4&5 - Pumps | 2026-02-12 | Shaj Muthiraparamibil Balan | Contractor dewatering Pump | ZD900-065 | Final fitting & PDI | 8:30 | 15:30 | 7 | Completed | 9:30 | 11:30 | 2 | Completed

## Sheet3
Emp No | Emp Name
140887 | Asif Mehmood
140219 | Jahir Nurul Islam
142702 | Muhammad Billal
142255 | Ismail Mostofa
142489 | Bharathesha Shubhakara Jain
141002 | Mintu Kumar
142864 | Haras Hussaon
140108 | Shaj Muthiraparamibil Balan
143213 | James Adukutwah
142882 | Suresh Kumar Sudhakaran
140482 | Jagdev Singh
143344 | Saeed Anwar
141191 | Haneefa Kalathingal
142296 | Mohammad Shahanwaz
142570 | Shah Fahad Khan
143010 | Gihan Rasanka Fernando
142716 | Saqib Khan
142858 | Faisal Hussain
143324 | Charith Madusanka
142904 | Venu Maranattu
142105 | Nesdonal Aghedse Chimontoh
140654 | Abdul Mannan Akmot Ali
140151 | Mohammed Abu Taher Late Abu Bakkar
142308 | Mohammed Abdul Hoque
142728 | Tariq Mehmood
142950 | Dinesh Pookat Jayan
142556 | Mohammed Kamrul Hasan
142859 | Azharuddin Ansari
141260 | Suresh Kumar Kalaikattu
140525 | Imran Hussain
141756 | Gurlal Singh
142258 | Abdullah Al Kafi Zisan
141894 | Muhammad Fayam
142893 | Arshad Bhati
141135 | Sushanth Kallipal
142848 | Martino Archin Buabin
142872 | Vinod Vijayan
142744 | Suraj Sunil
142828 | Muhammad Imran
141622 | Amanur Rub Farooqui
142917 | Gulam Murtaza
141775 | Vergelin Lijo
143339 | Suhaib Puthan Peedikakkal
142794 | Mohammad Sajjad
142862 | Shahanavaj Ahmad
142896 | Sonu Gupta
140075 | Paritosh Basu
141004 | Muhammad Shadeed Khan
141044 | Prince Prakash
140184 | Vakkachan
142923 | Gireesh Kumar
142171 | Santhosh Kumar Rajan
141814 | Fletcher Simson
141866 | Suleman Jehan Zeb
140439 | Afsar Khan Zar Ali Khan
142887 | Suresh Vishwakarma
140437 | Mohammad Moniruzzaman
Donald
140373 | Lijo